## e-DPR
e-DPR of Nerua GP, Block -Bharatpur , District- Koriya, Chhattisgarh
A |  | Back ground profile
|  | Micro Watershed code | 2A5G8k5,2A5F9h1,2A5G8k3
|  | District | Koriya
|  | Block | Bharatpur
|  | Gram Panchayat | Nerua
|  | Villages Covered | Nerua,Gidher,Kodwariya,Rajrawal
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) | 551.2
|  | Rainfall (mm) | 1053.5
|  | Soil type | Sandy - Loam
|  | Average Slope | 3-5%, 25-30%
|  | Details of Tributaries | Chuliya Nala,Chuadol Nala,Votham River,Patiya Nala,Balua Dhaar River,Turra Nala,Upka River,Thihai Nala,Ashil Nala,Karhaidol Nala
C |  | DEMOGRAPHIC PROFILE
|  | Total Population | 1170
|  | Total HouseHolds | 319
|  | ST Population | 7
|  | SC Population | 0
D |  | MGNREGA Status
|  | NREGA Job card holders | 444
|  | Person days per year (average of last 3 years) | 17826
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 42
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 46.3
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 44
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) | 229.6
|  | Multi cropped (Ha) | 3.5
|  | Current fallow(Ha) | 69.3
|  | Forest /Plantation (Ha) | 211.4
|  | Waste land (Ha) | 17.5
|  | Impounded Waterbody (Ha) | 12.065
|  | Others (Ha) | 23.6
F |  | LAND CLASSIFICATION
|  | Forest (Ha) | 211.4
|  | Upland (Ha) | 126.58
|  | Medium land (Ha) | 387.62
|  | Low Land (Ha) | 37
|  | River Stream Length (m) | 1000
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds | 15
|  | Borewells | 0
|  | Open wells | 28
H |  | Livelihood profile
|  | Agriculture | 57%
|  | Off Farm Activities | 4%
|  | Wages, labour | 34%
|  | Business | 2%
|  | Service/ job | 3%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) | 52.65
|  | Total Water Available (Ham) | 11.47
|  | Water Resource to be created (Ham) | 41.18
|  | Water Resourse Planned ( Ha M) | 52.58
|  | % of Water requirment fulfilled though MWS | 127.7%
J |  | EXPECTED OUTCOME
|  | Increase in Cropping area (in Ha) | 45
|  | Increase in Irrigated area (in Ha) | 42
|  | Income Enhancement (INR 50,000 per annum as additional income) | 35 HHs
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Beneficiary | No. | Dimension |  |  | Estimated cost (lakh) | Estimated labour cost | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
|  |  |  | Length (m) | Width (m) | Depth (m) | Lakh Rs. | Lakh Rs. | days | in Ha | in decimal | in decimal
Individual Works:
Nerua
1 | मेडबन्धान | रामप्रसाद / छोटेलाल | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7518 | 82.0215 | 1
2 | मेडबन्धान | रामसिंह / रनबहादुर | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7523 | 82.0223 | 1
3 | मेडबन्धान | बुद्धसेन / जियावन | 5 | 275 | 1.15 | 0.75 | 0.561 | 0.5335 | 303.125 | 0.375 | 23.7501 | 82.0191 | 1
4 | मेडबन्धान | कृपालसिंह / तुलसी | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.18 | 23.7492 | 82.019 | 1
5 | डबरी | कृपालसिंह / तुलसी | 1 | 20 | 25 | 3 | 1.811 | 1.6538 | 939.6818 | 1.25 | 23.7492 | 82.1881 | 1
6 | मेडबन्धान | दीपचन्द्र / फूलचन्द्र | 3 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.48 | 23.7478 | 82.0189 | 1
7 | मेडबन्धान | मायाराम / ललई | 5 | 175 | 1.15 | 0.75 | 0.357 | 0.3395 | 192.8977 | 0.15 | 23.7461 | 82.0195 | 1
8 | मेडबन्धान | सुरेश / बुधराम | 6 | 270 | 1.15 | 0.75 | 0.5508 | 0.5238 | 297.6136 | 0.3 | 23.7463 | 82.0193 | 1
9 | मेडबन्धान | शिवमंगल / बुद्धू | 7 | 490 | 1.15 | 0.75 | 0.9996 | 0.9506 | 540.1136 | 0.84 | 23.7458 | 82.0189 | 1
10 | मेडबन्धान | फुलिया / तेजई | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7495 | 82.0168 | 1
11 | मेडबन्धान | श्री चन्द्र / हीरासिंह | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7496 | 82.0156 | 1
12 | मेडबन्धान | जयनारायण / राजाराम | 1 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.0625 | 23.7494 | 82.0156 | 1
13 | मेडबन्धान | विजयसिंह / राजाराम | 1 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.0625 | 23.7489 | 82.0157 | 1
14 | मेडबन्धान | लक्ष्मण / राजाराम | 1 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.0225 | 23.7489 | 82.0153 | 1
15 | मेडबन्धान | लक्ष्मण / राजाराम | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7488 | 82.016 | 1
16 | मेडबन्धान | सुदर्शन / जैना पति | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.18 | 23.7494 | 82.0134 | 1
17 | मेडबन्धान | सुदर्शन / जैना पति | 4 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.16 | 23.7494 | 82.0154 | 1
18 | मेडबन्धान | रामसिंह / रनबहादुर | 3 | 45 | 1.15 | 0.75 | 0.0918 | 0.0873 | 49.6023 | 0.015 | 23.7483 | 82.0146 | 1
19 | मेडबन्धान | गोपीचन्द्र / रामधनी | 4 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.12 | 23.7489 | 82.0146 | 1
20 | मेडबन्धान | मानसिंह / जेतराम | 3 | 75 | 1.15 | 0.75 | 0.153 | 0.1455 | 82.6705 | 0.045 | 23.7485 | 82.0197 | 1
21 | मेडबन्धान | अमरसिंह / नाहरसिंह | 3 | 45 | 1.15 | 0.75 | 0.0918 | 0.0873 | 49.6023 | 0.015 | 23.7476 | 82.014 | 1
22 | मेडबन्धान | रामसिंह / रनबहादुर | 7 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.63 | 23.7488 | 82.0101 | 1
23 | तालाब निर्माण | अमीरसिंह / धोधा | 1 | 20 | 25 | 3 | 1.97 | 1.65 | 937 | 1.25 | 23.7486 | 82.0114 | 1
24 | मेडबन्धान | रामसुंदर / रामलाल | 6 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.24 | 23.7482 | 82.0175 | 1
25 | मेडबन्धान | सुदर्शन / जैना पति | 5 | 175 | 1.15 | 0.75 | 0.357 | 0.3395 | 192.8977 | 0.15 | 23.7484 | 82.0169 | 1
26 | मेडबन्धान | शंकर / जैना पति | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7482 | 82.0169 | 1
27 | मेडबन्धान | तुलसीसिंह / सुखदेव | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7485 | 82.0162 | 1
28 | मेडबन्धान | लालबहादुर / बीरबली | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7483 | 82.0162 | 1
29 | मेडबन्धान | रामखेलावन / गंगा | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7482 | 82.0161 | 1
30 | मेडबन्धान | सुमेर / झोलीराम | 2 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.32 | 23.749 | 82.0169 | 1
31 | मेडबन्धान | सुमेर / झोलीराम | 4 | 80 | 1.15 | 0.75 | 0.1632 | 0.1552 | 88.1818 | 0.04 | 23.7493 | 82.0166 | 1
32 | मेडबन्धान | रामजियावन / झोलीराम | 3 | 90 | 1.15 | 0.75 | 0.1836 | 0.1746 | 99.2045 | 0.0675 | 23.7494 | 82.0166 | 1
33 | मेडबन्धान | छोटनबाई / रामचरण | 3 | 135 | 1.15 | 0.75 | 0.2754 | 0.2619 | 148.8068 | 0.15 | 23.75 | 82.0163 | 1
34 | मेडबन्धान | अमरसिंह / नाहरसिंह | 6 | 270 | 1.15 | 0.75 | 0.5508 | 0.5238 | 297.6136 | 0.3 | 23.7538 | 82.022 | 1
35 | मेडबन्धान | रामखेलावन / गंगा | 6 | 270 | 1.15 | 0.75 | 0.5508 | 0.5238 | 297.6136 | 0.3 | 23.7574 | 82.0222 | 1
36 | मेडबन्धान | बुद्धराम / रूहटुल | 2 | 80 | 1.15 | 0.75 | 0.1632 | 0.1552 | 88.1818 | 0.08 | 23.7569 | 82.0212 | 1
37 | मेडबन्धान | कृपाल / देवलाल | 4 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.12 | 23.7525 | 82.0203 | 1
38 | मेडबन्धान | मायाराम / ललई | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7524 | 82.0195 | 1
39 | मेडबन्धान | छोटनबाई / रामचरण | 1 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.0225 | 23.7515 | 82.0202 | 1
40 | मेडबन्धान | रामसिंह / अजमेर | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7518 | 82.0202 | 1
41 | मेडबन्धान | बुद्धराम / रूहटुल | 2 | 60 | 1.15 | 0.75 | 0.1224 | 0.1164 | 66.1364 | 0.045 | 23.7515 | 82.0201 | 1
42 | मेडबन्धान | छोटनबाई / रामचरण | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7513 | 82.0201 | 1
43 | मेडबन्धान | बुद्धराम / रूहटुल | 3 | 45 | 1.15 | 0.75 | 0.0918 | 0.0873 | 49.6023 | 0.015 | 23.751 | 82.02 | 1
44 | मेडबन्धान | बुद्धराम / रूहटुल | 2 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.01 | 23.7512 | 82.0197 | 1
45 | मेडबन्धान | छोटनबाई / रामचरण | 2 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.01 | 23.7513 | 82.0195 | 1
46 | मेडबन्धान | रामसिंह / अजमेर | 1 | 15 | 1.15 | 0.75 | 0.0306 | 0.0291 | 16.5341 | 0.005 | 23.7512 | 82.0192 | 1
47 | मेडबन्धान | दयाराम / बैठोल | 3 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.48 | 23.7478 | 82.0194 | 1
48 | एस सी टी | सुमरन / नाहर | 181 | 3 | 0.5 | 0.5 | 0.25537 | 0.18238 | 103.625 | 0.4 | 23.7568 | 82.0118 | 3
49 | मेडबन्धान | सुमरन / नाहर | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.757 | 82.009 | 1
50 | बोल्डर चेक | संतोष / फूलचन्द्र | 3 | 5 | 2.25 | 1 | 0.16114 | 0.14394 | 81.7841 | 0.9 | 23.7554 | 82.0095 | 3
51 | मेडबन्धान | राजमनी सिंह / तिलकधारी | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.754 | 82.0117 | 1
52 | मेडबन्धान | जगदेव / राजाराम | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7538 | 82.0127 | 1
53 | मेडबन्धान | तुलसीसिंह / सुखदेव | 2 | 80 | 1.15 | 0.75 | 0.1632 | 0.1552 | 88.1818 | 0.08 | 23.7546 | 82.0125 | 1
54 | मेडबन्धान | खैरबली / झोलीराम | 2 | 60 | 1.15 | 0.75 | 0.1224 | 0.1164 | 66.1364 | 0.045 | 23.7549 | 82.013 | 1
55 | मेडबन्धान | सुमेर / झोलीराम | 2 | 80 | 1.15 | 0.75 | 0.1632 | 0.1552 | 88.1818 | 0.08 | 23.7551 | 82.0131 | 1
56 | मेडबन्धान | रामजियावन / झोलीराम | 2 | 60 | 1.15 | 0.75 | 0.1224 | 0.1164 | 66.1364 | 0.045 | 23.7558 | 82.0136 | 1
57 | मेडबन्धान | रामजियावन / झोलीराम | 3 | 45 | 1.15 | 0.75 | 0.0918 | 0.0873 | 49.6023 | 0.015 | 23.7549 | 82.0138 | 1
58 | मेडबन्धान | सुमेर / झोलीराम | 2 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.03 | 23.7547 | 82.0141 | 1
59 | मेडबन्धान | बुद्धसेन / टुबुल | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7546 | 82.0143 | 1
60 | मेडबन्धान | राजमनी सिंह / तिलकधारी | 2 | 110 | 1.15 | 0.75 | 0.2244 | 0.2134 | 121.25 | 0.15 | 23.7551 | 82.6173 | 1
61 | मेडबन्धान | रामसिंह / अजमेर | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7556 | 82.0154 | 1
62 | मेडबन्धान | बूटनबाई / रामचरण | 2 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.03 | 23.7555 | 82.0156 | 1
63 | मेडबन्धान | बुद्धराम / रूहटुल | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7551 | 82.0155 | 1
64 | मेडबन्धान | देवलाल / रामधनी | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7547 | 82.0155 | 1
65 | मेडबन्धान | विकनू / रूहटुल | 1 | 35 | 1.15 | 0.75 | 0.0714 | 0.0679 | 38.5795 | 0.03 | 23.755 | 82.015 | 1
66 | मेडबन्धान | बुद्धराम / रूहटुल | 1 | 35 | 1.15 | 0.75 | 0.0714 | 0.0679 | 38.5795 | 0.03 | 23.7552 | 82.0151 | 1
67 | मेडबन्धान | रामजियावन / झोलीराम | 2 | 110 | 1.15 | 0.75 | 0.2244 | 0.2134 | 121.25 | 0.15 | 23.7551 | 82.0147 | 1
68 | मेडबन्धान | खैरबली / झोलीराम | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.18 | 23.7563 | 82.0141 | 1
69 | मेडबन्धान | रघुबीर / धोली | 2 | 90 | 1.15 | 0.75 | 0.1836 | 0.1746 | 99.2045 | 0.09 | 23.7561 | 82.0141 | 1
70 | मेडबन्धान | जयसिंह जगजाहिर | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7562 | 82.0136 | 1
71 | मेडबन्धान | सुमरन / नाहर | 5 | 250 | 1.15 | 0.75 | 0.51 | 0.485 | 275.5682 | 0.3125 | 23.7559 | 82.013 | 1
72 | मेडबन्धान | सुमरन / नाहर | 5 | 250 | 1.15 | 0.75 | 0.51 | 0.485 | 275.5682 | 0.3125 | 23.7562 | 82.0124 | 1
73 | मेडबन्धान | सुमरन / नाहर | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7565 | 82.0121 | 1
74 | मेडबन्धान | विकनू / रूहटुल | 1 | 60 | 1.15 | 0.75 | 0.1224 | 0.1164 | 66.1364 | 0.09 | 23.7542 | 82.014 | 1
75 | मेडबन्धान | बुद्धराम / रूहटुल | 1 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.0225 | 23.7543 | 82.0139 | 1
76 | मेडबन्धान | रामसिंह / अजमेर | 1 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.0225 | 23.7543 | 82.0136 | 1
77 | मेडबन्धान | छोटनबाई / रामचरण | 1 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.0225 | 23.7541 | 82.0135 | 1
78 | मेडबन्धान | विकनू / रूहटुल | 1 | 35 | 1.15 | 0.75 | 0.0714 | 0.0679 | 38.5795 | 0.03 | 23.754 | 82.0134 | 1
79 | मेडबन्धान | बुद्धराम / रूहटुल | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7542 | 82.0133 | 1
80 | मेडबन्धान | छोटनबाई / रामचरण | 1 | 15 | 1.15 | 0.75 | 0.0306 | 0.0291 | 16.5341 | 0.005 | 23.7539 | 82.0131 | 1
81 | मेडबन्धान | शंकर / जैना पति | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.7534 | 82.0135 | 1
82 | मेडबन्धान | गोपीचन्द्र / रामधनी | 5 | 250 | 1.15 | 0.75 | 0.51 | 0.485 | 275.5682 | 0.3125 | 23.7534 | 82.013 | 1
83 | मेडबन्धान | हीरासिंह / जयपाल | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.25 | 23.7536 | 82.013 | 1
84 | मेडबन्धान | विजयसिंह / राजाराम | 1 | 25 | 1.15 | 0.75 | 0.051 | 0.0485 | 27.5568 | 0.015 | 23.7538 | 82.0129 | 1
85 | मेडबन्धान | सुखसेन / जगदेव | 2 | 60 | 1.15 | 0.75 | 0.1224 | 0.1164 | 66.1364 | 0.045 | 23.7538 | 82.0127 | 1
86 | मेडबन्धान | विजयसिंह / राजाराम | 2 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.03 | 23.754 | 82.0122 | 1
87 | मेडबन्धान | गोपीचन्द्र / रामधनी | 2 | 90 | 1.15 | 0.75 | 0.1836 | 0.1746 | 99.2045 | 0.1 | 23.7534 | 82.0116 | 1
88 | मेडबन्धान | विजयसिंह / राजाराम | 12 | 840 | 1.15 | 0.75 | 1.7136 | 1.6296 | 925.9091 | 1.44 | 23.7523 | 82.0113 | 1
89 | मेडबन्धान | दीपचन्द्र हीरा सिंह | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7523 | 82.0125 | 1
90 | मेडबन्धान | शंकर / जैना पति | 4 | 220 | 1.15 | 0.75 | 0.4488 | 0.4268 | 242.5 | 0.3 | 23.7514 | 82.0148 | 1
91 | मेडबन्धान | रामजियावन / झोलीराम | 2 | 110 | 1.15 | 0.75 | 0.2244 | 0.2134 | 121.25 | 0.15 | 23.7524 | 82.015 | 1
92 | मेडबन्धान | खैरबली / झोलीराम | 1 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.0625 | 23.7525 | 82.015 | 1
93 | मेडबन्धान | शंकर / जैना पति | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.754 | 82.0184 | 1
94 | मेडबन्धान | श्री चन्द्र / हीरासिंह | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7541 | 82.0191 | 1
95 | मेडबन्धान | अमरसिंह / नाहरसिंह | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.25 | 23.7535 | 82.0181 | 1
96 | मेडबन्धान | गोपीचन्द्र / रामधनी | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.25 | 23.7542 | 82.0203 | 1
97 | मेडबन्धान | दीपचन्द्र / हीरासिंह | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7541 | 82.0208 | 1
98 | मेडबन्धान | शंकर / जैनापति | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.754 | 82.0213 | 1
99 | मेडबन्धान | तुलसीसिंह / सुखदेव | 4 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.16 | 23.7562 | 82.0197 | 1
100 | मेडबन्धान | विकनू / रूहटुल | 4 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.16 | 23.7569 | 82.0192 | 1
101 | मेडबन्धान | विकनू / रूहटुल | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7574 | 82.0195 | 1
102 | मेडबन्धान | विकनू / रूहटुल | 1 | 30 | 1.15 | 0.75 | 0.0612 | 0.0582 | 33.0682 | 0.0225 | 23.7565 | 82.0211 | 1
103 | मेडबन्धान | रामभजन / रामरत्न | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.1875 | 23.7566 | 82.0224 | 1
104 | मेडबन्धान | विकनू / रूहटुल | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7553 | 81.0228 | 1
105 | मेडबन्धान | रामभजन / रामरत्न | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7561 | 82.0226 | 1
106 | मेडबन्धान | रामभजन / रामरत्न | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.1875 | 23.7552 | 82.023 | 1
107 | मेडबन्धान | रामसिंह / अजमेर | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.1875 | 23.7554 | 82.0226 | 1
108 | मेडबन्धान | छुटनबाई / रामचरण | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.7552 | 82.0226 | 1
109 | मेडबन्धान | बुधसेन /टुबुल | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7554 | 82.0207 | 1
110 | मेडबन्धान | विकनू / रूहटुल | 1 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.06 | 23.7556 | 82.0202 | 1
111 | मेडबन्धान | बुधसेन /टुबुल | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.756 | 82.0193 | 1
112 | मेडबन्धान | अमरसिंह / नाहरसिंह | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7559 | 82.0169 | 1
113 | कुंआ | रामभजन / रामरत्न | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7578 | 82.0164 | 1
114 | मेडबन्धान | धनीमान / जयलाल | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.7542 | 82.0147 | 1
115 | मेडबन्धान | धनीमान / जयलाल | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.18 | 23.7542 | 82.0147 | 1
116 | मेडबन्धान | रामसिंह / अजमेर | 1 | 25 | 1.15 | 0.75 | 0.051 | 0.0485 | 27.5568 | 0.015 | 23.7544 | 82.014 | 1
117 | मेडबन्धान | छोटनबाई / रामचरण | 1 | 25 | 1.15 | 0.75 | 0.051 | 0.0485 | 27.5568 | 0.015 | 23.7543 | 82.014 | 1
118 | मेडबन्धान | सुदर्शन / जैना पति | 7 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.4375 | 23.7566 | 82.0138 | 1
119 | कुंआ | सुदर्शन / जैना पति | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7571 | 82.0137 | 1
120 | मेडबन्धान | सुदर्शन / जैना पति | 4 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.16 | 23.7578 | 82.0128 | 1
121 | मेडबन्धान | वीरनसिंह / झोलीराम | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7582 | 82.0115 | 1
122 | बोल्डर चेक | सुदर्शन / जैना पति | 5 | 5 | 2.25 | 1 | 0.26188 | 0.23989 | 136.3011 | 1.5 | 23.7582 | 82.0127 | 3
123 | मेडबन्धान | बैराग / जीतराम | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.758 | 82.0133 | 1
124 | सी सी टी | बैराग / जीतराम | 181 | 5 | 0.5 | 0.5 | 0.2668 | 0.193 | 109.6591 | 0.4 | 23.7574 | 82.0128 | 2
125 | गेबियन | रामजियावन / झोलीराम | 1 | 8 | 1.5 | 1 | 0.76 | 0.24 | 136.3636 | 1 | 23.7586 | 82.0142 | 2
126 | मेडबन्धान | सोमलाल / बंसा | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7585 | 82.0143 | 1
127 | मेडबन्धान | सोमलाल / बंसा | 7 | 490 | 1.15 | 0.75 | 0.9996 | 0.9506 | 540.1136 | 0.84 | 23.7577 | 82.0143 | 1
128 | मेडबन्धान | रामभजन / रामरत्न | 6 | 120 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7583 | 82.0155 | 1
129 | मेडबन्धान | कुशीयालसिंह / बुधीलाल | 7 | 490 | 1.15 | 0.75 | 0.9996 | 0.9506 | 540.1136 | 0.84 | 23.7575 | 82.0135 | 1
130 | कुंआ | कुशीयालसिंह / बुधीलाल | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7568 | 82.0165 | 1
131 | मेडबन्धान | विकनू / रूहटुल | 3 | 165 | 1.15 | 0.75 | 0.3366 | 0.3201 | 181.875 | 0.225 | 23.7584 | 82.0175 | 1
132 | डबरी | विकनू / रूहटुल | 1 | 20 | 25 | 3 | 1.811 | 1.6538 | 939.6818 | 1.25 | 23.7584 | 82.0174 | 1
133 | मेडबन्धान | बुधराम / रूहटुल | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.7582 | 82.0177 | 1
134 | मेडबन्धान | रामसिंह/ अजमेर | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.758 | 82.0181 | 1
135 | मेडबन्धान | तुलसीसिंह / सुखदेव | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7566 | 82.0187 | 1
136 | मेडबन्धान | मानसिंह / जेतराम | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7477 | 82.0121 | 1
137 | मेडबन्धान | सुदर्शन / जैना पति | 5 | 275 | 1.15 | 0.75 | 0.561 | 0.5335 | 303.125 | 0.375 | 23.7474 | 82.0125 | 1
138 | बोल्डर चेक | रामखेलावन / गंगा | 3 | 5 | 2.25 | 1 | 0.16114 | 0.14394 | 81.7841 | 0.9 | 23.7466 | 82.0125 | 2
139 | मेडबन्धान | बैराग / जीतराम | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7475 | 82.0108 | 1
140 | मेडबन्धान | रघुबीर / धोली | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.7447 | 82.0124 | 1
141 | मेडबन्धान | सुमेर / झोलीराम | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.18 | 23.7453 | 82.0123 | 1
142 | मेडबन्धान | रामजियावन / झोलीराम | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7451 | 82.0122 | 1
143 | मेडबन्धान | खैरबली / झोलीराम | 1 | 60 | 1.15 | 0.75 | 0.1224 | 0.1164 | 66.1364 | 0.09 | 23.7448 | 82.0122 | 1
144 | मेडबन्धान | रामरति गिरधारी | 8 | 360 | 1.15 | 0.75 | 0.7344 | 0.6984 | 396.8182 | 0.36 | 23.7437 | 82.0125 | 1
145 | मेडबन्धान | शिवनारायण / साधूराम | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7429 | 82.0153 | 1
146 | मेडबन्धान | तुलसीसिंह / सुखदेव | 5 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.6 | 23.7463 | 82.0148 | 1
147 | मेडबन्धान | जयनरायन / राजाराम | 1 | 35 | 1.15 | 0.75 | 0.0714 | 0.0679 | 38.5795 | 0.03 | 23.7471 | 82.0152 | 1
148 | मेडबन्धान | अमीरसिंह / धोधा | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.04 | 23.7469 | 82.0154 | 1
149 | मेडबन्धान | गेंदलाल / सोनई | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.25 | 23.7475 | 82.0158 | 1
150 | मेडबन्धान | शिवनाथ / साधू | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.742 | 82.0161 | 1
151 | मेडबन्धान | रामकुँवारे / मोतीलाल | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7427 | 82.0116 | 1
152 | मेडबन्धान | काशीप्रसाद / देवशरण | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7437 | 82.0115 | 1
153 | मेडबन्धान | लालबहादुर / बीरबली | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.742 | 82.0085 | 1
154 | मेडबन्धान | मनोज / बालकरन | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7438 | 82.0085 | 1
155 | मेडबन्धान | रघुबीर / धोली | 4 | 220 | 1.15 | 0.75 | 0.4488 | 0.4268 | 242.5 | 0.3 | 23.7447 | 82.0073 | 1
156 | मेडबन्धान | लक्ष्मण / देवशरण | 6 | 390 | 1.15 | 0.75 | 0.7956 | 0.7566 | 429.8864 | 0.63 | 23.7436 | 82.0068 | 1
157 | मेडबन्धान | काशीप्रसाद / देवशरण | 12 | 840 | 1.15 | 0.75 | 1.7136 | 1.6296 | 925.9091 | 1.44 | 23.7435 | 82.0059 | 1
158 | डबरी | काशीप्रसाद / देवशरण | 1 | 20 | 25 | 3 | 1.811 | 1.6538 | 939.6818 | 1.25 | 23.7433 | 82.0061 | 1
159 | अर्दन डेम | अमीरसिंह / धोधा | 1 | 40 | 6.5 | 2 | 4.4 | 2.95 | 1676.1364 | 6 | 23.745 | 82.0036 | 4
160 | गेबियन | लालबहादुर / बीरबली | 1 | 8 | 1.5 | 1.5 | 1.19 | 0.39 | 221.5909 | 1 | 23.7431 | 82.0044 | 2
161 | मेडबन्धान | लालबहादुर / बीरबली | 7 | 490 | 1.15 | 0.75 | 0.9996 | 0.9506 | 540.1136 | 0.84 | 23.7423 | 82.005 | 1
162 | बोल्डर चेक | लालबहादुर / बीरबली | 4 | 5 | 2.25 | 1 | 0.21152 | 0.19192 | 109.0455 | 1.2 | 23.7423 | 82.006 | 2
163 | मेडबन्धान | तुलसीसिंह / सुखदेव | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.741 | 82.007 | 1
164 | मेडबन्धान | लालबहादुर / बीरबली | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7407 | 82.0071 | 1
165 | मेडबन्धान | रामखेलावन / गंगा | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7405 | 82.0071 | 1
166 | मेडबन्धान | बुधमान / धनीमान | 4 | 260 | 1.15 | 0.75 | 0.5304 | 0.5044 | 286.5909 | 0.42 | 23.7242 | 82.0572 | 1
167 | मेडबन्धान | बुधमान / धनीमान | 3 | 195 | 1.15 | 0.75 | 0.3978 | 0.3783 | 214.9432 | 0.315 | 23.7507 | 82.019 | 1
168 | मेडबन्धान | अमीरसिंह / धोधा | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7475 | 82.0174 | 1
169 | मेडबन्धान | रामनरेश / भोलाराम | 12 | 840 | 1.15 | 0.75 | 1.7136 | 1.6296 | 925.9091 | 1.44 | 23.7462 | 82.0157 | 1
170 | मेडबन्धान | रामनरेश / भोलाराम | 5 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.6 | 23.7437 | 82.0169 | 1
171 | मेडबन्धान | रामनरेश / भोलाराम | 5 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.6 | 23.7449 | 82.017 | 1
172 | मेडबन्धान | बबली / धनुप्रसाद | 2 | 130 | 1.15 | 0.75 | 0.2652 | 0.2522 | 143.2955 | 0.21 | 23.7462 | 82.0157 | 1
173 | मेडबन्धान | रामदास / टिकसाय | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7457 | 82.0163 | 1
174 | मेडबन्धान | रामदास / टिकसाय | 5 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.6 | 23.7442 | 82.0116 | 1
175 | मेडबन्धान | रामदास / टिकसाय | 5 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.6 | 23.7445 | 82.0169 | 1
176 | मेडबन्धान | गोपाल / जयलाल | 5 | 350 | 1.15 | 0.75 | 0.714 | 0.679 | 385.7955 | 0.6 | 23.7391 | 82.0071 | 1
177 | मेडबन्धान | जैतराम /नौसेर | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7398 | 82.0073 | 1
178 | मेडबन्धान | सुखसेनसिंह / रामबरन | 2 | 90 | 1.15 | 0.75 | 0.1836 | 0.1746 | 99.2045 | 0.09 | 23.739 | 82.0081 | 1
179 | मेडबन्धान | सुखलाल / भुर्री | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7382 | 82.0083 | 1
180 | मेडबन्धान | सुखसेन / रामबरन | 2 | 90 | 1.15 | 0.75 | 0.1836 | 0.1746 | 99.2045 | 0.1 | 23.7376 | 82.0082 | 1
181 | मेडबन्धान | बुधमान / धनीमान | 4 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.16 | 23.7375 | 82.0086 | 1
182 | मेडबन्धान | जैतराम /नौसेर | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.25 | 23.7367 | 82.008 | 1
183 | मेडबन्धान | गोपाल / जयलाल | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.125 | 23.7364 | 82.0085 | 1
184 | मेडबन्धान | मानसिंह / जेतराम | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.18 | 23.7363 | 82.0088 | 1
185 | मेडबन्धान | जयनारायण / राजाराम | 6 | 360 | 1.15 | 0.75 | 0.7344 | 0.6984 | 396.8182 | 0.54 | 23.7388 | 82.0103 | 1
186 | मेडबन्धान | गेंदलाल / जयलाल | 4 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.36 | 23.736 | 82.0089 | 1
187 | मेडबन्धान | जैतराम /नौसेर | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7359 | 82.0095 | 1
188 | मेडबन्धान | बुधमान / धनीमान | 4 | 260 | 1.15 | 0.75 | 0.5304 | 0.5044 | 286.5909 | 0.42 | 23.7362 | 82.0095 | 1
189 | मेडबन्धान | सुखसेन / रामबरन | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7363 | 82.01 | 1
190 | मेडबन्धान | रामनारायण / भैयालाल | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.736 | 82.01 | 1
191 | मेडबन्धान | लालबहादुर / बीरबली | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7369 | 82.0117 | 1
192 | मेडबन्धान | सुखसेन / जगदेव | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7374 | 82.0104 | 1
193 | भूमि समतलि करण | रामदयाल /रामनरेश |  |  |  |  | 1.4591 | 1.3148 | 747.04 |  |  |  | 1
194 | भूमि समतलि करण | महाविर / सुखई |  |  |  |  | 1.2002 | 1.1104 | 584.4271 |  |  |  | 1
195 | भूमि समतलि करण | कैलाशिया /रायसिंह |  |  |  |  | 1.1913 | 1.1025 | 580.28 |  |  |  | 1
Community Works:
Nerua
1 | तालाब गहरीकरण | शासकीय भूमि | 1 | 50 | 40 | 2 | 3.4 | 2.6 | 1590.9091 | 5.2 | 23.7487 | 82.0157 | 4
2 | अर्दन डेम | शासकीय भूमि | 1 | 50 | 6.5 | 1 | 4.8 | 3.2 | 1818 | 4.5 | 23.7562 | 82.0091 | 3
3 | बोल्डर चेक | शासकीय भूमि | 5 | 5 | 2.25 | 1 | 0.26188 | 0.23989 | 136.3011 | 1.5 | 23.7546 | 82.0095 | 2
4 | 30*40 | शासकीय भूमि | 44 | 9.14 | 12.19 |  | 0.79492 | 0.6508 | 369.7727 | 0.48 | 23.7532 | 82.0137 | 2
5 | तालाब गहरीकरण | शासकीय भूमि | 1 | 40 | 30 | 2 | 2.5 | 1.8 | 1022.7273 | 3.8 | 23.7536 | 82.0156 | 2
6 | बोल्डर चेक | शासकीय भूमि | 1 | 6 | 2.25 | 1 | 0.07045 | 0.05757 | 32.7102 | 0.3 | 23.7445 | 82.0083 | 2
7 | बोल्डर चेक | शासकीय भूमि | 4 | 4 | 2.25 | 1 | 0.17121 | 0.15353 | 87.233 | 1.2 | 23.7451 | 82.0078 | 2
8 | बोल्डर चेक | शासकीय भूमि | 2 | 2 | 2.25 | 1 | 0.0296 | 0.01192 | 6.7727 | 0.6 | 23.7433 | 82.0044 | 2
9 | बोल्डर चेक | शासकीय भूमि | 5 | 5 | 2.25 | 1 | 0.26188 | 0.23989 | 136.3011 | 1.5 | 23.7411 | 82.0073 | 2
10 | बोल्डर चेक | शासकीय भूमि | 7 | 2 | 2.25 | 1 | 0.15106 | 0.13434 | 76.3295 | 2.1 | 23.7404 | 82.0079 | 2
11 | डबरी | शासकीय भूमि | 1 | 25 | 25 | 3 | 2.2611 | 2.0885 | 1186.6307 | 1.5 | 23.736 | 82.012 | 1
12 | बोल्डर चेक | शासकीय भूमि | 5 | 5 | 2.25 | 1 | 0.625 | 0.25 | 142 | 1.5 | 23.7411 | 82.0073 | 2
13 | बोल्डर चेक | शासकीय भूमि | 7 | 2 | 2.25 | 1 | 0.238 | 0.098 | 55 | 2.1 | 23.7404 | 82.0079 | 2
14 | डबरी | शासकीय भूमि | 1 | 25 | 25 | 3 | 2.3 | 2 | 1136 | 1.5 | 23.736 | 82.012 | 1
15 | तालाब गहरीकरण | शासकीय भूमि |  |  |  |  | 5.7813 | 5.2973 | 3009.8199 |  |  |  | 4
Individual Works:
Gidher
1 | बोल्डर चेक | भगवत / बरनू | 3 | 6 | 2.25 | 1 | 0.19136 | 0.17272 | 98.1364 | 0.9 | 23.7384 | 81.9752 | 1
2 | मेडबन्धान | भगवत / बरनू | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.739 | 81.9764 | 1
3 | मेडबन्धान | रामकुमार / शंकर | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7391 | 81.9781 | 1
4 | बोल्डर चेक | रामकुमार / शंकर | 3 | 3 | 2.25 | 1 | 0.10068 | 0.08636 | 49.0682 | 0.9 | 23.7391 | 81.9781 | 2
5 | बोल्डर चेक | राममिलन / नारायण | 6 | 3 | 2.25 | 1 | 0.19136 | 0.17272 | 98.1364 | 1.8 | 23.7369 | 81.9791 | 2
6 | मेडबन्धान | राममिलन / नारायण | 5 | 400 | 1.15 | 0.75 | 0.816 | 0.776 | 440.9091 | 0.8 | 23.7328 | 81.9782 | 1
7 | मेडबन्धान | विजय / जगजाहिर | 8 | 520 | 1.15 | 0.75 | 1.0608 | 1.0088 | 573.1818 | 0.84 | 23.7372 | 81.9792 | 1
8 | बोल्डर चेक | विजय / जगजाहिर | 2 | 3 | 2.25 | 1 | 0.07045 | 0.05757 | 32.7102 | 0.6 | 23.7371 | 81.9788 | 1
9 | बोल्डर चेक | विकनू / रूहटुल | 2 | 3 | 2.25 | 1 | 0.07045 | 0.05757 | 32.7102 | 0.6 | 23.7363 | 81.9791 | 1
10 | बोल्डर चेक | बुधराम / रूहटूल | 2 | 5 | 2.25 | 1 | 0.11076 | 0.09596 | 54.5227 | 0.6 | 23.7359 | 81.9794 | 1
11 | मेडबन्धान | सुंदरिया / मुबीलाल | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7362 | 81.9796 | 1
12 | मेडबन्धान | पारसराम / मोहरलेसिंह | 5 | 225 | 1.15 | 0.75 | 0.459 | 0.4365 | 248.0114 | 0.25 | 23.7362 | 81.9801 | 1
13 | मेडबन्धान | रामसिंह / अजमेर | 2 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.32 | 23.7372 | 81.9808 | 1
14 | मेडबन्धान | विकनू / रूहटुल | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.7373 | 81.9811 | 1
15 | बोल्डर चेक | विकनू / रूहटुल | 1 | 4 | 2.25 | 1 | 0.0503 | 0.03838 | 21.8068 | 0.3 | 23.7373 | 81.9811 | 1
16 | मेडबन्धान | रामसिंह / अजमेर | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.7374 | 81.9815 | 1
17 | बोल्डर चेक | रामसिंह / अजमेर | 1 | 3 | 2.25 | 1 | 0.04023 | 0.02879 | 16.358 | 0.3 | 23.7374 | 81.9815 | 1
18 | मेडबन्धान | छोटनबाई / विजय | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.7375 | 81.982 | 1
19 | मेडबन्धान | राममिलन / नारायण | 4 | 260 | 1.15 | 0.75 | 0.5304 | 0.5044 | 286.5909 | 0.42 | 23.7376 | 81.9823 | 1
20 | मेडबन्धान | दीपचन्द्र / जयलाल | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7376 | 81.9834 | 1
21 | मेडबन्धान | भगवत / बरनू | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7369 | 81.9832 | 1
22 | मेडबन्धान | इंद्रपाल | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7369 | 81.9832 | 1
23 | बोल्डर चेक | इंद्रपाल | 2 | 6 | 2.25 | 1 | 0.13091 | 0.11515 | 65.4261 | 0.6 | 23.7366 | 81.9818 | 1
24 | कुंआ | भगवत / बरनू | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7382 | 81.9837 | 1
25 | मेडबन्धान | राममिलन / नारायण | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7382 | 81.9839 | 1
26 | मेडबन्धान | पारसराम / मोहरलेसिंह | 2 | 160 | 1.15 | 0.75 | 0.3264 | 0.3104 | 176.3636 | 0.3 | 23.7376 | 81.9848 | 1
27 | मेडबन्धान | सुखसेन / मोतीलाल | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7361 | 81.985 | 1
28 | मेडबन्धान | पारसराम / मोहरलेसिंह | 4 | 260 | 1.15 | 0.75 | 0.5304 | 0.5044 | 286.5909 | 0.42 | 23.7362 | 81.9856 | 1
29 | मेडबन्धान | पारसराम / मोहरलेसिंह | 6 | 360 | 1.15 | 0.75 | 0.7344 | 0.6984 | 396.8182 | 0.54 | 23.7362 | 81.9859 | 1
30 | मेडबन्धान | दीपचन्द्र / जयलाल | 3 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.48 | 23.7386 | 81.9872 | 1
31 | मेडबन्धान | रामफल / ललितराम | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7391 | 81.9873 | 1
32 | कुंआ | दीपचन्द्र / जयलाल | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7391 | 81.9843 | 1
33 | मेडबन्धान | लालसाय / जयराम | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7192 | 81.9791 | 1
34 | मेडबन्धान | उर्मिलासिंह / लालसाय | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7187 | 81.9802 | 1
35 | कुंआ | उर्मिलासिंह / लालसाय | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7184 | 81.9805 | 1
36 | डबरी निर्माण | जगजाहिर / अमीर | 1 | 20 | 20 | 3 | 1.4616 | 1.3165 | 748.0227 | 0.93 | 23.7182 | 81.9816 | 1
37 | मेडबन्धान | जगजाहिर / अमीर | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7182 | 81.9817 | 1
38 | कुंआ | जगजाहिर / अमीर | 1 |  |  |  | 1.8 | 0.67 | 481 | 0.4 | 23.7175 | 81.783 | 1
39 | मेडबन्धान | रामलाल / ललई | 6 | 390 | 1.15 | 0.75 | 0.7956 | 0.7566 | 429.8864 | 0.63 | 23.7184 | 81.9822 | 1
40 | मेडबन्धान | सेमलाल / बोरबाई | 2 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.03 | 23.7191 | 81.9827 | 1
41 | मेडबन्धान | शिशुपल / तकलाजू | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7202 | 81.9829 | 1
42 | मेडबन्धान | राममिलन / नारायण | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7205 | 81.9819 | 1
43 | मेडबन्धान | नानबाई / मुनिलाल | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.24 | 23.722 | 81.9796 | 1
Community Works:
Gidher
1 | ड्रेनेज चैनल | शासकीय भूमि | 1 | 12 | 1 | 1 | 0.0515 | 0.048 | 27 | 0.24 | 23.7386 | 81.975 | 3
2 | ब्रशवुड चेक डेम | शासकीय भूमि | 5 | 3 | 0.5 | 0.5 | 0.07 | 0.03 | 17 | 1 | 23.7383 | 81.976 | 2
3 | 30*40 | शासकीय भूमि | 72 | 9.14 | 12.19 |  | 1.1584 | 0.94748 | 538.3409 | 0.8 | 23.7383 | 81.976 | 2
4 | बोल्डर चेक | शासकीय भूमि | 5 | 3 | 2.25 | 1 | 0.16114 | 0.14394 | 81.7841 | 1.5 | 23.7381 | 81.9773 | 2
5 | 30*40 | शासकीय भूमि | 36 | 9.14 | 12.19 |  | 0.72258 | 0.59686 | 339.125 | 0.4 | 23.7312 | 81.9781 | 2
6 | बोल्डर चेक | शासकीय भूमि | 8 | 6 | 2.25 | 1 | 0.49363 | 0.4606 | 261.7045 | 2.4 | 23.7376 | 81.9776 | 2
7 | बोल्डर चेक | शासकीय भूमि | 2 | 8 | 2.25 | 1 | 0.17121 | 0.15353 | 87.233 | 0.6 | 23.7362 | 81.9787 | 1
8 | स्टाप डेम | शासकीय भूमि | 1 | 15 | 1.25 | 1 | 10.0426 | 3.1114 | 1767.8295 | 6 | 23.7366 | 81.9799 | 4
9 | बोल्डर चेक | शासकीय भूमि | 1 | 8 | 2.25 | 1 | 0.09061 | 0.07677 | 43.6193 | 0.3 | 23.7373 | 81.9867 | 1
10 | बोल्डर चेक | शासकीय भूमि | 2 | 10 | 2.25 | 1 | 0.21152 | 0.19192 | 109.0455 | 0.6 | 23.7375 | 81.9873 | 1
11 | 30*40 | शासकीय भूमि | 135 | 9.14 | 12.19 |  | 1.9211 | 1.5611 | 886.9659 | 1.5 | 23.7788 | 81.9788 | 2
12 | बोल्डर चेक | शासकीय भूमि | 3 | 6 | 2.25 | 1 | 0.19136 | 0.17272 | 98.1364 | 0.9 | 23.7789 | 81.9778 | 2
13 | एस सी टी | शासकीय भूमि | 363 | 3 | 0.5 | 0.5 | 0.45543 | 0.36913 | 209.733 | 0.8 | 23.7173 | 81.9804 | 2
14 | बोल्डर चेक | शासकीय भूमि | 4 | 6 | 2.25 | 1 | 0.25181 | 0.2303 | 130.8523 | 1.2 | 23.7172 | 81.9804 | 2
15 | बोल्डर चेक | शासकीय भूमि | 4 | 8 | 2.25 | 1 | 0.33242 | 0.30707 | 174.4716 | 1.2 | 23.723 | 81.9839 | 2
16 | बोल्डर चेक | शासकीय भूमि | 2 | 4 | 2.25 | 1 | 0.09061 | 0.07677 | 43.6193 | 0.6 | 23.7203 | 81.9839 | 1
Individual Works:
Rajrawal
1 | बोल्डर चेक | बालकरन / बाबूलाल | 3 | 4 | 2.25 | 1 | 0.13091 | 0.11515 | 65.4261 | 0.9 | 23.7425 | 82.0548 | 2
2 | मेडबन्धान | बालकरन / बाबूलाल | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7425 | 82.0548 | 1
3 | मेडबन्धान | कृष्णा / रामदेव | 1 | 40 | 1.15 | 0.75 | 0.0816 | 0.0776 | 44.0909 | 0.0375 | 23.7442 | 82.0548 | 1
4 | बोल्डर चेक | कृष्णा / रामदेव | 1 | 5 | 2.25 | 1 | 0.06038 | 0.04798 | 27.2614 | 0.3 | 23.7442 | 82.0548 | 1
5 | मेडबन्धान | सुभगिया / रामसेवक | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7428 | 82.5343 | 1
6 | मेडबन्धान | अमीरसिंह / भागीरथी | 4 | 180 | 1.15 | 0.75 | 0.6528 | 0.6208 | 352.7273 | 0.64 | 23.7411 | 82.0503 | 1
7 | मेडबन्धान | अमीर सिंह / भागीरथी | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7416 | 82.0478 | 1
8 | मेडबन्धान | महाबीर / सुखई | 2 | 70 | 1.15 | 0.75 | 0.1428 | 0.1358 | 77.1591 | 0.06 | 23.7432 | 82.0476 | 1
9 | मेडबन्धान | जयमंती / मोहन | 6 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.18 | 23.7432 | 82.0476 | 1
10 | मेडबन्धान | बालकरन / बाबूलाल | 3 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.27 | 23.7442 | 82.0482 | 1
11 | मेडबन्धान | धिरपालसिंह / देवलाल | 6 | 840 | 1.15 | 0.75 | 1.7136 | 1.6296 | 925.9091 | 1.98 | 23.7453 | 82.0513 | 1
12 | बोल्डर चेक | जमाहिरसिंह / मुटुकधारी | 2 | 4 | 2.25 | 1 | 0.09061 | 0.07677 | 43.6193 | 0.6 | 23.7445 | 82.0525 | 1
13 | मेडबन्धान | जमाहिरसिंह / मुटुकधारी | 2 | 50 | 1.15 | 0.75 | 0.102 | 0.097 | 55.1136 | 0.03 | 23.7445 | 82.0525 | 1
14 | अर्दन गली प्लग | जमाहिरसिंह / मुटुकधारी | 1 | 8 | 2.75 | 1 | 0.08 | 0.06 | 34 | 0.15 | 23.7445 | 82.0525 | 1
15 | मेडबन्धान | बालकरन / बाबूलाल | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7475 | 82.052 | 1
16 | 30*40 | जमाहिरसिंह / मुटुकधारी | 44 | 9.14 | 12.19 |  | 0.79492 | 0.6508 | 369.7727 | 0.48 | 23.7471 | 82.0529 | 2
17 | बोल्डर चेक | जमाहिरसिंह / मुटुकधारी | 3 | 3 | 2.25 | 1 | 0.10068 | 0.08636 | 49.0682 | 0.9 | 23.7471 | 82.0529 | 2
18 | मेडबन्धान | फूलचन्द्र / मुटुकधारी | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7471 | 82.0533.3 | 1
19 | मेडबन्धान | फूलचन्द्र / मुटुकधारी | 4 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7457 | 82.0541 | 1
20 | मेडबन्धान | फूलचन्द्र / मुटुकधारी | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.7447 | 82.053 | 1
21 | मेडबन्धान | रामलखन / कोसई | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7469 | 82.0488 | 1
22 | मेडबन्धान | लक्ष्मण / रामसेवक | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.742 | 82.0534 | 1
23 | मेडबन्धान | दीपचन्द्र / रामसेवक | 3 | 105 | 1.15 | 0.75 | 0.2142 | 0.2037 | 115.7386 | 0.09 | 23.942 | 82.0534 | 1
24 | मेडबन्धान | सोनकली / रामचन्द्र | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.742 | 82.0528 | 1
25 | मेडबन्धान | विद्यावती / देवप्रताप | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.742 | 82.0526 | 1
26 | मेडबन्धान | रामप्रसाद / समयलाल | 2 | 140 | 1.15 | 0.75 | 0.2856 | 0.2716 | 154.3182 | 0.24 | 23.7415 | 82.0513 | 1
27 | अर्दन गली प्लग | रामप्रसाद / समयलाल | 1 | 10 | 2.75 | 1 | 0.1 | 0.08 | 45 | 0.15 | 23.7416 | 82.0507 | 1
28 | बोल्डर चेक | दुर्गाप्रसाद / समयलाल | 4 | 6 | 2.25 | 1 | 0.25181 | 0.2303 | 130.8523 | 1.2 | 23.7407 | 82.0505 | 2
29 | डबरी | दुर्गाप्रसाद / समयलाल | 1 | 25 | 20 | 3 | 1.9038 | 1.6538 | 939.6818 | 1.15 | 23.7407 | 82.0505 | 1
30 | मेडबन्धान | लक्ष्मण / रामसेवक | 3 | 345 | 1.15 | 0.75 | 0.7038 | 0.6693 | 380.2841 | 0.675 | 23.7428 | 82.0534 | 1
31 | मेडबन्धान | रामचरण / मेहिलाल | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7423 | 82.0505 | 1
32 | मेडबन्धान | बसंत / सुखराम | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7428 | 82.0505 | 1
33 | मेडबन्धान | बुद्धलाल / बाबूलाल | 8 | 360 | 1.15 | 0.75 | 0.7344 | 0.6984 | 396.8182 | 0.4 | 23.7435 | 82.0496 | 1
34 | मेडबन्धान | भैयालाल / भागीरथी | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7429 | 82.0492 | 1
35 | मेडबन्धान | रंगलाल/ जीवनलाल | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7445 | 82.047 | 1
36 | मेडबन्धान | रामकुमार / वंशी | 4 | 280 | 1.15 | 0.75 | 0.5304 | 0.5044 | 286.5909 | 0.42 | 23.7453 | 82.0483 | 1
37 | बोल्डर चेक | रामकुमार / वंशी | 3 | 4 | 2.25 | 1 | 0.3 | 0.12 | 68 | 0.9 | 23.7453 | 82.0483 | 1
38 | मेडबन्धान | समयलाल / रामसिंह | 3 | 195 | 1.15 | 0.75 | 0.3978 | 0.3783 | 214.9432 | 0.315 | 23.7418 | 82.05 | 1
39 | बोल्डर चेक | समयलाल / रामसिंह | 2 | 8 | 2.25 | 1 | 0.17121 | 0.15353 | 87.233 | 0.6 | 23.7418 | 82.05 | 1
40 | बोल्डर चेक | रमबइया / सुखराम | 3 | 5 | 2.25 | 1 | 0.16114 | 0.14394 | 81.7841 | 0.9 | 23.7442 | 82.0513 | 1
41 | मेडबन्धान | महाबीर / सुखई | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7453 | 82.0512 | 1
42 | मेडबन्धान | सुखसेन / बैशाखू | 2 | 120 | 1.15 | 0.75 | 0.2448 | 0.2328 | 132.2727 | 0.16 | 23.753 | 82.0304 | 1
43 | मेडबन्धान | बालकरन / बाबूलाल | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7523 | 82.0289 | 1
44 | मेडबन्धान | जमाहिरसिंह / मुटुकधारी | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7522 | 82.0285 | 1
45 | मेडबन्धान | सुखसेन / बैशाखू | 8 | 560 | 1.15 | 0.75 | 1.1424 | 1.0864 | 617.2727 | 0.96 | 23.7524 | 82.0276 | 1
46 | मेडबन्धान | बसंतलाल / मिट्ठू | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7534 | 82.0267 | 1
47 | मेडबन्धान | सुखसेन / बैशाखू | 4 | 280 | 1.15 | 0.75 | 0.5712 | 0.5432 | 308.6364 | 0.48 | 23.7535 | 82.0262 | 1
48 | मेडबन्धान | बालकरन / बाबूलाल | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7532 | 82.0261 | 1
49 | मेडबन्धान | गेंदलाल / रामसिंह | 4 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.32 | 23.7526 | 82.0244 | 1
50 | मेडबन्धान | कृपाल / तुलसी | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.753 | 82.024 | 1
51 | डबरी | कृपाल / तुलसी | 1 | 20 | 20 | 3 | 1.6 | 1.4 | 795.4545 | 0.95 | 23.753 | 82.024 | 1
52 | भूमि समतलीकरण | समललाल रिचऊ |  |  |  |  | 1.2636 | 1.1691 | 664.2443 |  |  |  | 1
Community Works:
Rajrawal
1 | बोल्डर चेक | शासकीय भूमि | 3 | 6 | 2.25 | 1 | 0.19136 | 0.17272 | 98.1364 | 0.9 | 23.7443 | 82.0549 | 1
2 | बोल्डर चेक | शासकीय भूमि | 6 | 6 | 2.25 | 0.5 | 0.13097 | 0.11521 | 65.4602 | 1.8 | 23.7409 | 82.0492 | 2
3 | बोल्डर चेक | शासकीय भूमि | 3 | 6 | 2.25 | 1 | 0.19136 | 0.17272 | 98.1364 | 0.9 | 23.7426 | 82.0467 | 1
4 | अर्दन डेम | शासकीय भूमि | 1 | 25 | 6.5 | 2 | 3.85 | 3.2 | 1818 | 2.8 | 23.7459 | 82.0511 | 2
5 | बोल्डर चेक | शासकीय भूमि | 6 | 6 | 2.25 | 1 | 0.37272 | 0.34545 | 196.2784 | 1.8 | 23.7453 | 82.0526 | 3
6 | एस सी टी | शासकीय भूमि | 181 | 3 | 0.5 | 0.5 | 0.25537 | 0.18238 | 103.625 | 0.4 | 23.7479 | 82.0518 | 2
7 | बोल्डर चेक | शासकीय भूमि | 5 | 5 | 2.25 | 1 | 0.26188 | 0.23989 | 136.3011 | 1.5 | 23.7464 | 82.049 | 2
8 | बोल्डर चेक | शासकीय भूमि | 3 | 8 | 2.25 | 1 | 0.25181 | 0.2303 | 130.8523 | 0.9 | 23.7426 | 82.0505 | 2
9 | 30*40 | शासकीय भूमि | 72 | 9.14 | 12.19 |  | 1.1584 | 0.94748 | 538.3409 | 0.8 | 23.7527 | 82.0238 | 2
10 | डबरी निर्माण | शासकीय भूमि |  |  |  |  | 2.1613 | 1.943 | 1103.9706 |  |  |  | 1
11 | डबरी निर्माण | शासकीय भूमि |  |  |  |  | 2.4398 | 2.2909 | 1301.6572 |  |  |  | 1
Individual Works:
Kodwariya
1 | मेडबन्धान | तुलसीसिंह / सुखदेव | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.7471 | 81.9926 | 1
2 | मेडबन्धान | लालबहादुर / बीरबली | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.7471 | 81.9928 | 1
3 | मेडबन्धान | रामखेलावन / गंगा | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.747 | 81.9934 | 1
4 | मेडबन्धान | रामखेलावन / गंगा | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.7467 | 81.9939 | 1
5 | मेडबन्धान | लालबहादुर / बीरबली | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.747 | 81.9953 | 1
6 | मेडबन्धान | तुलसीसिंह / सुखदेव | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.7469 | 81.9958 | 1
7 | मेडबन्धान | जैतराम /नौसेर | 6 | 420 | 1.15 | 0.75 | 0.8568 | 0.8148 | 462.9545 | 0.72 | 23.7464 | 81.9935 | 1
8 | मेडबन्धान | अमीरसिंह / धोधा | 10 | 700 | 1.15 | 0.75 | 1.428 | 1.358 | 771.5909 | 1.2 | 23.7505 | 81.9956 | 1
9 | मेडबन्धान | गोपीचन्द्र / रामधनी | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.12 | 236.7513 | 81.9981 | 1
10 | मेडबन्धान | शुभरन / नाहर | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.7512 | 81.9982 | 1
11 | मेडबन्धान | रामखेलावन / गंगा | 4 | 200 | 1.15 | 0.75 | 0.408 | 0.388 | 220.4545 | 0.25 | 23.7508 | 81.9987 | 1
12 | मेडबन्धान | चन्द्रभान / लालमन | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.18 | 23.751 | 81.9996 | 1
13 | मेडबन्धान | तुलसीसिंह / सुखदेव | 4 | 180 | 1.15 | 0.75 | 0.3672 | 0.3492 | 198.4091 | 0.2 | 23.7512 | 81.9996 | 1
14 | मेडबन्धान | अमीरसिंह / धोधा | 3 | 210 | 1.15 | 0.75 | 0.4284 | 0.4074 | 231.4773 | 0.36 | 23.7513 | 81.9992 | 1
15 | मेडबन्धान | बुधमान / धनीमान | 2 | 100 | 1.15 | 0.75 | 0.204 | 0.194 | 110.2273 | 0.12 | 23.7519 | 81.9995 | 1
16 | मेडबन्धान | सुखसेन / जगदेव | 4 | 240 | 1.15 | 0.75 | 0.4896 | 0.4656 | 264.5455 | 0.36 | 23.7519 | 81.9989 | 1
17 | मेडबन्धान | श्री चन्द्र / हीरासिंह | 3 | 165 | 1.15 | 0.75 | 0.3366 | 0.3201 | 181.875 | 0.225 | 23.7525 | 81.9991 | 1
18 | बोल्डर चेक | अमीरसिंह / धोधा | 3 | 3 | 2.25 | 1 | 0.10068 | 0.08636 | 49.0682 | 0.9 | 23.7558 | 81.001 | 1
19 | मेडबन्धान | अमीरसिंह / धोधा | 3 | 150 | 1.15 | 0.75 | 0.306 | 0.291 | 165.3409 | 0.1875 | 23.7558 | 81.001 | 1
20 | स्टॉप डेम | रामप्रसाद / छोटेलाल | 1 | 20 | 1.25 | 2 | 18.7712 | 5.7159 | 3247.6818 | 8.5 | 23.7563 | 82.8014 | 3
21 | मेडबन्धान | बुधमान / धनीमान | 3 | 135 | 1.15 | 0.75 | 0.2754 | 0.2619 | 148.8068 | 0.15 | 23.7545 | 81.9989 | 1
22 | मेडबन्धान | सुदर्शन / जैना पति | 7 | 490 | 1.15 | 0.75 | 0.9996 | 0.9506 | 540.1136 | 0.84 | 23.7541 | 81.9984 | 1
23 | अर्दन डेम | सुखसेन / जगदेव | 1 | 50 | 6.5 | 1 | 4.8 | 3.2 | 1818 | 5.5 | 23.7539 | 81.9969 | 3
24 | मेडबन्धान | बुधमान / धनीमान | 11 | 770 | 1.15 | 0.75 | 1.5708 | 1.4938 | 848.75 | 1.32 | 23.7544 | 81.955 | 1
25 | मेडबन्धान | अमरबहादुर / बेनबहादुर | 7 | 490 | 1.15 | 0.75 | 0.9996 | 0.9506 | 540.1136 | 0.84 | 23.7547 | 81.9937 | 1
Community Works:
Kodwariya
1 | गेबियन | शासकीय भूमि | 1 | 7 | 1.5 | 1 | 0.7105 | 0.2305 | 130.9659 | 1 | 23.7509 | 81.9984 | 2
2 | बोल्डर चेक | शासकीय भूमि | 1 | 2 | 2.25 | 1 | 0.03015 | 0.01919 | 10.9034 | 0.3 | 23.7509 | 81.9984 | 1
3 | स्टॉप डेम | शासकीय भूमि | 1 | 15 | 1.25 | 2 | 15.6567 | 4.8268 | 2742.4886 | 7.2 | 23.7559 | 81.0017 | 3
Total |  |  | 2558 |  |  |  | 262.3647 | 202.4977 | 115775.564 | 220.5075 |  |  | 428

## NREGA Data (hidden)
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Baspattar | [5 empty] | As on 10-06-2020
I Job Card
Total No. of JobCards issued | 302
Total No. of Workers | 1445
Total No. of Active Job Cards | 291
Total No. of Active Workers | 1329
(i)SC worker against active workers[%] | 1.05
(ii)ST worker against active workers[%] | 65.46
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9390 | 37789 | 32713 | 34769 | 15342
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 1.66 | 1.37 | 1.13 | 0.89 | 1.1
ST persondays % as of total persondays | 54.1 | 50.59 | 53.89 | 51.82 | 44.81
Women Persondays out of Total (%) | 47.74 | 48.15 | 47.82 | 51.61 | 51.3
Average days of employment provided per Household | 42.49 | 133.06 | 115.19 | 124.18 | 57.25
Average Wage rate per day per person(Rs.) | 189.85 | 175.93 | 174 | 172 | 167
Total No of HHs completed 100 Days of Wage Employment | 0 | 233 | 204 | 198 | 23
Total Households Worked | 221 | 284 | 284 | 280 | 268
Total Individuals Worked | 455 | 627 | 617 | 606 | 555
Differently abled persons worked | 1 | 4 | 0 | 1 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 47 | 75 | 117 | 85 | 80
Number of Ongoing Works | 19 | 41 | 42 | 44 | 41
Number of Completed Works | 28 | 34 | 75 | 41 | 39
% of NRM Expenditure(Public + Individual) | 83.17 | 85.02 | 77.45 | 86.74 | 69.31
% of Category B Works | 85.11 | 90.67 | 94.02 | 82.35 | 80
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 33.78 | 70.99 | 62.08 | 68.25 | 28.57
Wages(Rs. In Lakhs) | 25.31 | 60.5 | 55.2 | 59.49 | 24.23
Material and skilled Wages(Rs. In Lakhs) | 8.28 | 9.83 | 6.08 | 7.78 | 3.46
Material(%) | 24.65 | 13.98 | 9.92 | 11.56 | 12.51
Total Adm Expenditure (Rs. in Lakhs.) | 0.18 | 0.66 | 0.8 | 0.98 | 0.88
Admin Exp(%) | 0.53 | 0.93 | 1.29 | 1.44 | 3.08
Average Cost Per Day Per Person(In Rs.) | 193.08 | 202 | 176.44 | 195.03 | 178.38
% of Total Expenditure through EFMS | 100 | 100 | 99.98 | 99.73 | 100
% payments gererated within 15 days | 100 | 79.31 | 90.55 | 100 | 45.71

## Calculation (hidden)
Tentative treated area calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | capacity/ volume (In Cum) | Command area (Irrigated Area ) | Minimum required catchment area | Area Treated
|  |  | Dimenssion | in m | in m | in m | In Cum | in Ha | In Ha | In Ha
1 | Farm Pond | शामकुंवर/रामबिशेष | 23X23X3 | 25 | 25 | 3 | 1491.87 | 0.74594 | 1.4919 | 2.2378
2 | Farm Pond | बंदीराम/दयाराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
3 | Farm Pond | आत्माराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
4 | Farm Pond | आत्माराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
5 | Farm Pond | कमितला बाई/सुकडू | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
6 | Farm Pond | बंदीराम/दयाराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
7 | Farm Pond | चैनबती मरकाम/रामदयाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
8 | Farm Pond | रामदयाल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
9 | Farm Pond | सुकमन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
10 | Farm Pond | भागबती | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
11 | Farm Pond | नारायण | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
12 | Farm Pond | नारद | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
13 | Farm Pond | गनेशिया बाई/आनंद राम सोनी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
14 | Farm Pond | नारायण मरकाम/मेहत्तर | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
15 | Farm Pond | सुकलाईन/धनसिंग विश्वकर्मा | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
16 | Farm Pond | बरमन कुलदीप/कंगलाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
17 | Farm Pond | दसरु राम यादव/मेहत्तर यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
18 | Farm Pond | रमेश सोनवानी/राजकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
19 | Farm Pond | पीलादास मरकाम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
20 | Farm Pond | दयमोतीन नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
21 | Farm Pond | अघनसिंह नेताम/तिजिया नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
22 | Farm Pond | रामसिंह वट्टी/केशरी बाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
23 | Farm Pond | प्रभुराम वट्टी/स्वयं | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
24 | Farm Pond | लतखोरीन नेताम/छेरका | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
25 | Farm Pond | मनराखन यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
26 | Farm Pond | मन्नूराम भास्कर/झंगन सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
27 | Farm Pond | पुष्कर/नथेला राम यादव | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
28 | Farm Pond | लक्ष्मी लाल/गनेशिया | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
29 | Farm Pond | नोहर सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
30 | Farm Pond | नोहर सिंह | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
31 | Farm Pond | राजकुमार/सोनूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
32 | Farm Pond | राम/हलाल राम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
33 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
34 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
35 | Farm Pond | झाड़ूराम/लादूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
36 | Farm Pond | झाड़ूराम/लादूराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
37 | Farm Pond | नोहरसिंह/मसिया | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
38 | Farm Pond | फूलसिंह/हीरासिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
39 | Farm Pond | उदेराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
40 | Farm Pond | लक्ष्मण | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
41 | Farm Pond | पिलाराम/रामभरोष | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
42 | Farm Pond | धनीराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
43 | Farm Pond | चमरसिंह /सुरेखा नेताम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
44 | Farm Pond | रामनाथ/रमतुला वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
45 | Farm Pond | नन्दकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
46 | Farm Pond | चमरसिंह/सगन बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
47 | Farm Pond | जयलाल नेताम/अघनबाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
48 | Farm Pond | सुकबाई यादव/स्वयं | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
49 | Farm Pond | सुकबाई यादव/स्वयं | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
50 | Farm Pond | रामजी/मानकी वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
51 | Farm Pond | नवल सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
52 | Farm Pond | नवल यादव/दल्ली यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
53 | Farm Pond | दुर्जन यादव/दिनदयाल | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
54 | Farm Pond | धनेश यादव/धर्मिन | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
55 | Farm Pond | धनेश यादव/धर्मिन | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
56 | Farm Pond | गुहाराम यादव/अहिल्या | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
57 | Farm Pond | छन्नू राम/उषा बाई | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
58 | Farm Pond | छन्नू राम/उषा बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
59 | Farm Pond | लालसाय मंडावी | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
60 | Farm Pond | लक्ष्मीनाथ नेताम/बैजनतीन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
61 | Farm Pond | रामबती/सुकलाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
62 | Farm Pond | शांति बाई/रामसिंग | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
63 | Farm Pond | बिन्देसिंह/रोहीदास | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
64 | Farm Pond | अमरोबाई/रामजी | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
65 | Farm Pond | जयराम/रामचंद | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
66 | Farm Pond | सन्तुराम मंडावी/सवित्री | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
67 | Farm Pond | आनंदराम नेताम/दुखिया | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
68 | Farm Pond | आनंदराम नेताम/दुखिया | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
69 | Farm Pond | दुखिया नेताम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
70 | Farm Pond | संग्राम/रामसिंह | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
71 | Farm Pond | कनसी/सैदर | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
72 | Farm Pond | किसनू/जोहन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
73 | Farm Pond | कौशिल्या/दीपल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
74 | Farm Pond | प्रवीण मरकाम/रामचंद | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
75 | Land levelling | रूपनाथ मरकाम/परमिला मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
76 | Land levelling | राजाराम मरकाम/चंद्रिका मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
77 | Land levelling | अनीत मरकाम/बृजबती | 1.01 | 1.01 | [5 empty] | 1.01
78 | Land levelling | नीलम कुमार/सगारो बाई | 0.8 | 0.8 | [5 empty] | 0.8
79 | Land levelling | अघनसिंह नेताम/तिजिया नेताम | 0.4 | 0.4 | [5 empty] | 0.4
80 | Land levelling | रूपराय मरकाम/रेमा मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
81 | Land levelling | मोहनराम वट्टी/भवनतीन वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
82 | Land levelling | प्रभुराम वट्टी/स्वयं | 0.4 | 0.4 | [5 empty] | 0.4
83 | Land levelling | रामसिंह वट्टी/केशरी बाई | 0.4 | 0.4 | [5 empty] | 0.4
84 | Land levelling | सगनी/देवराज मरकाम | 0.4 | 0.4 | [5 empty] | 0.4
85 | Land levelling | अमरसिंह/परमिला | 0.4 | 0.4 | [5 empty] | 0.4
86 | Land levelling | उदेराम | 0.8 | 0.8 | [5 empty] | 0.8
87 | Land levelling | रामनाथ/रमतुला वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
88 | Land levelling | धनीराम | 0.8 | 0.8 | [5 empty] | 0.8
89 | Land levelling | श्री राम/दयाबती | 0.2 | 0.2 | [5 empty] | 0.2
90 | Land levelling | चमरसिंह/सगन बाई | 0.8 | 0.8 | [5 empty] | 0.8
91 | Land levelling | जयलाल नेताम/अघनबाई | 0.8 | 0.8 | [5 empty] | 0.8
92 | Land levelling | रामजी/मानकी वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
93 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
94 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
95 | Land levelling | लक्ष्मीनाथ नेताम/बैजनतीन | 0.4 | 0.4 | [5 empty] | 0.4
96 | Land levelling | संगीता/राम नेताम | 0.04 | 0.04 | [5 empty] | 0.04
97 | Land levelling | राजूराम/रामसिंग | 0.8 | 0.8 | [5 empty] | 0.8
98 | Land levelling | जयराम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
99 | Land levelling | सिरमो/छेदीलाल | 0.4 | 0.4 | [5 empty] | 0.4
100 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.5 | 0.5 | [5 empty] | 0.5
101 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.4 | 0.4 | [5 empty] | 0.4
102 | Land levelling | लक्ष्मीनाथ/बैजन्तीन | 0.4 | 0.4 | [5 empty] | 0.4
103 | Land levelling | संग्राम/रामसिंह | 0.04 | 0.04 | [5 empty] | 0.04
104 | Plantation | मन्नूराम भास्कर/झंगन सिंह | 0.4 | 0.4 | [5 empty] | 0.4
105 | Plantation | सुकबाई यादव/स्वयं | 0.2 | 0.2 | [5 empty] | 0.2
106 | Plantation | दुर्जन यादव/दिनदयाल | 0.5 | 0.5 | [5 empty] | 0.5
107 | Plantation | धनेश यादव/धर्मिन | 0.5 | 0.5 | [5 empty] | 0.5
108 | Plantation | गुहाराम यादव/अहिल्या | 0.5 | 0.5 | [5 empty] | 0.5
109 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  | as per Field data |  | 1
110 | Dug Well | नारद/जयलाल | 7X7 | 7 | 7 |  |  |  |  | 1
111 | Dug Well | आत्माराम | 7X7 | 7 | 7 |  |  |  |  | 1
112 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  |  |  | 1
113 | Dug Well | बंदीराम/दयाराम | 7X7 | 7 | 7 |  |  |  |  | 1
114 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
115 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
116 | Dug Well | नारायण | 7X7 | 7 | 7 |  |  |  |  | 1
117 | Dug Well | सुकमन | 7X7 | 7 | 7 |  |  |  |  | 1
118 | Dug Well | भागबती | 7X7 | 7 | 7 |  |  |  |  | 1
119 | Dug Well | दशोबाई | 7X7 | 7 | 7 |  |  |  |  | 1
120 | Dug Well | नरेश | 7X7 | 7 | 7 |  |  |  |  | 1
121 | Dug Well | शामकुंवर/रामबिशेष | 7X7 | 7 | 7 |  |  |  |  | 1
122 | Dug Well | गनेशिया बाई/आनंद राम सोनी | 7X7 | 7 | 7 |  |  |  |  | 1
123 | Dug Well | माखन यादव/तिभू | 7X7 | 7 | 7 |  |  |  |  | 1
124 | Dug Well | तीजऊ राम यादव/बिसऊराम | 7X7 | 7 | 7 |  |  |  |  | 1
125 | Dug Well | सुकलाईन/धनसिंग विश्वकर्मा | 7X7 | 7 | 7 |  |  |  |  | 1
126 | Dug Well | बरमन कुलदीप/कंगलाराम | 7X7 | 7 | 7 |  |  |  |  | 1
127 | Dug Well | रामबाई सोनवानी/तुलीया राम सोनवानी | 7X7 | 7 | 7 |  |  |  |  | 1
128 | Dug Well | भगवान सिंह मरकाम/ | 7X7 | 7 | 7 |  |  |  |  | 1
129 | Dug Well | केशव मरकाम/बिराजो मरकाम | 7X7 | 7 | 7 |  |  |  |  | 1
130 | Dug Well | शिवनारायण यादव/रजमन | 7X7 | 7 | 7 |  |  |  |  | 1
131 | Dug Well | लतखोरीन नेताम/छेरका | 7X7 | 7 | 7 |  |  |  |  | 1
132 | Dug Well | श्याम लाल यादव/लतखोर | 7X7 | 7 | 7 |  |  |  |  | 1
133 | Dug Well | मन्नूराम भास्कर/झंगन सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
134 | Dug Well | मोती राम सोनी/मोहन लाल | 7X7 | 7 | 7 |  |  |  |  | 1
135 | Dug Well | राजकुमार/सोनूराम | 7X7 | 7 | 7 |  |  |  |  | 1
136 | Dug Well | झाड़ूराम/लादूराम | 7X7 | 7 | 7 |  |  |  |  | 1
137 | Dug Well | नोहरसिंह/मसिया | 7X7 | 7 | 7 |  |  |  |  | 1
138 | Dug Well | अर्जुन/दीनदयाल | 7X7 | 7 | 7 |  |  |  |  | 1
139 | Dug Well | छन्नू राम | 7X7 | 7 | 7 |  |  |  |  | 1
140 | Dug Well | उदेराम | 7X7 | 7 | 7 |  |  |  |  | 1
141 | Dug Well | लक्ष्मण | 7X7 | 7 | 7 |  |  |  |  | 1
142 | Dug Well | पिलाराम/रामभरोष | 7X7 | 7 | 7 |  |  |  |  | 1
143 | Dug Well | श्री राम/दयाबती | 7X7 | 7 | 7 |  |  |  |  | 1
144 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
145 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
146 | Dug Well | माखन यादव/तीजू यादव | 7X7 | 7 | 7 |  |  |  |  | 1
147 | Dug Well | नवल सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
148 | Dug Well | नवल यादव/दल्ली यादव | 7X7 | 7 | 7 |  |  |  |  | 1
149 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
150 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
151 | Dug Well | गुहाराम यादव/अहिल्या | 7X7 | 7 | 7 |  |  |  |  | 1
152 | Dug Well | लालसाय मंडावी | 7X7 | 7 | 7 |  |  |  |  | 1
153 | Dug Well | तुलसी/सुकलाल | 7X7 | 7 | 7 |  |  |  |  | 1
154 | Dug Well | कांशीराम/सैदर | 7X7 | 7 | 7 |  |  |  |  | 1
155 | Dug Well | किसून/जोहन | 7X7 | 7 | 7 |  |  |  |  | 1
156 | Dug Well | कौश्लिया/दीपल | 7X7 | 7 | 7 |  |  |  |  | 1
157 | Dug Well | प्रवीण मरकाम/रामचंद | 7X7 | 7 | 7 |  |  |  |  | 1
158 | Farm bonding | संगीता/श्रीराम | 0.4 | 0.4 | [5 empty] | 0.4
159 | Farm bonding | श्यामलाल/मेहेरसिंह | 0.4 | 0.4 | [5 empty] | 0.4
160 | Farm bonding | प्रवीण मरकाम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
161 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
162 | Desilting | common Land | 45X45X4 | 45 | 45 | 4 | 6421.3511 | 3.2107 | 6.4214 | 9.632
163 | Desilting | common Land | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
164 | Desilting | common Land | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
165 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
166 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1 | Command area as per actual field data (Minimum command area
167 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1
168 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7500 | 13.5 |  | 2 |  | Time of refills X (Submergence area* d/3)
169 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 8750 | 15.75 |  | 2 |  | Time of refills X (Submergence area* d/3)
170 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7200 | 12.96 |  | 2 |  | Time of refills X (Submergence area* d/3)
171 | Checkdam | 3rd Order Nala | 25X 40X1.5 | 25 | 125 | 2 | 8700 | 15.66 |  | 2 |  | Time of refills X (Submergence area* d/3)
172 | Checkdam | 3rd Order Nala | 25X 40X1.6 | 25 | 125 | 2 | 9800 | 17.64 |  | 2 |  | Time of refills X (Submergence area* d/3)
[7 empty] | 237159.0111 | 173.1145 | 195.209 | 372.0235
23.7159

## Sheet1 (hidden)
Earthwork Calculation
| Step | Length m | Width m | Depth m | Volume m3
Hard soil depth
| Step 1 | 23 | 23 | 0.3 | 158.7 | 17.6
| Step 2 | 22.4 | 22.4 | 0.3 | 150.528 | 22.4
| Step 3 | 21.8 | 21.8 | 0.3 | 142.572 | 21.8
| Step 4 | 21.2 | 21.2 | 0.3 | 134.832 | 16.6
| Step 5 | 20.6 | 20.6 | 0.3 | 127.308 | 16
| Step 6 | 20 | 20 | 0.3 | 120 | 20
3 | Step 7 | 19.4 | 19.4 | 0.3 | 112.908 | 19.4
| Step 8 | 18.8 | 18.8 | 0.3 | 106.032 | 18.8
| Step 9 | 18.2 | 18.2 | 0.3 | 99.372 | 18.2
23 | Step 10 | 17.6 | 17.6 | 0.3 | 92.928 | 17.6
23 | Total Earthwork in Cum |  |  |  | 1245.18