## Sheet1
e DPR of Sonjhari, Magarlod,Dhamtari, Chhattisgarh
A | Back ground profile
| Micro Watershed code | 4G2G4B1j
| District | Dhamtari
| Block | Magarlod
| Gram Panchayat | Sonjhari
| Villages Covered | Sonjhari, Dhanora, Muroomdih
B | PHYSIOGRAPHIC PROFILE
| Total Area (Ha) | 515.93Hec.
| Rainfall (mm) | 1160.7
| Soil type | Sandy, loam, clay
| Average Slope | 5.25%
| Details of Tributaries | Jhabipathra nala | 3000 m long | Flows till 12 Month
C | DEMOGRAPHIC PROFILE
| Total Population | 1105
| Total HouseHolds | 256
| ST Population | 892
| SC Population | 10
D | MGNREGA Status
| NREGA Job card holders | 233
| Person days per year (average of last 3 years) | 101.83
| Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 109
| Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 50.99
| % of NRM Expenditure(Public + Individual) (average of last 3 years) | 92.27
E | LAND USE LAND COVER
| Mono cropped (Ha) | 311.4
| Multi cropped (Ha) | 1.6
| Current fallow(Ha) | 3.1
| Forest /Plantation (Ha) | 0
| Waste land (Ha) | 1
Impounded Waterbody (Ha)
Others (Ha)
F | LAND CLASSIFICATION
| Forest (Ha) | 148.6
| Upland (Ha) | 57.08
| Medium land (Ha) | 38.72
| Low Land (Ha) | 250.58
| River Stream Length (m) | N/A
G | Existing Water sources/ Structures
| Water harvesting Ponds | 10
| Borewells | 15
| Open wells | 8
H | Livelihood profile
| Agriculture | 85.5%
| Off Farm Activities | 7.5%
| Wages, labour | 4.5%
| Business | 1.5%
| Service/ job | 1%
I | WATER BUDGET
| Total Water Requirement (Ham) | 71.4
| Total Water Available (Ham) | 30.14
| Water Resource to be created (Ham) | 42.84
J | EXPECTED OUTCOME
Increase in Cropping area (in Ha)
Increase in Irrigated area (in Ha)
Income Enhancement (INR 50000 per annum as additional income)
K | ACTIVITY PROPOSED
Sr No. | Type of intervention | No. | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area | Targeted HH
1 | खेल मैदान तालाब गहरीकरण | 1 | 75*75*3 m | 8.96 | 8 | 4545.4545 | 22.47
2 | नया तालाब कच्ची नाली | 1 | 400 | 1.1 | 0.99 | 562.5
3 | मुड़ा खार नया तालाब निर्माण | 1 | 50*50*3 m | 8.431 | 8.0422 | 4569.4432 | 16.56
4 | ऊपर खार तालाब गहरीकरण | 1 | 60*55*3 m | 9.7 | 9.26 | 5261.3636 | 16.75
5 | झाबी पथरा नाला एल बी एस | 1 | 6*2 m | 0.89 | 0.68 | 386.3636 | 13.12
6 | झाबी पथरा नाला अर्थेन गाईड वाल | 1 | 400 | 0.29 | 0.22 | 125 | 1.25
7 | दीवान मुड़ा नया तालाब निर्माण | 1 | 75*55*3 m | 7.93 | 7.08 | 4022.7273 | 22.47
8 | चारभाठा स्टॉपडेम गहरीकरण | 1 | 75*75*3 m | 9.5272 | 9.1758 | 5213.5002 | 22.47
9 | चारभाठा स्टॉपडेम कच्ची नाली | 1 | 3000 m | 9.5272 | 9.1758 | 5213.5002
10 | जाम बहारा कच्ची नाली | 1 | 2 km | 6.66 | 6.66 | 3505.2632 | 3.12
11 | नया तालाब गहरीकरण | 1 | 60*60*3 m | 7.049 | 7.049 | 3709.9866 | 16.56
12 | नया तालाब कच्ची नाली | 1 | 550 m | 6.66 | 6.66 | 3505.2632
13 | बिन्देराम गहरीकरण | 1 | 60*55*3 m | 7.05 | 7.05 | 3710.5263 | 16.56
14 | नया स्टॉप डैम गहरीकरण | 1 | 75*75*3 m | 7.26 | 7.26 | 3821.0526 | 22.47
15 | नया स्टॉप डैम गेट | 1 | 8*1*2 m | 3.84 | 3.84 | 2021.0526 | 4.52
16 | चारभाठा कच्ची नाली | 1 | 1.5 km | 9.34 | 9.34 | 4915.7895 | 2.34
17 | बंजर डिपरा तालाब गहरीकरण | 1 | 75*75*3 m | 9.1758 | 9.1758 | 4829.3475 | 22.47
18 | शीतला तालाब गहरीकरण | 1 | 75*75*3 m | 9.1758 | 9.1758 | 4829.3475 | 22.47
19 | फारेस्ट भूमि वृक्षारोपण | 1 | 2 एकड़ | 5.45 | 5.45 | 2868.4211 | 9.45
20 | कोनाखार डैम गहरीकरण | 1 | 75*75*3 m | 6.2 | 6.2 | 3263.1579 | 22.47
21 | कोनाखार डैम गेट | 1 | 3*1*2 m | 7.8 | 7.8 | 4105.2632
22 | कोनाखार डैम कच्ची नाली | 1 | 900 m | 4.1 | 4.1 | 2157.8947
23 | झाबीपथरा डैम पक्की नाली | 1 | 500 m | 3.15 | 3.15 | 1657.8947
24 | दीवानमुड़ा डैम गहरीकरण | 1 | 75*75*3 m | 8.1 | 8.1 | 4263.1579 | 22.47
25 | तुरेकंदा स्टॉप डैम गहरीकरण | 1 | 75*75*3 m | 7.8 | 7.8 | 4105.2632 | 22.47
26 | आमा तालाब गहरीकरण | 1 | 75*75*3 m | 5.45 | 5.45 | 2868.4211 | 22.47
27 | सुन्दरी तालाब गहरीकरण | 1 | 75*75*3 m | 6.45 | 6.45 | 3394.7368 | 22.47
28 | गौठान | 1 | 4 Acre | 12 | 8.4 | 4421.0526
29 | घसिया राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
30 | गणेश भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
31 | फूलसिंग भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
32 | कान्ति भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
33 | सविता बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
34 | सुखिया बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
35 | उपासीन बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
36 | चित्र रेखा कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
37 | चैती बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
38 | निलेश डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
39 | बुधन्तीन डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
40 | धनेश डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
41 | झारियानी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
42 | प्रेमलता भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
43 | दरशन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
44 | लक्ष्मण भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
45 | कार्तिक भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
46 | घसिया राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
47 | धनेश कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
48 | कुमारी बाई/ रामाधीन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
49 | देवली बाई/ रामलाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
50 | कोटा बाई/ सरजू भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
51 | भुनेश्वरी / कीर्तन कुमार भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
52 | नरेश्वरी/ चंदू लाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
53 | नरेश्वरी/ चंदू लाल डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
54 | पूर्णिमा बाई/ छबिलाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
55 | रामशिला बाई/श्याम चरण भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
56 | ज्योतिन बाई/सियाराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
57 | बुधन बाई / गणेश राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
58 | उर्मिला बाई/श्याम लाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
59 | सुखबाई/मनोज कुमार भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
60 | कांतिबाई/दिलीप कुमार भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
61 | लता बाई/ चंद्रप्रकाश भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
62 | शारी बाई/ प्रह्लाद भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
63 | बिन्दा बाई/राखन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
64 | हसवन्तीन/शिवनाथ भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
65 | सुमित्रा/भुखऊ राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
66 | बसंती बाई/ जगदीश कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
67 | हेमलता/ राजकुमार भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
68 | राधिका बाई/ अगहन सिंह भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
69 | सावित्री बाई/ घनराज भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
70 | कौशिल्या बाई/ थानूराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
71 | झमनि बाई/ प्रेमसिंग भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
72 | फलेन्द्री बाई/ जगेश्वर भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
73 | रतन बाई/ आत्मा राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
74 | रतन बाई/ आत्मा राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
75 | राजुला बाई/ प्रभु लाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
76 | सोनाबती/धनीराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
77 | जमनी बाई/ कुंवर सिंग भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
78 | सुमरिन बाई/ गोपाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
79 | कलेश्वरी/ पंचो बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
80 | सतो बाई/ पति राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
81 | रमला बाई/ नेहरू भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
82 | रमला बाई/ नेहरू कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
83 | खोदी बाई/ संतराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
84 | खोदी बाई/ संतराम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
85 | तुलेश्वरी/ कृष्ण चंद भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
86 | खेमीन बाई/ हिरऊ राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
87 | संतोषी बाई/ भुनेश्वर ठाकुर भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
88 | ममता बाई/ गंगाराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
89 | सुलोचना बाई/ विदेशी राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
90 | सुलोचना बाई/ विदेशी राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
91 | रमौतीन/ नारायण भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
92 | रमौतीन/ नारायण कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
93 | अहिल्या बाई/ घस्याराग राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
94 | अहिल्या बाई/ घस्याराग राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
95 | देवन्तीन बाई/ राजाराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
96 | सतरूपा बाई/ आशाराम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
97 | सतरूपा बाई/ आशाराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
98 | सरस्वती/ फिरतु राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
99 | राधिका बाई/ सुरेश कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
100 | राधिका बाई/ सुरेश भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
101 | संगीता बाई/ बिसाखू राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
102 | संगीता बाई/ बिसाखू राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
103 | जयश्री बाई/ छुरक राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
104 | मुरारी बाई/ धुरवा कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
105 | रजंतिन बाई/ स्व झड़ीराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
106 | चैतीबाई/ स्व गणेश राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
107 | चैतीबाई/ स्व गणेश राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
108 | चैतीबाई/ स्व गणेश राम डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
109 | प्रेमिन बाई /टकेश्वर कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
110 | कौशिल्या बाई/ स्व सुखऊ राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
111 | कौशिल्या बाई/ स्व सुखऊ राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
112 | सरिता बाई/ जगदेव सिंग भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
113 | अहिल बति/ सन्तु राम कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
114 | अहिल बति/ सन्तु राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
115 | अहिल बति/ सन्तु राम डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
116 | राजवन्तीन बाई/ गोविन्द राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
117 | प्रमिला बाई/गजेंद्र कुमार भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
118 | रामबती/ जीवन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
119 | अनीता बाई/ सुदामा राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
120 | हिरा बाई/ जगत भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
121 | झागथरीन/ समारू राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
122 | रामेश्वरी/ धनेश भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
123 | अनीता बाई/ गोकुल यादव कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
124 | मोहन/ श्रीराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
125 | देवकी बाई/ पुनीतराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
126 | केशर बाई/ जोहन राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
127 | संतोषी बाई/ मोहन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
128 | ठाकुर राम /अमर सिंग भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
129 | सतरूपा बाई/ सोहन लाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
130 | उर्मिला/ रामभुवन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
131 | सलेंदरी बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
132 | चित्ररेखा भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
133 | बलेसिया बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
134 | अमृत बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
135 | अमृत बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
136 | प्रमिला भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
137 | सुनोति बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
138 | प्रतीमा भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
139 | उपासिन कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
140 | उपासिन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
141 | आरती भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
142 | दिनेश्वरी कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
143 | दिनेश्वरी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
144 | किसुन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
145 | रमला बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
146 | शांति बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
147 | शांति बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
148 | जतिन बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
149 | शिव कुमारी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
150 | लक्ष्मी बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
151 | अमरौतींन कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
152 | शिव कुमारी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
153 | शिव कुमारी कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
154 | फुलेशवरी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
155 | अमृत लाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
156 | रामबती भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
157 | रामबती कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
158 | फुलेश्वरी पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
159 | फुलेश्वरी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
160 | फुलेश्वरी कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
161 | गणेशी पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
162 | गणेशी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
163 | देतीग्य बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
164 | तुलेश्वर भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
165 | भगवती भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
166 | भगवती पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
167 | केशरी कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
168 | केशरी पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
169 | जयंती भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
170 | उर्मिला भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
171 | उर्मिला कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
172 | सविता कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
173 | स्याम बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
174 | सन्तु राम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
175 | सन्तु राम पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
176 | तिकेश्वरी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
177 | तिकेश्वरी कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
178 | तिकेश्वरी पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
179 | तीज बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
180 | तीज बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
181 | कुंती बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
182 | कुंती बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
183 | चैती बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
184 | चैती बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
185 | रम्भा बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
186 | रम्भा बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
187 | उमा बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
188 | उमा बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
189 | देवंतीं बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
190 | मंगली बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
191 | मंगली बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
192 | संगीता बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
193 | संगीता बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
194 | चंपा बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
195 | चंपा बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
196 | लीला बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
197 | जानकी बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
198 | रामकुमारी पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
199 | रामकुमारी भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
200 | हरमन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
201 | हरमन कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
202 | शुखिया पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
203 | शुखिया भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
204 | देवकी कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
205 | देवकी पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
206 | कुंती बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
207 | कुंती बाई मुर्गी शेड निर्माण कार्य | 1 | 4.75*1.75 m | 0.54 | 0.46 | 242.1053
208 | कुंती बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
209 | गेंदी बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
210 | गेंदी बाई डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
211 | गेंदी बाई मुर्गी शेड निर्माण कार्य | 1 | 4.75*1.75 m | 0.54 | 0.46 | 242.1053
212 | कांती पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
213 | सातो बाई पशुशेड निर्माण कार्य | 1 | 8*3.75 m | 0.54 | 0.46 | 242.1053
214 | सातो बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
215 | सातो बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
216 | अनीता भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
217 | अनीता कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
218 | अनीता मुर्गी शेड निर्माण कार्य | 1 | 4.75*1.75 m | 0.54 | 0.46 | 242.1053
219 | रामगुलाल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
220 | बिमला भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
221 | बुध्वन्तीन बाई भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
222 | बुध्वन्तीन बाई कुंआ निर्माण कार्य | 1 | व्यास-5m, गहराई -30 फिट | 2.54 | 0.7 | 368.4211 | 1.25
223 | बुध्वन्तीन बाई मुर्गी शेड निर्माण कार्य | 1 | 4.75*1.75 m | 0.54 | 0.46 | 242.1053
224 | जीवराखन भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
225 | निर्भय भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
226 | गेंदलाल भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
227 | गेंदलाल डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
228 | सहदेव भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
229 | सहदेव वृक्षारोपण कार्य | 1 | 7 नग | 2.89 | 2.61 | 1373.6842
230 | हेमंत भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
231 | हेमंत वृक्षारोपण कार्य | 1 | 8 नग | 2.89 | 2.61 | 1373.6842
232 | विमल भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
233 | विमल वृक्षारोपण कार्य | 1 | 11 नग | 2.89 | 2.61 | 1373.6842
234 | पहरसिंग भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
235 | पहरसिंग डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
236 | पहरसिंग वृक्षारोपण कार्य | 1 | 4 नग | 2.89 | 2.61 | 1373.6842
237 | रेखराज भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
238 | रेखराज वृक्षारोपण कार्य | 1 | 9 नग | 2.89 | 2.61 | 1373.6842
239 | सोनुराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
240 | सोनुराम डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
241 | लीलाराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
242 | बिसराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
243 | बिसराम वृक्षारोपण कार्य | 1 | 12 नग | 2.89 | 2.61 | 1373.6842
244 | तुलसीराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
245 | गुमानसिंह भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
246 | गुमानसिंह वृक्षारोपण कार्य | 1 | 20 नग | 2.89 | 2.61 | 1373.6842
247 | दयालुराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
248 | दयालुराम डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
249 | सुभाष भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
250 | सुभाष डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
251 | आशाराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
252 | बहुरसिंग भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
253 | माखन भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
254 | रूप सिंग भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
255 | रूप सिंग डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
256 | अनुज भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
257 | अनुज वृक्षारोपण कार्य | 1 | 8 नग | 2.89 | 2.61 | 1373.6842
258 | हरीश चन्द्र भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
259 | हीरऊराम भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
260 | हेमूला भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
261 | नरायण भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
262 | मंगलू भूमि सुधार कार्य भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
263 | मंगलू वृक्षारोपण कार्य | 1 | 15 नग | 2.89 | 2.61 | 1373.6842
264 | कोमल भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
265 | कोमल डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
266 | संतराम भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
267 | श्रवण भूमि सुधार कार्य | 1 | 1 एकड़ | 0.36 | 0.35 | 184.2105 | 0.4
268 | श्रवण डबरी निर्माण कार्य | 1 | 20*20*3 m | 1.28 | 1.1615 | 611.3211 | 1.5
| Total | 268 |  |  |  |  | 485.75