## Seldeep
e DPR of Seldeep GP, Kurud,Dhamtari, Chhattisgarh
A | Back ground profile
Micro Watershed code
| District | Dhamtari
| Block | Kurud
| Gram Panchayat | Seldeep
| Villages Covered | Seldeep
B | PHYSIOGRAPHIC PROFILE
| Total Area (Ha) | 364.56 Hectares
| Rainfall (mm) | 1190
| Soil type | Sandy, loam, clay
| Average Slope | 0-5 %
| Details of Tributaries | Mahanadi | 3000 m long | Flows till December
C | DEMOGRAPHIC PROFILE
| Total Population | 1564
| Total HouseHolds | 295
| ST Population | 218
| SC Population | 0
D | MGNREGA Status
| NREGA Job card holders | 263
| Person days per year (average of last 3 years) | 33.91
| Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 9
| Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 38.42
| % of NRM Expenditure(Public + Individual) (average of last 3 years) | 84.94
E | LAND USE LAND COVER
| Mono cropped (Ha) | 34.85
| Multi cropped (Ha) | 164.29
| Current fallow(Ha) | 0.3
| Forest /Plantation (Ha) | 0
| Waste land (Ha) | 3.34
Impounded Waterbody (Ha)
Others (Ha)
F | LAND CLASSIFICATION
| Forest (Ha) | 0
| Upland (Ha) | 61.97
| Medium land (Ha) | 54.68
| Low Land (Ha) | 247.9
| River Stream Length (m) | N/A
G | Existing Water sources/ Structures
| Water harvesting Ponds | 5
| Borewells | 45
| Open wells | N/A
H | Livelihood profile
| Agriculture | 66%
| Off Farm Activities | 18%
| Wages, labour | 10%
| Business | 3%
| Service/ job | 3%
I | WATER BUDGET
Total Water Requirement (Ham)
Total Water Available (Ham)
Water Resource to be created (Ham)
J | EXPECTED OUTCOME
Increase in Cropping area (in Ha)
Increase in Irrigated area (in Ha)
Income Enhancement (INR 50000 per annum as additional income)
K | ACTIVITY PROPOSED
Sr No. | Type of intervention | No. | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area in Hac | Targeted HH
1 | KACHI NALI NIRAMAN KARYA (JANAK SAHU KHET SE PAWAN BADI TARAF) | 1 | 350 m | 85000 | 67000 | 352.6316
2 | KACHI NALI NIRMAN KARYA (SANTOSH KE KHET SE ANIKAT TAK 400M) | 1 | 400 m | 94000 | 80000 | 421.0526
3 | Gautiya Talab Gaharikaran Sah Piching Kary | 1 | 3.5 Acre | 950000 | 785000 | 4131.5789 | 19.56
4 | FALDAR MISRIT VRIKSHAROPAN KARYA 3.00H (ROD KE PAS) | 1 | 3 hec | 556000 | 358000 | 1884.2105
5 | SAMUDAYIK PASHU ASHRAYE STHAL NIRMAN KARYA | 1 | 2 Acre | 323000 | 72000 | 378.9474
6 | SAMUDAIYK DABARI NIRMAN (VRIKCHHAROPAN KE PASS) | 1 | 25X25X3 | 248000 | 220000 | 1157.8947 | 1.5
7 | SAMUDAIYK DABARI NIRMAN ( KATH SINBADI KE PASS) | 1 | 25X25X3 | 341000 | 310000 | 1631.5789 | 1.5
8 | SAMUDAIYK DABARI NIRMAN (ANGANBADI KE PICHHE) | 1 | 25X25X3 | 388000 | 355000 | 1868.4211 | 19.56
9 | Naya Talab Gaharikaran,Piching Sah Nirmalaghat Nirman Kary | 1 | 3.5 Acre | 950000 | 785000 | 4131.5789 | 19.56
10 | FALDHAR MISTRIT VRICHAROPAN 2.38H | 1 | 2.38 hec | 556000 | 358000 | 1884.2105
11 | BHUMI SAMTALIKARAN KARYA ( VRICHAROPAN STHAL ) 2.38 | 1 | 2.38 hec | 556000 | 358000 | 1884.2105 | 0.2
12 | SAMUDAYIK DABARI NIRMAN KARYA | 1 | 25X25X3 | 388000 | 355000 | 1868.4211 | 1.5
13 | DABARI TALAB GAHARIKRAN KARYA | 1 | 3 Acre | 950000 | 785000 | 4131.5789 | 19.56
14 | sadak kinare vrikcharopan karya 3 year seldip khel maidan se santara badi tak (0.50 Km) | 1 | 500 m | 248000 | 220000 | 1157.8947
15 | AamaTalab Gaharikaran,Piching Sah Nirmalaghat Nirman Kary | 1 | 3 Acre | 950000 | 785000 | 4131.5789 | 19.56
16 | Kachchi Nali Nirman Kary Ramkrishana Sahu Ke Badi Se Anikat Tak. | 1 | 2000m | 8.6353 | 7.3911 | 0.0389 | 2.52
17 | Charagah Nirman Kary | 1 | 5 Acre | 9.44 | 6.81 | 0.035842
18 | Mainar Nali Gaharikaran Sah Safai Kary Ramchand Sahu Khet Se Mandroud Khar Tak | 1 | 3000m | 8.6353 | 7.3911 | 0.0389 | 2.55
19 | Mandali Talab Gaharikaran,Piching Sah Nirmalaghat Nirman Kary | 1 | 3 Acre | 950000 | 785000 | 4131.5789 | 19.56
20 | Seeta Bai/Rohit Kanwar Dabari Nirman Kary | 1 | 20X20X3 | 140000 | 102000 | 536.8421 | 1.5
21 | Ganga Bai/Nathu Das Dabari Nirman Kary | 1 | 20X20X3 | 140000 | 102000 | 536.8421 | 1.5
22 | Dharmin/Ganga Ram Yadav Bakarished Nirman Kary | 1 | 6X4 | 73000 | 7000 | 36.8421
23 | Punni Bai/Rainsingh Kuaa Nirman Kary | 1 | Dia-5m, Depth-10m | 225000 | 69000 | 363.1579 | 1.62
24 | Vishvasha Bai/Dhansingh Kuaa Nirman Kary | 1 | Dia-5m, Depth-10m | 225000 | 69000 | 363.1579 | 1.62
25 | Chitrekha/Kaliram Bakrished Nirman Kary | 1 | 6X4 | 73000 | 7000 | 36.8421
26 | Ramshila/Anantsingh Kuaa Mirman Kary | 1 | Dia-5m, Depth-10m | 225000 | 69000 | 363.1579 | 1.62
27 | Daya Bai/Jainsingh Kuaa Nirman Kary | 1 | Dia-5m, Depth-10m | 225000 | 69000 | 363.1579 | 1.62
28 | Fagani/Manuram Sahu Kuaa Nirman Kary | 1 | Dia-5m, Depth-10m | 225000 | 69000 | 363.1579 | 1.62
29 | Puspalata/Maniram Sahu Nadep Nirman Kary | 1 | 3*2 m | 12000 | 2000 | 10.5263
| Grand Total | 29 |  |  |  |  | 138.23