## Sheet1
e DPR of Ghanikhuta GP, Kabirdham, Chhattisgarh
A | Back ground profile
| Micro Watershed code | 5D6A8C1b,4G3C6A2e,4G3C6A2d,5D6A8B1g,4G3C6A2c,
| District | KABIRDHAM
| Block | Bodla
| Gram Panchayat | Ghanikhuta
| Villages Covered | Ghanikhuta,Parsahi,Raniguda,Kanhari.
B | PHYSIOGRAPHIC PROFILE
| Total Area (Ha) | 813.353
| Rainfall (mm) | 725mm
| Soil type | Sandy loam, clay,Murum clay
| Average Slope | 0-16%
| Details of Tributaries | 2
C | DEMOGRAPHIC PROFILE
| Total Population | 1054
| Total HouseHolds | 249
| ST Population | 703
| SC Population | 0
D | MGNREGA Status
| NREGA Job card holders | 327
| Person days per year (average of last 3 years) | 23823
| Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 117.33
| Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 52.88
| % of NRM Expenditure(Public + Individual) (average of last 3 years) | 67.92
E | LAND USE LAND COVER
| Mono cropped (Ha) | 442.134
| Multi cropped (Ha) | 128.168
| Current fallow(Ha) | 21.357
| Forest /Plantation (Ha) | 213.494
| Waste land (Ha) | 0
| Impounded Waterbody (Ha) | 8.2
Others (Ha)
F | LAND CLASSIFICATION
| Forest (Ha) | 213.494
| Upland (Ha) | 21.357
| Medium land (Ha) | 442.134
| Low Land (Ha) | 136.368
| River Stream Length (m) | 5748
G | Existing Water sources/ Structures
| Water harvesting Ponds | 6 nos
| Borewells | 18 nos
| Open wells | 8 nos
| Farm Ponds | 8 nos
H | Livelihood profile
| Agriculture | 69.07%
| Off Farm Activities | 13.65%
| Wages, labour | 14.45%
| Business | 1%
| Service/ job | 2%
I | WATER BUDGET
| Total Water Requirement (Ham) | 93.37
| Total Water Available (Ham) | 48.07
| Water Resource to be created (Ham) | 45.3
J | EXPECTED OUTCOME
| Increase in Cropping area (in Ha) | 277.812
| Increase in Irrigated area (in Ha) | 84.45
| Income Enhancement (INR 50000 per annum as additional income) | 226 HH
K | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the beneficiary | No. | Length | Width | Height/Depth | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
1 | 30-40 माँडल | भागदु/हगरू | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.7483 | 80.9535 | 1
2 | रिर्टनिंग वाल निर्माण कार्य | सामूहिक कार्य | 1 | 200 | 3 | 1.5 | 1218000 | 211000 | 5217 | 8.95 | 21.8657 | 80.9428 | 0
3 | कुआँ निर्माण | सालिक राम/तेज राम | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8636 | 80.9435 | 1
4 | कुआँ निर्माण | अंगद /तेजराम | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8626 | 80.8094 | 1
5 | चेकडेम निर्माण | सामूहिक कार्य | 1 | 12 | 2 | 1.5 | 14.3 | 2.24 | 1160 | 10.5 | 21.8665 | 80.9432 | 5
6 | पशुशेड निर्माण | रतनीबाई/हौसिलाल | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8607 | 80.942 | 1
7 | भूमि सुधार एवं मेड बंधान कार्य | झामकुंवर/परशराम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.892 | 80.9592 | 1
8 | तालाब निर्माण | सामूहिक कार्य | 1 | 200 | 150 | 3 | 1800000 | 1780000 | 9222 | 38.11 | 21.3948 | 80.9614 | 7
9 | वर्मी कम्पोस्ट निर्माण | सामूहिक कार्य | 10 | 3.4 | 2 | 0.9 | 237200 | 41300 | 1015 | 0 | 21.8949 | 80.9617 | 5
10 | भूमि सुधार एवं मेड बंधान कार्य | बजरहीन/करंग | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8424 | 80.8976 | 1
11 | तालाब निर्माण | सामूहिक कार्य | 1 | 200 | 150 | 3 | 1800000 | 1780000 | 9222 | 38.11 | 21.898 | 80.943 | 8
12 | भूमि सुधार एवं मेड बंधान कार्य | मन्नु/छिद्दी | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8936 | 80.9578 | 1
13 | कुआँ निर्माण | रूपसिंह /पुनऊ | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8448 | 80.9616 | 1
14 | भूमि सुधार एवं मेड बंधान कार्य | सुकलाल /चरनु | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8949 | 80.9618 | 1
15 | भूमि सुधार एवं मेड बंधान कार्य | बुधराम /परसादी | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8949 | 80.9617 | 1
16 | भूमि सुधार एवं मेड बंधान कार्य | दिनेश/होसीलाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.892 | 80.9592 | 1
17 | डबरी निर्माण | दिनेश/होसीलाल | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8934 | 80.9571 | 1
18 | डबरी निर्माण | गोवर्धन/दिलीप | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8579 | 80.9404 | 1
19 | भूमि सुधार एवं मेड बंधान कार्य | परशराम/हीरालाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8576 | 80.9404 | 1
20 | भूमि सुधार एवं मेड बंधान कार्य | ललिता/गहरा | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8576 | 80.9406 | 1
21 | भूमि सुधार एवं मेड बंधान कार्य | मानसिंह/हीरासिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8581 | 80.9429 | 1
22 | भूमि सुधार एवं मेड बंधान कार्य | चन्द्रपाल/गेंदलाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8584 | 80.9443 | 1
23 | भूमि सुधार एवं मेड बंधान कार्य | इतवारी/गेंदसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8598 | 80.9956 | 1
24 | भूमि सुधार एवं मेड बंधान कार्य | बारेलाल/जयसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8621 | 80.9517 | 1
25 | भूमि सुधार एवं मेड बंधान कार्य | गेंदलाल/जयसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8646 | 80.9548 | 1
26 | पशुशेड निर्माण | घुडान/बरनु | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8604 | 80.9417 | 1
27 | पशुशेड निर्माण | पिराम/धन सिंह | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8579 | 80.9404 | 1
28 | पशुशेड निर्माण | सुखमत /झुरू | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8576 | 80.9404 | 1
29 | पशुशेड निर्माण | बुद्दू सिंह/धरम | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8576 | 80.9406 | 1
30 | पशुशेड निर्माण | इतवारी/गेंदसिंह | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8581 | 80.9429 | 1
31 | पशुशेड निर्माण | मुन्ना/बिपत राम | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8584 | 80.9443 | 1
32 | वर्मी कम्पोस्ट निर्माण | सामूहिक कार्य | 5 | 3.4 | 2 | 0.9 | 237200 | 41300 | 1015 | 0 | 21.8598 | 80.9956 | 5
33 | तालाब निर्माण | सामूहिक कार्य | 1 | 200 | 150 | 3 | 1800000 | 1780000 | 9222 | 38.11 | 21.8621 | 80.9517 | 6
34 | कुआँ निर्माण | शेरसिंह/हगरू | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8674 | 80.9506 | 1
35 | भूमि सुधार एवं मेड बंधान कार्य | बिदेश/जंगल | 1 | 40 | 40 | 0.3 | 27000 | 26500 | 139 | 1 | 21.7651 | 80.9455 | 1
36 | कुआँ निर्माण | नगल/गौतम | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8653 | 80.9434 | 1
37 | भूमि सुधार एवं मेड बंधान कार्य | हरीलाल/केशर | 1 | 40 | 40 | 0.3 | 27000 | 26500 | 139 | 1 | 21.8657 | 80.9428 | 1
38 | भूमि सुधार एवं मेड बंधान कार्य | किन्तु/नह्बा | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8636 | 80.9435 | 1
39 | भूमि सुधार एवं मेड बंधान कार्य | बिसर/जगतु | 1 | 40 | 40 | 0.3 | 27000 | 26500 | 139 | 1 | 21.8608 | 80.3432 | 1
40 | भूमि सुधार एवं मेड बंधान कार्य | बृजलाल/समलू | 1 | 20 | 18 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8607 | 80.942 | 1
41 | कुआँ निर्माण | मुज्बल/सुलउ | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8666 | 80.9417 | 1
42 | नाडेप टैंक निर्माण | गणेश/मुज्बल | 1 | 3.5 | 1.7 | 0.9 | 110000 | 29000 | 150 | 0 | 21.8608 | 80.9407 | 1
43 | भूमि सुधार एवं मेड बंधान कार्य | ईतवारी/जयराम | 1 | 40 | 40 | 0.3 | 27000 | 26500 | 139 | 1 | 21.8576 | 80.9404 | 1
44 | कुआँ निर्माण | बिसर/जगतु | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8376 | 80.4053 | 1
45 | भूमि सुधार एवं मेड बंधान कार्य | दशन/फुगेलाल | 1 | 40 | 40 | 0.3 | 27000 | 26500 | 139 | 1 | 21.8584 | 80.9443 | 1
46 | कुआँ निर्माण | दशन/फुगेलाल | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8544 | 80.9448 | 1
47 | कुआँ निर्माण | कमल/सुमेर | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.7483 | 80.9535 | 1
48 | 30-40 माँडल | गहरी/जोहरू | 1 | 30 | 40 | 2 | 27000 | 26500 | 139 | 1.5 | 21.8696 | 80.9512 | 1
49 | 30-40 माँडल | झुरू/बरनु | 1 | 30 | 40 | 2 | 27000 | 26500 | 139 | 1.5 | 21.8699 | 80.9506 | 1
50 | 30-40 माँडल | भागवत/रतन | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.7657 | 80.9455 | 1
51 | डबरी निर्माण | सुधारी/परसादी | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8657 | 80.9428 | 1
52 | 30-40 माँडल | गेंदू/मतलू | 1 | 30 | 40 | 2 | 35000 | 34500 | 181 | 1.5 | 21.8636 | 80.9435 | 1
53 | 30-40 माँडल | जोहन/हगरू | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8626 | 80.8094 | 1
54 | 30-40 माँडल | चेंनराय/सुकलाल | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8665 | 80.9432 | 1
55 | 30-40 माँडल | बाबूलाल/द्चालू | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8607 | 80.942 | 1
56 | 30-40 माँडल | आग्रहित/ | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8604 | 80.9417 | 1
57 | 30-40 माँडल | शिवकुमार/घुडन | 1 | 30 | 40 | 2 | 35000 | 34500 | 181 | 1.5 | 21.8579 | 80.9404 | 1
58 | 30-40 माँडल | सुखमत/झुरू | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8576 | 80.9404 | 1
59 | 30-40 माँडल | घुरउ/बरनी | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8576 | 80.9406 | 1
60 | 30-40 माँडल | जहरू/जोगन | 1 | 30 | 40 | 2 | 35000 | 34500 | 181 | 1.5 | 21.8581 | 80.9429 | 1
61 | 30-40 माँडल | कुमारी/मटुकसिंह | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8584 | 80.9443 | 1
62 | 30-40 माँडल | अंजोरी/रामलाल | 1 | 30 | 40 | 2 | 35000 | 34500 | 181 | 1.5 | 21.8598 | 80.9956 | 1
63 | कुआँ निर्माण | जोहन/हगरू | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8621 | 80.9517 | 1
64 | 30-40 माँडल | भागबत/रतन | 1 | 30 | 40 | 2 | 50000 | 49500 | 260 | 1.5 | 21.8646 | 80.9548 | 1
65 | 30-40 माँडल | जंगू/भरोसी | 1 | 30 | 40 | 2 | 35000 | 34500 | 181 | 1.5 | 21.8558 | 80.9496 | 1
66 | डबरी निर्माण | दुकलू/जोहर | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8585 | 80.9587 | 1
67 | भूमि सुधार एवं मेड बंधान कार्य | मेहतरू/लारकन | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.9033 | 80.9676 | 1
68 | भूमि सुधार एवं मेड बंधान कार्य | भादू/लार्मन | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.9054 | 80.8679 | 1
69 | भूमि सुधार एवं मेड बंधान कार्य | बुद्धू/परसादी | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.9859 | 80.9662 | 1
70 | भूमि सुधार एवं मेड बंधान कार्य | सुकलू/बुद्धू | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.905 | 80.9678 | 1
71 | भूमि सुधार एवं मेड बंधान कार्य | ईश्वर/घुटोलाल | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.9088 | 80.7677 | 1
72 | भूमि सुधार एवं मेड बंधान कार्य | अनीता/इतवार | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.7096 | 80.9687 | 1
73 | भूमि सुधार एवं मेड बंधान कार्य | मंगल/सुंदिर | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8999 | 80.9668 | 1
74 | भूमि सुधार एवं मेड बंधान कार्य | रामखिलावन/मेह्त्त्र | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8989 | 80.9888 | 1
75 | भूमि सुधार एवं मेड बंधान कार्य | श्याम/छेरकू | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.898 | 80.9818 | 1
76 | भूमि सुधार एवं मेड बंधान कार्य | लालतीन/मंगल | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8949 | 80.9603 | 1
77 | भूमि सुधार एवं मेड बंधान कार्य | भागीलाल/बोपत | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.898 | 80.943 | 1
78 | भूमि सुधार एवं मेड बंधान कार्य | महेतर/धरम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.893 | 80.9583 | 1
79 | डबरी निर्माण | उषा बाई /बुधसिंह | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8927 | 80.9548 | 1
80 | डबरी निर्माण | हेमंत/केशर | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.892 | 80.9592 | 1
81 | डबरी निर्माण | कोशिला/भुजबल | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8934 | 80.9571 | 1
82 | डबरी निर्माण | गहरा/धरम | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.3948 | 80.9614 | 1
83 | भूमि सुधार एवं मेड बंधान कार्य | छिददी/घनश्याम | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8943 | 80.9694 | 1
84 | नाडेप टैंक निर्माण | मुन्नू /छिददी | 1 | 3.5 | 1.7 | 0.9 | 110000 | 29000 | 150 | 0 | 21.8927 | 80.9548 | 1
85 | भूमि सुधार एवं मेड बंधान कार्य | नोहर/छिददी | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.892 | 80.9592 | 1
86 | भूमि सुधार एवं मेड बंधान कार्य | समारू/जमेमर | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8934 | 80.9571 | 1
87 | भूमि सुधार एवं मेड बंधान कार्य | चैतु/दिलीत | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8424 | 80.8976 | 1
88 | भूमि सुधार एवं मेड बंधान कार्य | लालतीन/मंगल | 1 | 30 | 30 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8949 | 80.96 | 1
89 | भूमि सुधार एवं मेड बंधान कार्य | भागीलाल/बिपत | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.898 | 80.943 | 1
90 | भूमि सुधार एवं मेड बंधान कार्य | सोनेराम/शुसील | 1 | 45 | 45 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8448 | 80.9616 | 1
91 | भूमि सुधार एवं मेड बंधान कार्य | महेतर/धरम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8949 | 80.9618 | 1
92 | भूमि सुधार एवं मेड बंधान कार्य | छिददी/घनश्याम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.893 | 80.893 | 1
93 | भूमि सुधार एवं मेड बंधान कार्य | नोहर/छिददी | 1 | 70 | 70 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8927 | 80.9548 | 1
94 | नाडेप टैंक निर्माण | समारू/जमेमर | 1 | 3.5 | 1.7 | 0.9 | 110000 | 29000 | 150 | 0 | 21.892 | 80.9592 | 1
95 | भूमि सुधार एवं मेड बंधान कार्य | कोसिल्या/गेंदलाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8948 | 80.9614 | 1
96 | भूमि सुधार एवं मेड बंधान कार्य | चैतु/दिलीत | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.9636 | 80.9726 | 1
97 | भूमि सुधार एवं मेड बंधान कार्य | हिरुह/मंगलसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8914 | 80.9624 | 1
98 | भूमि सुधार एवं मेड बंधान कार्य | गनेसिया/हिरूह | 1 | 70 | 70 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8326 | 80.9633 | 1
99 | भूमि सुधार एवं मेड बंधान कार्य | भागीलाल/मेह्न्तर | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8852 | 80.9655 | 1
100 | भूमि सुधार एवं मेड बंधान कार्य | दुर्बसी/मांगीलाल | 1 | 70 | 70 | 0.3 | 20000 | 19500 | 102 | 1 | 21.8349 | 80.9633 | 1
101 | बकरी शेड निर्माण | रूपसिंह/पुनऊ | 1 | 3 | 1.8 | 2 | 37000 | 6000 | 31 | 0 | 21.7483 | 80.9535 | 1
102 | बकरी शेड निर्माण | जयंती/गुदन | 1 | 3 | 1.8 | 2 | 37000 | 6000 | 31 | 0 | 21.862 | 80.9512 | 1
103 | मुर्गी शेड निर्माण | मंगलसिंह /कुंवरसिंह | 1 | 3.5 | 2 | 1.8 | 37000 | 6000 | 31 | 0 | 21.8674 | 80.9506 | 1
104 | नाडेप टैंक निर्माण | सामूहिक कार्य | 5 | 3.5 | 1.7 | 0.9 | 110000 | 29000 | 150 | 0 | 21.8696 | 80.9512 | 5
105 | भूमि सुधार एवं मेड बंधान कार्य | जगदिश/बुध सिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8674 | 80.9506 | 1
106 | भूमि सुधार एवं मेड बंधान कार्य | गांसू राम/बैराग | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.7651 | 80.9455 | 1
107 | भूमि सुधार एवं मेड बंधान कार्य | देवसिंह/अंजोर | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8653 | 80.9434 | 1
108 | भूमि सुधार एवं मेड बंधान कार्य | केशोबाई/सोनूसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8657 | 80.9428 | 1
111 | तालाब गहरीकरण | सामूहिक कार्य | 1 | 120 | 100 | 0.8 | 1800000 | 1780000 | 9222 | 38.11 | 21.8626 | 80.8034 | 6
112 | तालाब गहरीकरण | सामूहिक कार्य | 1 | 120 | 100 | 0.8 | 1800000 | 1780000 | 9222 | 38.11 | 21.8579 | 80.9404 | 7
113 | तालाब निर्माण | सामूहिक कार्य | 1 | 200 | 150 | 3 | 1070400 | 1065000 | 5518 | 38.11 | 21.3743 | 80.8983 | 8
114 | तालाब निर्माण | सामूहिक कार्य | 1 | 200 | 150 | 3 | 1800000 | 1780000 | 9222 | 38.11 | 21.8576 | 80.9404 | 8
115 | भूमि सुधार एवं मेड बंधान कार्य | शिवकुमारी/अशोक | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8576 | 80.9406 | 1
116 | भूमि सुधार एवं मेड बंधान कार्य | भगवातबाई/रतन सिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8581 | 80.9429 | 1
117 | मुर्गी शेड निर्माण | मानसिंह/हीरासिंह | 1 | 3.5 | 2 | 1.8 | 37000 | 6000 | 31 | 0 | 21.8584 | 80.9443 | 1
118 | पशुशेड निर्माण | बारेलाल/जयसिंह | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8598 | 80.9956 | 1
119 | पशुशेड निर्माण | सक्तु/चंदूलाल | 1 | 3 | 5 | 2 | 37000 | 6000 | 31 | 0 | 21.8621 | 80.9517 | 1
120 | भूमि सुधार एवं मेड बंधान कार्य | सोनकुंवर/छिंदी | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8646 | 80.9548 | 1
121 | भूमि सुधार एवं मेड बंधान कार्य | कवलसिंह/चैतराम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8626 | 80.8094 | 1
122 | भूमि सुधार एवं मेड बंधान कार्य | मुन्ना/बिपतराम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8607 | 80.942 | 1
123 | भूमि सुधार एवं मेड बंधान कार्य | छिंदी/धनसाय | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8666 | 80.9417 | 1
124 | भूमि सुधार एवं मेड बंधान कार्य | सुकसिंह/पुनऊ | 1 | 70 | 70 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8608 | 80.9431 | 1
125 | भूमि सुधार एवं मेड बंधान कार्य | रामकुंवर/गनसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8587 | 80.9405 | 1
126 | भूमि सुधार एवं मेड बंधान कार्य | मंगलसिंह /कुंवरसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8949 | 80.9618 | 1
127 | भूमि सुधार एवं मेड बंधान कार्य | चैतु/पिरत | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8949 | 80.9617 | 1
128 | भूमि सुधार एवं मेड बंधान कार्य | जीवंती/बाई | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.893 | 80.893 | 1
129 | भूमि सुधार एवं मेड बंधान कार्य | सवालसिंह/कांसीराम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8943 | 80.9694 | 1
130 | भूमि सुधार एवं मेड बंधान कार्य | गणेश/भुजबल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8927 | 80.9548 | 1
131 | भूमि सुधार एवं मेड बंधान कार्य | तीजाबाई/सोनऊ | 1 | 70 | 70 | 0.3 | 20000 | 19500 | 102 | 1 | 21.892 | 80.9592 | 1
132 | भूमि सुधार एवं मेड बंधान कार्य | हीरालाल/धुरेलाल | 1 | 70 | 70 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8949 | 80.9617 | 1
133 | भूमि सुधार एवं मेड बंधान कार्य | सोनकुंवर/कमलू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8326 | 80.9614 | 1
134 | भूमि सुधार एवं मेड बंधान कार्य | रमेश/bhujbal | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.9429 | 80.9636 | 1
135 | भूमि सुधार एवं मेड बंधान कार्य | रामसिंह/घेरकू | 1 | 70 | 70 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8914 | 80.9624 | 1
136 | कुआँ निर्माण | भक्तु/हगरू | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8326 | 80.9633 | 1
137 | डबरी निर्माण | लक्ष्मण/बखारी | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8584 | 80.9443 | 1
138 | डबरी निर्माण | आनंद/सोभनाथ | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8674 | 80.9506 | 1
139 | भूमि सुधार एवं मेड बंधान कार्य | सुन्दर/बिसरू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8653 | 80.9434 | 1
140 | भूमि सुधार एवं मेड बंधान कार्य | बाबूलाल/दयालु | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8657 | 80.9428 | 1
141 | भूमि सुधार एवं मेड बंधान कार्य | मीना/सिवलाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8636 | 80.9435 | 1
142 | भूमि सुधार एवं मेड बंधान कार्य | गुहरू/जोगन सिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8626 | 80.8034 | 1
143 | भूमि सुधार एवं मेड बंधान कार्य | अजोर/रामलाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8608 | 80.3432 | 1
144 | भूमि सुधार एवं मेड बंधान कार्य | बुधारी/परसादी | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8607 | 80.942 | 1
145 | भूमि सुधार एवं मेड बंधान कार्य | जोहन /हट्टू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8666 | 80.9417 | 1
146 | भूमि सुधार एवं मेड बंधान कार्य | कुमारीबाई/मुकुटसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8608 | 80.9407 | 1
147 | भूमि सुधार एवं मेड बंधान कार्य | झामसिंह/उजियार | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8587 | 80.9405 | 1
148 | भूमि सुधार एवं मेड बंधान कार्य | शिवनाथ /सोमनाथ | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8576 | 80.9404 | 1
149 | भूमि सुधार एवं मेड बंधान कार्य | डोंगर/सुन्दर | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8376 | 80.4053 | 1
150 | भूमि सुधार एवं मेड बंधान कार्य | सेवंता /महगू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8581 | 80.9429 | 1
151 | भूमि सुधार एवं मेड बंधान कार्य | दुर्जन/कोदू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8584 | 80.9443 | 1
152 | भूमि सुधार एवं मेड बंधान कार्य | अग्राहित/दयालु | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8544 | 80.9448 | 1
153 | भूमि सुधार एवं मेड बंधान कार्य | पुनियाबाई/गुहरू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.7483 | 80.9535 | 1
154 | भूमि सुधार एवं मेड बंधान कार्य | पंचराम/खेलन | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8696 | 80.9512 | 1
155 | भूमि सुधार एवं मेड बंधान कार्य | सीताबाई /धनीराम | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8699 | 80.9506 | 1
156 | भूमि सुधार एवं मेड बंधान कार्य | तिलोकसिंह/दुर्जन सिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.7657 | 80.9455 | 1
157 | भूमि सुधार एवं मेड बंधान कार्य | चैनु/सुकलाल | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8657 | 80.9428 | 1
158 | भूमि सुधार एवं मेड बंधान कार्य | सगनी बाई/रूपसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8636 | 80.9435 | 1
159 | भूमि सुधार एवं मेड बंधान कार्य | महगू/धरमु | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8626 | 80.8094 | 1
160 | भूमि सुधार एवं मेड बंधान कार्य | शेरसिंह /हगरू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8665 | 80.9432 | 1
161 | भूमि सुधार एवं मेड बंधान कार्य | तिसर/जगतु | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8607 | 80.942 | 1
162 | भूमि सुधार एवं मेड बंधान कार्य | लगतु/हगरू | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8604 | 80.9417 | 1
163 | भूमि सुधार एवं मेड बंधान कार्य | बुधसिंह/पूनउ | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8579 | 80.9404 | 1
164 | तालाब निर्माण | सामूहिक कार्य | 1 | 200 | 150 | 3 | 1408500 | 1400000 | 7253 | 38.11 | 21.8576 | 80.9404 | 6
165 | मुर्गी शेड निर्माण | मानसिंह/हीरासिंह | 1 | 3.5 | 2 | 1.8 | 68000 | 15000 | 78 | 0 | 21.8657 | 80.9428 | 1
166 | पशुशेड निर्माण | बरेलाल/जय सिंह | 1 | 3 | 5 | 2 | 35000 | 34500 | 181 | 0 | 21.8636 | 80.9435 | 1
167 | पशुशेड निर्माण | सक्तु/चंदुलाल | 1 | 3 | 5 | 2 | 50000 | 49500 | 260 | 0 | 21.8626 | 80.8034 | 1
168 | भूमि सुधार एवं मेड बंधान कार्य | सुमित्रा/मानसिंह | 1 | 70 | 70 | 0.3 | 50000 | 49500 | 260 | 1 | 21.8608 | 80.3432 | 1
169 | कुआँ निर्माण | भगतु /हगरू | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8579 | 80.9404 | 1
170 | कुआँ निर्माण | सालिक राम /छोटू | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8576 | 80.9404 | 1
171 | कुआँ निर्माण | अंगद /तेजराम | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8576 | 80.9406 | 1
172 | भूमि सुधार एवं मेड बंधान कार्य | घुरउ/बनउ | 1 | 55 | 55 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8581 | 80.9429 | 1
173 | भूमि सुधार एवं मेड बंधान कार्य | जोहन /कैसल राम | 1 | 55 | 55 | 0.3 | 35000 | 34500 | 181 | 1 | 21.8584 | 80.9443 | 1
174 | भूमि सुधार एवं मेड बंधान कार्य | सुखमत /झुरू | 1 | 55 | 55 | 0.3 | 140000 | 122000 | 642 | 1 | 21.8646 | 80.9548 | 1
175 | डबरी निर्माण | तुलसी /रामलाल | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8666 | 80.9417 | 1
176 | डबरी निर्माण | हिरोंदा /उजियार | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8608 | 80.9431 | 1
177 | डबरी निर्माण | सालिक राम /करन | 1 | 20 | 20 | 3 | 222000 | 84000 | 442 | 1.5 | 21.8949 | 80.9618 | 1
178 | कुआँ निर्माण | सावली /सालिक | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 294 | 5.39 | 21.893 | 80.893 | 1
179 | कुआँ निर्माण | विदेश /जंगल | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8943 | 80.9694 | 1
180 | कुआँ निर्माण | सेवंता /महगू | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.8927 | 80.9548 | 1
181 | कुआँ निर्माण | इश्वर/छोटेलाल | 1 | 4.5 | 4.5 | 6.09 | 198000 | 56000 | 1042.1053 | 5.39 | 21.892 | 80.9592 | 1
कुल :- | [6 empty] | 20527100 | 15956800 | 94382.4737 | 436.01 |  |  | 242