## e-DPR
e-DPR of Korbi C GP, Block -Podi Uproda , District- Korba, Chhattisgarh
A |  | Back ground profile
Micro Watershed code
|  | District | Korba
|  | Block | Podi Uproda
|  | Gram Panchayat | Korbi C
|  | Villages Covered | Korbi C, Achanakpur
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) | 462.05
|  | Rainfall (mm) | 1264.4
|  | Soil type | Sandy loam, Clay loam, clay
|  | Average Slope | 5%
|  | Details of Tributaries | Ghoghari Nala | 1200 m
C |  | DEMOGRAPHIC PROFILE
|  | Total Population | 1376
|  | Total HouseHolds | 315
|  | ST Population | 840
|  | SC Population | 154
D |  | MGNREGA Status
|  | NREGA Job card holders | 236
|  | Person days per year (average of last 3 years) | 52
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 18
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 22.02
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 42.66
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) | 261
|  | Multi cropped (Ha) | 3.48
|  | Current fallow(Ha) | 13.49
|  | Forest /Plantation (Ha) | 125.67
|  | Waste land (Ha) | 30.11
|  | Impounded Waterbody (Ha) | 3.51
|  | Others (Ha) | 24.79
F |  | LAND CLASSIFICATION
|  | Forest (Ha) | 125.67
|  | Upland (Ha) | 98.5856
|  | Medium land (Ha) | 92.424
|  | Low Land (Ha) | 117.0704
|  | River Stream Length (m) | 1200
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds | 13
|  | Borewells | 4
|  | Open wells | 20
H |  | Livelihood profile
|  | Agriculture | 4.47%
|  | Off Farm Activities | 3.51%
|  | Wages, labour | 70.31%
|  | Business | .
|  | Service/ job | 21.71%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) | 68.13
|  | Total Water Available (Ham) | 40.91
|  | Water Resource to be created (Ham) | 27.22
|  | Water Resourse Planned ( Ha M) | 36.43
|  | % of Water requirment fulfilled though MWS | 133.8%
J |  | EXPECTED OUTCOME
|  | Increase in Cropping area (in Ha) | 164.44
|  | Increase in Irrigated area (in Ha) | 113.97
|  | Income Enhancement (INR 50,000 per annum as additional income) | 137
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Beneficiary | No. | Dimension |  |  | Estimated cost (lakh) | Estimated labour cost | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
|  |  |  | Length (m) | Width (m) | Depth (m) | Lakh Rs. | Lakh Rs. | days | in Ha | in decimal
Individual Works:
1 | Dugwell | Tanuja ratre | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4894 | 82.4943 | 1
2 | Dugwell | Lakshman singh | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4896 | 82.4959 | 1
3 | Dugwell | Khol bahar nayak | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4862 | 82.4862 | 1
4 | Dugwell | Teras bai | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4913 | 82.4913 | 1
5 | Dugwell | Rava ji lal | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4912 | 82.4891 | 1
6 | Dugwell | Sahas ram | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4902 | 82.4981 | 1
7 | Dugwell | Adham singh/Parash ram | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4891 | 82.4937 | 1
8 | Dugwell | Shivratan singh/Anand ram | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4809 | 82.8075 | 1
9 | Dugwell | Dev narayan | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4915 | 82.492 | 1
10 | Dugwell | Mahipaal ratre | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4825 | 82.5076 | 1
11 | Dugwell | Ram Kumar singh | 1 |  | 6 | 9 | 0.6 | 0.15 | 87.2093 | 2.03 | 22.4917 | 82.4908 | 1
12 | Dabri | Kadam bai Kurrey | 1 | 20 | 20 | 3 | 0.5 | 0.45 | 261.6279 | 1.5 | 22.4783 | 82.4988 | 1
13 | Dabri | Naresh kurrey | 1 | 20 | 20 | 3 | 0.5 | 0.45 | 261.6279 | 1.5 | 22.4905 | 82.4986 | 1
14 | Dabri | Budhwar singh kawar | 1 | 20 | 20 | 3 | 0.5 | 0.45 | 261.6279 | 1.5 | 22.4892 | 82.4937 | 1
15 | Dabri | Anand singh Sarothiya | 1 | 20 | 20 | 3 | 0.5 | 0.45 | 261.6279 | 1.5 | 22.4802 | 82.8015 | 1
16 | Dabri | Tanuja ratre | 1 | 20 | 20 | 3 | 1.26 | 1.134 | 590 | 1.5 | 22.4782 | 82.4984 | 1
17 | Dabri | Ramkumar | 1 | 20 | 20 | 3 | 0.5 | 0.45 | 261.6279 | 1.5 | 22.4897 | 82.4932 | 1
18 | Pond Renovation | Rahul ratre | 1 | 55 | 50 | 1.5 | 0.5 | 0.45 | 261.6279 | 6.47 | 22.4893 | 82.4914 | 5
19 | Pond Renovation | Community Work(Gauraha) | 1 | 55 | 50 | 1.5 | 0.5 | 0.45 | 261.6279 | 6.47 | 22.4874 | 82.4907 | 5
20 | Farm Bunding | Janak ram | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 2 | 22.4826 | 82.5079 | 1
21 | Farm Bunding | Ram lal | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 1.2 | 22.4824 | 82.4921 | 1
22 | Farm Bunding | ram kumar | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 1 | 22.4908 | 82.4903 | 1
23 | Farm Bunding | Lokesh markam | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 1.5 | 22.4868 | 82.4869 | 1
24 | Farm Bunding | Dharmendra kumar | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 2 | 22.4918 | 82.4916 | 1
25 | Farm Bunding | Madho Kumar | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 1 | 22.4915 | 82.4892 | 1
26 | Farm Bunding | Ramesh kumar | 1 | 60 | 60 |  | 0.1 | 0.09 | 52.3256 | 1.5 | 22.4918 | 82.4925 | 1
27 | Pond Renovation | Community Work(Gauraha) | 1 | 55 | 50 | 1.5 | 8.16 | 7.344 | 3865.2632 | 6.47 | 22.4835 | 82.5078 | 5
28 | Dabri | Chhabila Bai | 1 | 20 | 20 | 3 | 1.49 | 1.32 | 694.7368 | 1.5 | 22.4896 | 82.4933 | 1
29 | Dabri | Jugur Bai | 1 | 20 | 20 | 3 | 1.49 | 1.32 | 694.7368 | 1.5 | 22.4905 | 82.4902 | 1
30 | Pond | Budkunvar | 1 | 55 | 50 | 3 | 10.82 | 10.05 | 5289.4737 | 12.37 | 22.4891 | 82.4916 | 5
31 | Dugwell | Nira Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4814 | 82.5359 | 1
32 | Dugwell | Bhagwat Singh | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4712 | 82.4691 | 1
33 | Dugwell | Shakuntala | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4828 | 82.444 | 1
34 | Dugwell | Etvara Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4894 | 82.4335 | 1
35 | Pond Renovation | Fuleshwari | 1 | 55 | 50 | 1.5 | 10.82 | 10.05 | 5289.4737 | 6.47 | 22.4909 | 62.4807 | 5
36 | Farm Bunding | Budhvara Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1.326 | 22.4814 | 82.49 | 1
37 | Farm Bunding | Kamal Kunvar Gond | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.267 | 22.5113 | 82.8213 | 1
38 | Farm Bunding | Sukhiram | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1.02 | 22.5113 | 82.4913 | 1
39 | Dugwell | Chanvati | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4657 | 82.4478 | 1
40 | Dugwell | Bimala Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4898 | 82.4333 | 1
41 | Farm Bunding | Amrita Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.85 | 22.4896 | 82.4932 | 1
42 | Dugwell | Neha Kanvar | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4882 | 82.502 | 1
43 | Farm Bunding | Mina Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4829 | 82.5002 | 1
44 | Farm Bunding | Puspa Devi | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.099 | 22.476 | 82.5015 | 1
45 | Farm Bunding | Urmila Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4881 | 82.4892 | 1
46 | Farm Bunding | Tijbai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 2.5 | 22.4843 | 82.4853 | 1
47 | Dugwell | Ganga Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4927 | 82.4906 | 1
48 | Dugwell | Kaleshwari Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4902 | 82.4916 | 1
49 | Farm Bunding | Amrika Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.5975 | 22.4913 | 82.489 | 1
50 | Farm Bunding | Koushilya Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.1 | 22.4755 | 82.5003 | 1
51 | Farm Bunding | Jhagli Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4829 | 82.5003 | 1
52 | Farm Bunding | Samarin Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.5 | 22.4029 | 82.5004 | 1
53 | Farm Bunding | Shanti Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1.1875 | 22.483096` | 82.502 | 1
54 | Farm Bunding | Surupa Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.405 | 22.4912 | 82.4899 | 1
55 | Farm Bunding | Koushilya Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.6225 | 22.4754 | 82.5001 | 1
56 | Farm Bunding | Teras Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.05 | 22.4897 | 82.4932 | 1
57 | Farm Bunding | Maya Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 2 | 22.4754 | 82.5001 | 1
58 | Farm Bunding | Basanti Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.3525 | 22.4793 | 82.4916 | 1
59 | Farm Bunding | Bhamati | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 2 | 22.4861 | 82.4967 | 1
60 | Farm Bunding | Lila Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.05 | 22.4897 | 82.4932 | 1
61 | Farm Bunding | Urmila Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4397 | 82.4932 | 1
62 | Farm Bunding | Binda Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4896 | 82.494 | 1
63 | Farm Bunding | Saroj Bai Markam | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.485 | 22.4888 | 82.4892 | 1
64 | Dugwell | Savitri Bai Maravi | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4902 | 82.4916 | 1
65 | Farm Bunding | Sagun Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.19 | 22.4896 | 82.4312 | 1
66 | Farm Bunding | Sumintra Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.142 | 22.4897 | 82.4932 | 1
67 | Farm Bunding | Kevra Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.182 | 22.4697 | 82.4932 | 1
68 | Dugwell | Savitri | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4905 | 82.499 | 1
69 | Farm Bunding | Jamuna Bai Mahant | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.651 | 22.4897 | 82.4932 | 1
70 | Farm Bunding | Dharam Kunvar | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.191 | 22.4854 | 82.4832 | 1
71 | Dabri | Chhabila Bai | 1 | 20 | 20 | 3 | 1.49 | 1.32 | 694.7368 | 1.5 | 22.4896 | 82.4933 | 1
72 | Farm Bunding | Sadhan Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.162 | 22.4897 | 82.4958 | 1
73 | Farm Bunding | Endkunvar | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.429 | 22.4862 | 82.4867 | 1
74 | Pond Renovation | Brijmati | 1 | 55 | 50 | 1.5 | 10.82 | 10.05 | 5289.4737 | 6.47 | 22.4911 | 82.4918 | 5
75 | Farm Bunding | Koushilya Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.294 | 22.4913 | 82.4891 | 1
76 | Farm Bunding | Punni Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 5.8 | 22.4901 | 82.498 | 1
77 | Farm Bunding | Arji Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.085 | 22.4829 | 82.5009 | 1
78 | Farm Bunding | Vranda Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.202 | 22.4862 | 82.4961 | 1
79 | Dabri | Jugur Bai | 1 | 20 | 20 | 3 | 1.49 | 1.32 | 694.7368 | 1.5 | 22.4905 | 82.4902 | 1
80 | Farm Bunding | Sukvara Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.21 | 22.4805 | 82.5056 | 1
81 | Farm Bunding | Laxmaniya Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.138 | 22.4667 | 82.4932 | 1
82 | Dugwell | Parmila Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4897 | 82.4932 | 1
83 | Farm Bunding | Chandshekhar | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.109 | 22.4897 | 82.4932 | 1
84 | Farm Bunding | Panchkunvar | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.239 | 22.4897 | 82.4932 | 1
85 | Farm Bunding | Shanti Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1.5 | 22.4804 | 82.8045 | 1
86 | Dugwell | Savitri Bai | 1 |  | 6 | 9 | 2.1 | 0.64 | 336.8421 | 2.03 | 22.4905 | 82.499 | 1
87 | Farm Bunding | Rajani Kurre | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 2 | 22.4805 | 82.5056 | 1
88 | Farm Bunding | Dulourin Bai/Laxminarayan | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1.68 | 22.4913 | 82.4909 | 1
89 | Farm Bunding | Mangli Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 0.162 | 22.4787 | 82.4981 | 1
90 | Farm Bunding | Gonda Bai | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4897 | 82.4933 | 1
91 | Pond | Budkunvar | 1 | 55 | 50 | 3 | 10.82 | 10.05 | 5289.4737 | 12.37 | 22.4891 | 82.4916 | 5
92 | Farm Bunding | Sushila Ratre | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 1 | 22.4871 | 82.4908 | 1
93 | Farm Bunding | Kadam Bai Kurre | 1 | 60 | 60 |  | 0.27 | 0.23 | 121.0526 | 4 | 22.4785 | 82.4982 | 1
94 | Pond | Community Work(Nawamuda) | 1 | 55 | 50 | 3 | 11.71 | 10.54 | 5547.3684 | 12.37 | 22.4914 | 82.4902 | 5
95 | Pond Renovation | Community Work(Buraha) | 1 | 55 | 50 | 1.5 | 11.71 | 10.54 | 5547.3684 | 6.47 | 22.4865 | 82.4862 | 5
96 | Dabri | Sewa ram | 1 | 20 | 20 | 3 | 1.4 | 1.246 | 645 | 1.5 | 22.4802 | 82.8015 | 1
97 | Dabri | Anand singh | 1 | 20 | 20 | 3 | 1.4 | 1.246 | 645 | 1.5 | 22.4913 | 82.4891 | 1
98 | Dabri | Magho kumar | 1 | 20 | 20 | 3 | 1.4 | 1.246 | 645 | 1.5 | 22.4901 | 82.498 | 1
99 | Dabri | Tij ram yadav | 1 | 20 | 20 | 3 | 1.4 | 1.246 | 645 | 1.5 | 22.4782 | 82.4984 | 1
100 | Gothan | Gothan community work | 1 |  |  |  | 0.978 | 0.5868 | 304.0415 | 0 | 22.4897 | 82.4932
101 | Pond | Community Work Dugupara | 1 | 55 | 50 | 3 | 10.163 | 9.045 | 4710 | 12.37 | 22.4902 | 82.4981 | 5
102 | Pond | Daripaithu Community Work | 1 | 55 | 50 | 3 | 11.71 | 1.17 | 5489 | 12.37 | 22.5113 | 82.4913 | 5
103 | Pond | Achankpur Katelpara Community Work | 1 | 55 | 50 | 3 | 11.71 | 1.17 | 5489 | 12.37 | 22.4657 | 82.4478 | 5
104 | EGP | KHARA NALA (EGP-10) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4902 | 82.4982 | 1
105 | EGP | KHARA NALA (EGP-11) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
106 | EGP | KHARA NALA (EGP-12) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4902 | 82.4982 | 1
107 | EGP | KHARA NALA (EGP-13) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
108 | EGP | KHARA NALA (EGP-14) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
109 | EGP | KHARA NALA (EGP-3) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
110 | EGP | KHARA NALA (EGP-4) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
111 | EGP | KHARA NALA (EGP-5) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4981 | 1
112 | EGP | KHARA NALA (EGP-6) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
113 | EGP | KHARA NALA (EGP-7) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
114 | EGP | KELHA NALA (EGP-8) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4901 | 82.4982 | 1
115 | EGP | KHARA NALA (EGP-9) | 1 |  | 5 | 1 | 0.267 | 0.251 | 130.0518 | 0.5 | 22.4902 | 82.4983 | 1
116 | New Pond | NAYA TALAB NIRMAD KARY KORBI C | 1 | 55 | 50 | 3 | 13.07 | 12.42 | 6435.2332 | 12.37 | 22.4897 | 82.4932 | 5
117 | New Pond | NAYA TALAB NIRMAD KARY GHERIMUDA | 1 | 55 | 50 | 3 | 13.07 | 12.42 | 6435.2332 | 12.37 | 22.4804 | 82.8045 | 5
118 | Farm Pond | JAYKARAN /AANAD SINGH | 1 | 20 | 20 | 3 | 1.38 | 1.286 | 666.3212 | 1.5 | 22.4905 | 82.4986
119 | Farm Pond | GOVIND SINGH /KHOLBAHRA | 1 | 20 | 20 | 3 | 1.38 | 1.286 | 666.3212 | 1.5 | 22.4892 | 82.4937
120 | Land development | Korbi C Gouthan Parisar Me Soakpit Mitti Murum Road Kotna Pakk Farsh Evam Urine Tank Nirman Karya | 1 | 60 | 60 |  | 7.3881 | 6.6493 | 3445.228 | 0.5 | 22.4754 | 82.5001 | 1
121 | dabri | korbi c dabri nirman karya naresh kumar | 1 | 20 | 20 | 3 | 1.2765 | 1.1488 | 595.2591 | 1.5 | 22.4902 | 82.4916 | 1
122 | dabri | korbi c dabri nirman karya ram kumar ram singh | 1 | 20 | 20 | 3 | 1.269 | 1.1421 | 591.7617 | 1.5 | 22.4913 | 82.489 | 1
123 | dabri | korbi c dabri nirman karya tanuja ratre dilip kumar | 1 | 20 | 20 | 3 | 1.269 | 1.1421 | 591.7617 | 1.5 | 22.4897 | 82.4932 | 1
124 | Vermi tank | Korbi (c) SHG hetu Vermi compost Tank (Taka) 10 Nag nirman Karya | 10 | 3.6 | 1.5 | 1 | 3.1318 | 2.8186 | 1460.4249 | 0 | 22.4896 | 82.4312 | 5
125 | Pond renovation | korbi c burahha talab gahri karan achankpur | 1 | 55 | 50 | 1.5 | 11.7189 | 10.547 | 5464.772 | 6.47 | 22.4897 | 82.4932 | 5
126 | Pond Renovation | Korbi C Talab Gahari karan Karya dugupara | 1 | 55 | 50 | 1.5 | 11.7124 | 10.5412 | 5461.7409 | 6.47 | 22.4902 | 82.4981 | 5
127 | Vermi tank | Korbi C Swah Sahayta Samuh Ke liye Vermi Taka Nirman Karya Bhag -III | 1 |  |  |  | 9.29 | 8.361 | 4332.1244 |  | 22.4891 | 82.4937 | 5
Total |  |  | 136 |  |  |  | 251.6507 | 188.8679 | 108748.9792 | 284.418 |  |  | 196

## NREGA Data (hidden)
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Baspattar | [5 empty] | As on 10-06-2020
I Job Card
Total No. of JobCards issued | 302
Total No. of Workers | 1445
Total No. of Active Job Cards | 291
Total No. of Active Workers | 1329
(i)SC worker against active workers[%] | 1.05
(ii)ST worker against active workers[%] | 65.46
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9390 | 37789 | 32713 | 34769 | 15342
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 1.66 | 1.37 | 1.13 | 0.89 | 1.1
ST persondays % as of total persondays | 54.1 | 50.59 | 53.89 | 51.82 | 44.81
Women Persondays out of Total (%) | 47.74 | 48.15 | 47.82 | 51.61 | 51.3
Average days of employment provided per Household | 42.49 | 133.06 | 115.19 | 124.18 | 57.25
Average Wage rate per day per person(Rs.) | 189.85 | 175.93 | 174 | 172 | 167
Total No of HHs completed 100 Days of Wage Employment | 0 | 233 | 204 | 198 | 23
Total Households Worked | 221 | 284 | 284 | 280 | 268
Total Individuals Worked | 455 | 627 | 617 | 606 | 555
Differently abled persons worked | 1 | 4 | 0 | 1 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 47 | 75 | 117 | 85 | 80
Number of Ongoing Works | 19 | 41 | 42 | 44 | 41
Number of Completed Works | 28 | 34 | 75 | 41 | 39
% of NRM Expenditure(Public + Individual) | 83.17 | 85.02 | 77.45 | 86.74 | 69.31
% of Category B Works | 85.11 | 90.67 | 94.02 | 82.35 | 80
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 33.78 | 70.99 | 62.08 | 68.25 | 28.57
Wages(Rs. In Lakhs) | 25.31 | 60.5 | 55.2 | 59.49 | 24.23
Material and skilled Wages(Rs. In Lakhs) | 8.28 | 9.83 | 6.08 | 7.78 | 3.46
Material(%) | 24.65 | 13.98 | 9.92 | 11.56 | 12.51
Total Adm Expenditure (Rs. in Lakhs.) | 0.18 | 0.66 | 0.8 | 0.98 | 0.88
Admin Exp(%) | 0.53 | 0.93 | 1.29 | 1.44 | 3.08
Average Cost Per Day Per Person(In Rs.) | 193.08 | 202 | 176.44 | 195.03 | 178.38
% of Total Expenditure through EFMS | 100 | 100 | 99.98 | 99.73 | 100
% payments gererated within 15 days | 100 | 79.31 | 90.55 | 100 | 45.71

## Calculation (hidden)
Tentative treated area calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | capacity/ volume (In Cum) | Command area (Irrigated Area ) | Minimum required catchment area | Area Treated
|  |  | Dimenssion | in m | in m | in m | In Cum | in Ha | In Ha | In Ha
1 | Farm Pond | शामकुंवर/रामबिशेष | 23X23X3 | 25 | 25 | 3 | 1491.87 | 0.74594 | 1.4919 | 2.2378
2 | Farm Pond | बंदीराम/दयाराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
3 | Farm Pond | आत्माराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
4 | Farm Pond | आत्माराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
5 | Farm Pond | कमितला बाई/सुकडू | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
6 | Farm Pond | बंदीराम/दयाराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
7 | Farm Pond | चैनबती मरकाम/रामदयाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
8 | Farm Pond | रामदयाल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
9 | Farm Pond | सुकमन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
10 | Farm Pond | भागबती | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
11 | Farm Pond | नारायण | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
12 | Farm Pond | नारद | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
13 | Farm Pond | गनेशिया बाई/आनंद राम सोनी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
14 | Farm Pond | नारायण मरकाम/मेहत्तर | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
15 | Farm Pond | सुकलाईन/धनसिंग विश्वकर्मा | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
16 | Farm Pond | बरमन कुलदीप/कंगलाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
17 | Farm Pond | दसरु राम यादव/मेहत्तर यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
18 | Farm Pond | रमेश सोनवानी/राजकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
19 | Farm Pond | पीलादास मरकाम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
20 | Farm Pond | दयमोतीन नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
21 | Farm Pond | अघनसिंह नेताम/तिजिया नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
22 | Farm Pond | रामसिंह वट्टी/केशरी बाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
23 | Farm Pond | प्रभुराम वट्टी/स्वयं | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
24 | Farm Pond | लतखोरीन नेताम/छेरका | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
25 | Farm Pond | मनराखन यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
26 | Farm Pond | मन्नूराम भास्कर/झंगन सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
27 | Farm Pond | पुष्कर/नथेला राम यादव | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
28 | Farm Pond | लक्ष्मी लाल/गनेशिया | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
29 | Farm Pond | नोहर सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
30 | Farm Pond | नोहर सिंह | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
31 | Farm Pond | राजकुमार/सोनूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
32 | Farm Pond | राम/हलाल राम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
33 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
34 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
35 | Farm Pond | झाड़ूराम/लादूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
36 | Farm Pond | झाड़ूराम/लादूराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
37 | Farm Pond | नोहरसिंह/मसिया | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
38 | Farm Pond | फूलसिंह/हीरासिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
39 | Farm Pond | उदेराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
40 | Farm Pond | लक्ष्मण | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
41 | Farm Pond | पिलाराम/रामभरोष | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
42 | Farm Pond | धनीराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
43 | Farm Pond | चमरसिंह /सुरेखा नेताम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
44 | Farm Pond | रामनाथ/रमतुला वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
45 | Farm Pond | नन्दकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
46 | Farm Pond | चमरसिंह/सगन बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
47 | Farm Pond | जयलाल नेताम/अघनबाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
48 | Farm Pond | सुकबाई यादव/स्वयं | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
49 | Farm Pond | सुकबाई यादव/स्वयं | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
50 | Farm Pond | रामजी/मानकी वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
51 | Farm Pond | नवल सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
52 | Farm Pond | नवल यादव/दल्ली यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
53 | Farm Pond | दुर्जन यादव/दिनदयाल | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
54 | Farm Pond | धनेश यादव/धर्मिन | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
55 | Farm Pond | धनेश यादव/धर्मिन | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
56 | Farm Pond | गुहाराम यादव/अहिल्या | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
57 | Farm Pond | छन्नू राम/उषा बाई | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
58 | Farm Pond | छन्नू राम/उषा बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
59 | Farm Pond | लालसाय मंडावी | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
60 | Farm Pond | लक्ष्मीनाथ नेताम/बैजनतीन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
61 | Farm Pond | रामबती/सुकलाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
62 | Farm Pond | शांति बाई/रामसिंग | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
63 | Farm Pond | बिन्देसिंह/रोहीदास | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
64 | Farm Pond | अमरोबाई/रामजी | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
65 | Farm Pond | जयराम/रामचंद | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
66 | Farm Pond | सन्तुराम मंडावी/सवित्री | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
67 | Farm Pond | आनंदराम नेताम/दुखिया | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
68 | Farm Pond | आनंदराम नेताम/दुखिया | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
69 | Farm Pond | दुखिया नेताम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
70 | Farm Pond | संग्राम/रामसिंह | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
71 | Farm Pond | कनसी/सैदर | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
72 | Farm Pond | किसनू/जोहन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
73 | Farm Pond | कौशिल्या/दीपल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
74 | Farm Pond | प्रवीण मरकाम/रामचंद | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
75 | Land levelling | रूपनाथ मरकाम/परमिला मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
76 | Land levelling | राजाराम मरकाम/चंद्रिका मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
77 | Land levelling | अनीत मरकाम/बृजबती | 1.01 | 1.01 | [5 empty] | 1.01
78 | Land levelling | नीलम कुमार/सगारो बाई | 0.8 | 0.8 | [5 empty] | 0.8
79 | Land levelling | अघनसिंह नेताम/तिजिया नेताम | 0.4 | 0.4 | [5 empty] | 0.4
80 | Land levelling | रूपराय मरकाम/रेमा मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
81 | Land levelling | मोहनराम वट्टी/भवनतीन वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
82 | Land levelling | प्रभुराम वट्टी/स्वयं | 0.4 | 0.4 | [5 empty] | 0.4
83 | Land levelling | रामसिंह वट्टी/केशरी बाई | 0.4 | 0.4 | [5 empty] | 0.4
84 | Land levelling | सगनी/देवराज मरकाम | 0.4 | 0.4 | [5 empty] | 0.4
85 | Land levelling | अमरसिंह/परमिला | 0.4 | 0.4 | [5 empty] | 0.4
86 | Land levelling | उदेराम | 0.8 | 0.8 | [5 empty] | 0.8
87 | Land levelling | रामनाथ/रमतुला वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
88 | Land levelling | धनीराम | 0.8 | 0.8 | [5 empty] | 0.8
89 | Land levelling | श्री राम/दयाबती | 0.2 | 0.2 | [5 empty] | 0.2
90 | Land levelling | चमरसिंह/सगन बाई | 0.8 | 0.8 | [5 empty] | 0.8
91 | Land levelling | जयलाल नेताम/अघनबाई | 0.8 | 0.8 | [5 empty] | 0.8
92 | Land levelling | रामजी/मानकी वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
93 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
94 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
95 | Land levelling | लक्ष्मीनाथ नेताम/बैजनतीन | 0.4 | 0.4 | [5 empty] | 0.4
96 | Land levelling | संगीता/राम नेताम | 0.04 | 0.04 | [5 empty] | 0.04
97 | Land levelling | राजूराम/रामसिंग | 0.8 | 0.8 | [5 empty] | 0.8
98 | Land levelling | जयराम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
99 | Land levelling | सिरमो/छेदीलाल | 0.4 | 0.4 | [5 empty] | 0.4
100 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.5 | 0.5 | [5 empty] | 0.5
101 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.4 | 0.4 | [5 empty] | 0.4
102 | Land levelling | लक्ष्मीनाथ/बैजन्तीन | 0.4 | 0.4 | [5 empty] | 0.4
103 | Land levelling | संग्राम/रामसिंह | 0.04 | 0.04 | [5 empty] | 0.04
104 | Plantation | मन्नूराम भास्कर/झंगन सिंह | 0.4 | 0.4 | [5 empty] | 0.4
105 | Plantation | सुकबाई यादव/स्वयं | 0.2 | 0.2 | [5 empty] | 0.2
106 | Plantation | दुर्जन यादव/दिनदयाल | 0.5 | 0.5 | [5 empty] | 0.5
107 | Plantation | धनेश यादव/धर्मिन | 0.5 | 0.5 | [5 empty] | 0.5
108 | Plantation | गुहाराम यादव/अहिल्या | 0.5 | 0.5 | [5 empty] | 0.5
109 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  | as per Field data |  | 1
110 | Dug Well | नारद/जयलाल | 7X7 | 7 | 7 |  |  |  |  | 1
111 | Dug Well | आत्माराम | 7X7 | 7 | 7 |  |  |  |  | 1
112 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  |  |  | 1
113 | Dug Well | बंदीराम/दयाराम | 7X7 | 7 | 7 |  |  |  |  | 1
114 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
115 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
116 | Dug Well | नारायण | 7X7 | 7 | 7 |  |  |  |  | 1
117 | Dug Well | सुकमन | 7X7 | 7 | 7 |  |  |  |  | 1
118 | Dug Well | भागबती | 7X7 | 7 | 7 |  |  |  |  | 1
119 | Dug Well | दशोबाई | 7X7 | 7 | 7 |  |  |  |  | 1
120 | Dug Well | नरेश | 7X7 | 7 | 7 |  |  |  |  | 1
121 | Dug Well | शामकुंवर/रामबिशेष | 7X7 | 7 | 7 |  |  |  |  | 1
122 | Dug Well | गनेशिया बाई/आनंद राम सोनी | 7X7 | 7 | 7 |  |  |  |  | 1
123 | Dug Well | माखन यादव/तिभू | 7X7 | 7 | 7 |  |  |  |  | 1
124 | Dug Well | तीजऊ राम यादव/बिसऊराम | 7X7 | 7 | 7 |  |  |  |  | 1
125 | Dug Well | सुकलाईन/धनसिंग विश्वकर्मा | 7X7 | 7 | 7 |  |  |  |  | 1
126 | Dug Well | बरमन कुलदीप/कंगलाराम | 7X7 | 7 | 7 |  |  |  |  | 1
127 | Dug Well | रामबाई सोनवानी/तुलीया राम सोनवानी | 7X7 | 7 | 7 |  |  |  |  | 1
128 | Dug Well | भगवान सिंह मरकाम/ | 7X7 | 7 | 7 |  |  |  |  | 1
129 | Dug Well | केशव मरकाम/बिराजो मरकाम | 7X7 | 7 | 7 |  |  |  |  | 1
130 | Dug Well | शिवनारायण यादव/रजमन | 7X7 | 7 | 7 |  |  |  |  | 1
131 | Dug Well | लतखोरीन नेताम/छेरका | 7X7 | 7 | 7 |  |  |  |  | 1
132 | Dug Well | श्याम लाल यादव/लतखोर | 7X7 | 7 | 7 |  |  |  |  | 1
133 | Dug Well | मन्नूराम भास्कर/झंगन सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
134 | Dug Well | मोती राम सोनी/मोहन लाल | 7X7 | 7 | 7 |  |  |  |  | 1
135 | Dug Well | राजकुमार/सोनूराम | 7X7 | 7 | 7 |  |  |  |  | 1
136 | Dug Well | झाड़ूराम/लादूराम | 7X7 | 7 | 7 |  |  |  |  | 1
137 | Dug Well | नोहरसिंह/मसिया | 7X7 | 7 | 7 |  |  |  |  | 1
138 | Dug Well | अर्जुन/दीनदयाल | 7X7 | 7 | 7 |  |  |  |  | 1
139 | Dug Well | छन्नू राम | 7X7 | 7 | 7 |  |  |  |  | 1
140 | Dug Well | उदेराम | 7X7 | 7 | 7 |  |  |  |  | 1
141 | Dug Well | लक्ष्मण | 7X7 | 7 | 7 |  |  |  |  | 1
142 | Dug Well | पिलाराम/रामभरोष | 7X7 | 7 | 7 |  |  |  |  | 1
143 | Dug Well | श्री राम/दयाबती | 7X7 | 7 | 7 |  |  |  |  | 1
144 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
145 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
146 | Dug Well | माखन यादव/तीजू यादव | 7X7 | 7 | 7 |  |  |  |  | 1
147 | Dug Well | नवल सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
148 | Dug Well | नवल यादव/दल्ली यादव | 7X7 | 7 | 7 |  |  |  |  | 1
149 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
150 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
151 | Dug Well | गुहाराम यादव/अहिल्या | 7X7 | 7 | 7 |  |  |  |  | 1
152 | Dug Well | लालसाय मंडावी | 7X7 | 7 | 7 |  |  |  |  | 1
153 | Dug Well | तुलसी/सुकलाल | 7X7 | 7 | 7 |  |  |  |  | 1
154 | Dug Well | कांशीराम/सैदर | 7X7 | 7 | 7 |  |  |  |  | 1
155 | Dug Well | किसून/जोहन | 7X7 | 7 | 7 |  |  |  |  | 1
156 | Dug Well | कौश्लिया/दीपल | 7X7 | 7 | 7 |  |  |  |  | 1
157 | Dug Well | प्रवीण मरकाम/रामचंद | 7X7 | 7 | 7 |  |  |  |  | 1
158 | Farm bonding | संगीता/श्रीराम | 0.4 | 0.4 | [5 empty] | 0.4
159 | Farm bonding | श्यामलाल/मेहेरसिंह | 0.4 | 0.4 | [5 empty] | 0.4
160 | Farm bonding | प्रवीण मरकाम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
161 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
162 | Desilting | common Land | 45X45X4 | 45 | 45 | 4 | 6421.3511 | 3.2107 | 6.4214 | 9.632
163 | Desilting | common Land | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
164 | Desilting | common Land | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
165 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
166 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1 | Command area as per actual field data (Minimum command area
167 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1
168 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7500 | 13.5 |  | 2 |  | Time of refills X (Submergence area* d/3)
169 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 8750 | 15.75 |  | 2 |  | Time of refills X (Submergence area* d/3)
170 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7200 | 12.96 |  | 2 |  | Time of refills X (Submergence area* d/3)
171 | Checkdam | 3rd Order Nala | 25X 40X1.5 | 25 | 125 | 2 | 8700 | 15.66 |  | 2 |  | Time of refills X (Submergence area* d/3)
172 | Checkdam | 3rd Order Nala | 25X 40X1.6 | 25 | 125 | 2 | 9800 | 17.64 |  | 2 |  | Time of refills X (Submergence area* d/3)
[7 empty] | 237159.0111 | 173.1145 | 195.209 | 372.0235
23.7159

## Sheet1 (hidden)
Earthwork Calculation
| Step | Length m | Width m | Depth m | Volume m3
Hard soil depth
| Step 1 | 23 | 23 | 0.3 | 158.7 | 17.6
| Step 2 | 22.4 | 22.4 | 0.3 | 150.528 | 22.4
| Step 3 | 21.8 | 21.8 | 0.3 | 142.572 | 21.8
| Step 4 | 21.2 | 21.2 | 0.3 | 134.832 | 16.6
| Step 5 | 20.6 | 20.6 | 0.3 | 127.308 | 16
| Step 6 | 20 | 20 | 0.3 | 120 | 20
3 | Step 7 | 19.4 | 19.4 | 0.3 | 112.908 | 19.4
| Step 8 | 18.8 | 18.8 | 0.3 | 106.032 | 18.8
| Step 9 | 18.2 | 18.2 | 0.3 | 99.372 | 18.2
23 | Step 10 | 17.6 | 17.6 | 0.3 | 92.928 | 17.6
23 | Total Earthwork in Cum |  |  |  | 1245.18