## e DPR
e DPR of Dhaurabhata GP, Block Narharpur , Dist kanker Chhattisgarh
| A |  | Back ground profile
|  |  | Micro Watershed code | 4G2G5A3f, 4G2G5A4j, 4G2G5A5i, 4G2G5B2i
|  |  | District | Kanker
|  |  | Block | Narharpur
|  |  | Gram Panchayat | Dhaurabhata
|  |  | Villages Covered | Dhaurabhata, Uraiya
| B |  | PHYSIOGRAPHIC PROFILE
|  |  | Total Area (Ha) | 998.98
|  |  | Rainfall (mm) | 1200
|  |  | Soil type | Sandy Loam
|  |  | Average Slope | 1.5-14%
|  |  | Details of Tributaries | Aama Naala |  |  | 2 km
|  |  |  | Nangara Naala |  |  | 3 km
| C |  | DEMOGRAPHIC PROFILE
|  |  | Total Population | 1380
|  |  | Total HouseHolds | 260
|  |  | ST Population | 1336
|  |  | SC Population | 16
| D |  | MGNREGA Status
|  |  | NREGA Job card holders | 280
|  |  | Person days per year (average of last 3 years) | 14311
|  |  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 72.66
|  |  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 24.56
|  |  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 80.48
| E |  | LAND USE LAND COVER
|  |  | Mono cropped (Ha) | 416.22
|  |  | Multi cropped (Ha) | 14.8
|  |  | Current fallow(Ha) | 14.8
|  |  | Forest /Plantation (Ha) | 195.72
|  |  | Waste land (Ha) | 57.18
|  |  | Impounded Waterbody (Ha) | 17.54
Others (Ha)
| F |  | LAND CLASSIFICATION
|  |  | Forest (Ha) | 195.72
|  |  | Upland (Ha) | 361.77
|  |  | Medium land (Ha) | 285.19
|  |  | Low Land (Ha) | 156.13
|  |  | River Stream Length (m) | 5000 m
| G |  | Existing Water sources/ Structures
|  |  | Water harvesting Ponds | 43 |  |  | 17.9 Ha-m
|  |  | Borewells | 60
|  |  | Open wells | 45
| H |  | Livelihood profile
|  |  | Agriculture | 90%
|  |  | Off Farm Activities | 10%
|  |  | Wages, labour | 85%
|  |  | Business | 3%
|  |  | Service/ job | 6%
| I |  | WATER BUDGET
|  |  | Total Water Requirement (Ham) | 56.925 |  |  | Considering 50% Water requirement will be meet by Rainfall
|  |  | Total Water Available (Ham) | 17.9
|  |  | Water Resource to be created (Ham) | 39.025
|  |  | Water Resourse Planned ( Ha M) | 25.4004
|  |  | % of Water requirment fulfilled though MWS | 65.13%
| J |  | EXPECTED OUTCOME
|  |  | Increase in Cropping area (in Ha) | 84.35
|  |  | Increase in Irrigated area (in Ha) | 55.5
|  |  | Income Enhancement (INR 50000 per annum as additional income) | 70 HH
| K |  | ACTIVITY PROPOSED
| Sr No. | Type of intervention | Name of the Beneficiary | No. |  |  | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area | Targeted HH
Individual Works:
| 1 | Farm Pond | आत्माराम मरकाम | 1 | 20.4712 | 81.7142 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 2 | Farm Pond | तुलसा बाई | 1 | 20.4585 | 81.7153 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 3 | Farm Pond | बुद्धुराम नेताम | 1 | 20.4646 | 81.726 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 4 | Farm Pond | श्यामलाल | 1 | 20.4594 | 81.7236 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 5 | Farm Pond | बसंत नेताम | 1 | 20.46 | 81.7184 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 6 | Farm Pond | रतन नेताम | 1 | 20.4604 | 81.7288 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 7 | Farm Pond | लक्ष्मण नेताम | 1 |  |  | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 8 | Farm Pond | लक्ष्मण नेताम | 1 | 20.4603 | 81.7272 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 9 | Farm Pond | सुकदेव मंडावी | 1 | 20.4672 | 81.7321 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 10 | Farm Pond | लक्ष्मण नेताम | 1 | 20.4584 | 81.7264 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 11 | Farm Pond | लक्ष्मण कोर्राम | 1 | 20.4697 | 81.7192 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 12 | Farm Pond | समलू राम नेताम | 1 | 20.4591 | 81.7134 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 13 | Farm Pond | श्यामलाल | 1 | 20.4596 | 81.7249 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 14 | Farm Pond | छितल राम सलाम | 1 | 20.4555 | 81.716 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 15 | Farm Pond | राम नेताम | 1 | 20.4603 | 81.7181 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 16 | Farm Pond | छित्तल राम सलाम | 1 |  |  | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 17 | Farm Pond | सगराम / सोनुराम | 1 | 20.4609 | 81.7149 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 18 | Farm Pond | चमरा राम नेताम | 1 | 20.4596 | 81.7174 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 19 | Farm Pond | गरभुराम /हीराराम सलाम | 1 | 20.4572 | 81.7229 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 20 | Farm Pond | सगनु राम बुद्धू राम | 1 | 20.4679 | 81.7086 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 21 | Farm Pond | छित्तल राम सलाम | 1 | 20.4553 | 81.7173 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 22 | Farm Pond | राम सलाम | 1 | 20.4712 | 81.7216 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 23 | Farm Pond | रामबाई सलाम | 1 | 20.4553 | 81.716 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 24 | Farm Pond | मानसिंह मरकाम | 1 | 20.4619 | 81.7189 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 25 | Farm Pond | दुखु राम सलाम | 1 | 20.4565 | 81.7232 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 26 | Farm Pond | सगारो बाई सलाम /बरातू | 1 | 20.4572 | 81.7218 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 27 | Farm Pond | गरभुराम /हीराराम सलाम | 1 | 20.4567 | 81.7214 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 28 | Farm Pond | फत्तेसिंग नेताम | 1 | 20.4584 | 81.7121 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 29 | Farm Pond Desiltation | आत्माराम मरकाम | 1 | 20.47 | 81.7162 | 10x100x1.5 | 3.259 | 2.963 | 1775 | 1.9003 | 1
| 30 | Farm Pond Desiltation | शंकर सलाम | 1 | 20.4558 | 81.7178 | 50x50x1.5 | 0.661 | 0.595 | 356 | 0.48 | 1
| 31 | Farm Pond Desiltation | फूलचंद नेताम / सुन्दर | 1 |  |  | 50x50x1.5 | 0.661 | 0.595 | 356 | 0.48 | 1
| 32 | Land levelling | मानसिंह मरकाम | 1 | 20.4619 | 81.7189 | 0.4 | 0.4655 | 0.323 | 184 | 0.4 | 1
| 33 | Land levelling | प्रबल सिंग मरकाम | 1 | 20.4654 | 81.7096 | 0.8 | 0.7885 | 0.646 | 368 | 0.8 | 1
| 34 | Land levelling | घसनिन कावडे | 1 | 20.4655 | 81.7143 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 35 | Land levelling | सांवत राम मंडावी | 1 |  |  | 0.4 | 0.4655 | 0.323 | 184 | 0.4 | 1
| 36 | Land levelling | दुखु राम सलाम | 1 | 20.4565 | 81.7222 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 37 | Land levelling | श्यामलाल | 1 | 20.4597 | 81.7237 | 0.8 | 0.7885 | 0.646 | 368 | 0.8 | 1
| 38 | Land levelling | सगनु राम बुद्धू राम | 1 | 20.4677 | 81.709 | 0.8 | 0.7885 | 0.646 | 368 | 0.8 | 1
| 39 | Land levelling | सुकदेव मंडावी | 1 | 20.4664 | 81.7322 | 0.4 | 0.4655 | 0.323 | 184 | 0.4 | 1
| 40 | Land levelling | शंकर सलाम | 1 | 20.4549 | 81.7159 | 0.4 | 0.4655 | 0.323 | 184 | 0.4 | 1
| 41 | Land levelling | सिया राम नेताम | 1 | 20.4555 | 81.7134 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 42 | Land levelling | सगराम / सोनुराम | 1 | 20.4607 | 81.7148 | 0.8 | 0.7885 | 0.646 | 368 | 0.8 | 1
| 43 | Land levelling | चमरा राम नेताम | 1 | 20.462 | 81.7109 | 0.8 | 0.7885 | 0.646 | 368 | 0.8 | 1
| 44 | Land levelling | सुकदेव मंडावी | 1 | 20.4664 | 81.7322 | 1.6 | 1.4345 | 1.292 | 736 | 1.6 | 1
| 45 | Farm Bunding | दुखु राम सलाम | 1 | 20.4567 | 81.723 | 0.32 | 0.285 | 0.2423 | 138 | 0.32 | 1
| 46 | Farm Bunding | गरभुराम /हीराराम सलाम | 1 | 20.4568 | 81.7212 | 0.9 | 0.57 | 0.4845 | 276 | 0.9 | 1
| 47 | Farm Bunding | कमलेश नेताम | 1 | 20.4598 | 81.719 | 0.14 | 0.19 | 0.1615 | 92 | 0.14 | 1
| 48 | Farm Bunding | फत्तेसिंग नेताम | 1 | 20.4584 | 81.7121 | 0.36 | 0.38 | 0.323 | 184 | 0.36 | 1
| 49 | Farm Bunding | अतिराम नेताम | 1 | 20.4614 | 81.719 | 0.86 | 0.76 | 0.646 | 368 | 0.86 | 1
| 50 | Farm Bunding | भावसिंह मरकाम | 1 | 20.4641 | 81.7105 | 0.94 | 0.76 | 0.646 | 368 | 0.94 | 1
| 51 | Plantation | गंगा राम मरकाम | 1 | 20.4604 | 81.7137 | 0.2 | 0.536 | 0.087 | 50 | 0.2 | 1
| 52 | Plantation | गंगा राम मरकाम | 1 | 20.4603 | 81.7137 | 0.2 | 0.536 | 0.087 | 50 | 0.2 | 1
| 53 | Plantation | लक्ष्मण नेताम | 1 | 20.4603 | 81.7264 | 0.4 | 1.072 | 0.174 | 100 | 0.4 | 1
| 54 | Farm Pond | बसंता बाई / कवलु राम | 1 | 20.4739 | 81.685 | 45x45x3 | 7.861 | 7.155 | 4285 | 4.28 | 1
| 55 | Farm Pond | बसंता नेताम | 1 | 20.4739 | 81.685 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 56 | Farm Pond | प्रभुराम / जुझारी राम | 1 | 20.4727 | 81.703 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 57 | Farm Pond | अर्जुन कोडोपी | 1 | 20.4659 | 81.6946 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 58 | Farm Pond | अर्जुन कोडोपी | 1 | 20.4658 | 81.6954 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 59 | Farm Pond | फिरतु वट्टी | 1 | 20.4772 | 81.6974 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 60 | Farm Pond | सुंदरु राम सलाम | 1 | 20.4797 | 81.6961 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 61 | Farm Pond | सुंदरु राम सलाम | 1 | 20.481 | 81.6965 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 62 | Farm Pond | कुंवरो बाई मरकाम | 1 | 20.473 | 81.6967 | 30X30X3 | 3.261 | 2.963 | 1775 | 1.9003 | 1
| 63 | Farm Pond | मेहत्तर राम / अंजोर सिंग | 1 | 20.4794 | 81.6936 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 64 | Farm Pond | कंवलू राम / धरम सिंग | 1 |  |  | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 65 | Farm Pond | चैनसिंग | 1 | 20.4654 | 81.6921 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 66 | Farm Pond | मोहन राम मंडावी | 1 | 20.4649 | 81.6949 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 67 | Farm Pond | टिकेश्वर निषाद | 1 | 20.4803 | 81.705 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 68 | Farm Pond | संतलाल सिंग कुंजाम | 1 | 20.4797 | 81.7013 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 69 | Farm Pond | नेगी राम / सुन्ना राम | 1 | 20.4754 | 81.7076 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 70 | Farm Pond | गोकुल मरकाम / अमरसिंग | 1 | 20.4761 | 81.6875 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 71 | Farm Pond | पूरन नेताम | 1 | 20.4787 | 81.6956 | 23X23X3 | 1.742 | 1.58 | 908 | 1.0563 | 1
| 72 | Farm Pond | नवलसिंग मरकाम | 1 |  |  | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 73 | Farm Pond | चैतराम नरेटी | 1 | 20.4732 | 81.7038 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 74 | Farm Pond | लादूराम | 1 | 20.4792 | 81.7072 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 75 | Farm Pond | बरसन नेताम / हरक राम | 1 |  |  | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 76 | Farm Pond | पुनीत मरकाम | 1 | 20.4788 | 81.6979 | 15x15x3 | 0.661 | 0.595 | 356 | 0.48 | 1
| 77 | Farm Pond | मंगली बाई मरकाम | 1 | 20.4718 | 81.686 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 78 | Farm Pond | घसिया राम मरकाम | 1 | 20.4696 | 81.6867 | 9x12x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 79 | Farm Pond | माहरीन बाई नेताम | 1 | 20.4837 | 81.6817 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 80 | Farm Pond | ठाकुर राम शोरी | 1 | 20.4809 | 81.7069 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 81 | Farm Pond | जोहर नेताम / चरणसिंग | 1 | 20.4709 | 81.6931 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 82 | Farm Pond | झामुराम मरकाम / पदुमसिंग | 1 |  |  | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 83 | Farm Pond | अजय कुमार शोरी | 1 | 20.4743 | 81.7 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 84 | Farm Pond | धनेश मंडावी | 1 | 20.4686 | 81.6941 | 9x9x3 | 0.186 | 0.16 | 96 | 0.17 | 1
| 85 | Farm Pond Desiltation | झाडूराम मंडावी | 1 | 20.4709 | 81.6889 | 75x75x1.5 | 1.742 | 1.58 | 908 | 1.06 | 1
| 86 | Farm Pond Desiltation | बुधराम सलाम | 1 | 20.4794 | 81.697 | 100x100x1.5 | 3.261 | 2.963 | 1775 | 1.9 | 1
| 87 | Farm Pond Desiltation | इंद्रकुमार नेताम | 1 | 20.4721 | 81.6959 | 50x50x1.5 | 0.661 | 0.595 | 356 | 0.48 | 1
| 88 | Farm Pond Desiltation | रामदयाल नेताम | 1 | 20.4771 | 81.7049 | 75x75x1.5 | 1.742 | 1.58 | 908 | 1.06 | 1
| 89 | Farm Pond Desiltation | रमेश नेताम | 1 | 20.4834 | 81.6856 | 75x75x1.5 | 1.742 | 1.58 | 908 | 1.06 | 1
| 90 | Farm Pond Desiltation | गोवर्धन मरकाम / बलिराम | 1 | 20.4798 | 81.6914 | 150x150x1.5 | 7.861 | 7.155 | 4285 | 4.28 | 1
| 91 | Land levelling | रूपसिंग मरकाम | 1 | 20.474 | 81.686 | 0.3 | 0.285 | 0.24225 | 138 | 0.3 | 1
| 92 | Land levelling | मंगली बाई मरकाम | 1 | 20.4734 | 81.6856 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 93 | Land levelling | मंगली बाई मरकाम | 1 | 20.4718 | 81.686 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 94 | Land levelling | घसिया राम मरकाम | 1 | 20.47 | 81.6868 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 95 | Land levelling | झाडूराम मंडावी | 1 | 20.4709 | 81.6889 | 1 | 0.95 | 0.8075 | 460 | 1 | 1
| 96 | Land levelling | धनेश नेताम | 1 | 20.4702 | 81.6935 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 97 | Land levelling | चैतराम नरेटी | 1 | 20.4739 | 81.7036 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 98 | Land levelling | बसंता नेताम | 1 | 20.4733 | 81.6851 | 0.32 | 0.304 | 0.2584 | 147.2 | 0.32 | 1
| 99 | Land levelling | मोहन राम मंडावी | 1 | 20.4651 | 81.6952 | 0.28 | 0.266 | 0.2261 | 128.8 | 0.28 | 1
| 100 | Land levelling | माहरीन बाई नेताम | 1 | 20.4837 | 81.6816 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 101 | Land levelling | टिकेश्वर निषाद | 1 | 20.4803 | 81.7053 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 102 | Land levelling | ठाकुर राम शोरी | 1 | 20.4804 | 81.7065 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 103 | Land levelling | रंजीत शोरी | 1 |  |  | 0.16 | 0.152 | 0.1292 | 73.6 | 0.16 | 1
| 104 | Land levelling | लादूराम | 1 | 20.4796 | 81.7059 | 0.6 | 0.57 | 0.4845 | 276 | 0.6 | 1
| 105 | Land levelling | रजनू / समारू | 1 | 20.473 | 81.6871 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 106 | Land levelling | जोहर नेताम / चरणसिंग | 1 | 20.4703 | 81.6933 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 107 | Land levelling | झामुराम मरकाम / पदुमसिंग | 1 | 20.4703 | 81.6903 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 108 | Land levelling | नोहरसिंग | 1 | 20.4687 | 81.6914 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 109 | Land levelling | बसंता बाई / कवलु राम | 1 | 20.4733 | 81.6851 | 0.3 | 0.285 | 0.24225 | 138 | 0.3 | 1
| 110 | Land levelling | रमेश नेताम | 1 | 20.4834 | 81.6856 | 0.8 | 0.76 | 0.646 | 368 | 0.8 | 1
| 111 | Land levelling | प्रभुराम / जुझारी राम | 1 | 20.4737 | 81.7036 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 112 | Land levelling | घसिया राम मरकाम / कँवल सिंह | 1 | 20.4694 | 81.6868 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 113 | Land levelling | श्यामलाल मरकाम /पदुम सिंग | 1 | 20.4731 | 81.6859 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 114 | Land levelling | कँवल सिंग / धरम सिंग | 1 | 20.4661 | 81.6945 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 115 | Land levelling | गोकुल मरकाम / अमरसिंग | 1 | 20.4761 | 81.6875 | 0.36 | 0.342 | 0.2907 | 165.6 | 0.36 | 1
| 116 | Land levelling | इन्द्र कुमार नेताम / महेश | 1 | 20.4826 | 81.6829 | 0.3 | 0.285 | 0.24225 | 138 | 0.3 | 1
| 117 | Land levelling | पूरन नेताम / हरकराम | 1 | 20.4823 | 81.6837 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 118 | Land levelling | अजय कुमार शोरी | 1 | 20.4741 | 81.6999 | 0.3 | 0.285 | 0.24225 | 138 | 0.3 | 1
| 119 | Land levelling | चैत राम मंडावी | 1 | 20.4688 | 81.6947 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 120 | Land levelling | धनेश मंडावी | 1 | 20.4686 | 81.6944 | 0.1 | 0.095 | 0.08075 | 46 | 0.1 | 1
| 121 | Land levelling | पुनीत मरकाम | 1 | 20.4785 | 81.6983 | 0.8 | 0.76 | 0.646 | 368 | 0.8 | 1
| 122 | Farm Bunding | इतवारू कल्लो | 1 | 20.4714 | 81.6917 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 1
| 123 | Farm Bunding | रमेश मरकाम / अमरसिंग | 1 | 20.4834 | 81.6856 | 0.5 | 0.475 | 0.40375 | 230 | 0.5 | 1
| 124 | Farm Bunding | रामदयाल नेताम | 1 | 20.4778 | 81.7042 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 1
| 125 | Farm Bunding | संतलाल सिंग कुंजाम | 1 | 20.4794 | 81.7021 | 1 | 0.95 | 0.8075 | 460 | 1 | 1
| 126 | Plantation | बुधराम सलाम | 1 | 20.4801 | 81.6967 | 0.8 | 2.144 | 0.348 | 200 | 0.8 | 1
| 127 | Plantation | चैतराम नरेटी | 1 | 20.474 | 81.7034 | 0.2 | 0.536 | 0.087 | 50 | 0.2 | 1
| 128 | Plantation | गोकुल मरकाम | 1 | 20.4825 | 81.6868 | 0.4 | 1.072 | 0.174 | 100 | 0.4 | 1
| 129 | Plantation | रमेश नेताम | 1 | 20.478 | 81.7031 | 1.21 | 3.2428 | 0.52635 | 302.5 | 1.21 | 1
| 130 | Plantation | प्रभुराम / जुझारी राम | 1 | 20.473 | 81.7024 | 0.2 | 0.536 | 0.087 | 50 | 0.2 | 1
| 131 | Plantation | सुंदरु राम सलाम | 4 | 20.4799 | 81.6962 | 0.4 | 1.072 | 0.174 | 100 | 0.4 | 1
| 132 | Plantation | संतलाल सिंग कुंजाम |  | 20.4795 | 81.7021 | 0.8 | 2.144 | 0.348 | 200 | 0.8 | 1
| 133 | Dugwell | बुधराम सलाम | 1 | 20.4801 | 81.6968 | 7x7 | 1.5 | 0.525 | 259 | 1 | 1
| 134 | LBS | ब्रिजबती सलाम | 1 | 20.4731 | 81.6873 | L-5m; H-1m | 0.146 | 0.015 | 17 | 0.1 | 1
| 135 | LBS | महारिन बाई नेताम | 1 | 20.4708 | 81.6926 | L-5m; H-1m | 0.146 | 0.015 | 17 | 0.1 | 1
| 136 | Gabion | मिलाऊ राम / चांदू राम सलाम | 1 | 20.4761 | 81.6875 | L-5m; H-1m | 0.51 | 0.143 | 82 | 0.2 | 1
Community Works:
| 137 | LBS | Common Land | 3 | 20.4771 | 81.7313 | L-4m; H-1m | 0.438 | 0.045 | 51 | 0.3 | 1
| 138 | LBS | Common Land | 4 | 20.4763 | 81.7309 | L-4m; H-1m | 0.584 | 0.06 | 68 | 0.4 | 1
| 139 | LBS | Common Land | 4 | 20.4755 | 81.7303 | L-4m; H-1m | 0.584 | 0.08 | 68 | 0.4 | 1
| 140 | Gabion | Common Land | 2 | 20.4693 | 81.7358 | L-6m; H-1m | 1.02 | 0.286 | 164 | 0.4 | 1
| 141 | Check Dam | Common Land | 1 | 20.4737 | 81.7318 | L-50m, H-3m | 18.89 | 3.26 | 1853 | 15 | 15
| 142 | LBS | Common Land | 4 | 20.4671 | 81.686 | L-4m; H-1m | 0.584 | 0.06 | 68 | 0.4 | 1
| 143 | LBS | Common Land | 4 | 20.4687 | 81.6877 | L-4m; H-1m | 0.584 | 0.06 | 68 | 0.4 | 1
| 144 | Gabion | Common Land | 2 | 20.4653 | 81.4653 | L-6m; H-1m | 0.584 | 0.08 | 68 | 0.4 | 1
Total |  |  |  | 162 |  |  |  | 188.0898 | 140.7795 | 82956.7 | 124.1028 | 158

## MGNREGA Status
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Dhaurabhata
I Job Card
Total No. of JobCards issued | 280
Total No. of Workers | 712
Total No. of Active Job Cards | 249
Total No. of Active Workers | 528
(i)SC worker against active workers[%] | 0.76
(ii)ST worker against active workers[%] | 96.21
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 6431 | 18290 | 14489 | 10154 | 3935
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 1.54 | 1.12 | 1.39 | 1.75 | 0.3
ST persondays % as of total persondays | 95.52 | 96.91 | 98.16 | 95 | 97.69
Women Persondays out of Total (%) | 37.68 | 43.23 | 43.7 | 41.46 | 40.99
Average days of employment provided per Household | 31.22 | 91 | 85.23 | 67.69 | 26.77
Average Wage rate per day per person(Rs.) | 190 | 173.21 | 174 | 172 | 166.8
Total No of HHs completed 100 Days of Wage Employment | 0 | 104 | 77 | 37 | 2
Total Households Worked | 206 | 201 | 170 | 150 | 147
Total Individuals Worked | 332 | 393 | 316 | 284 | 277
Differently abled persons worked | 0 | 0 | 0 | 4 | 1
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 35 | 47 | 54 | 53 | 99
Number of Ongoing Works | 26 | 34 | 17 | 25 | 41
Number of Completed Works | 9 | 13 | 37 | 28 | 58
% of NRM Expenditure(Public + Individual) | 91.77 | 96.6 | 91.15 | 53.69 | 19.72
% of Category B Works | 91.43 | 95.74 | 100 | 75.47 | 71.72
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 16.03 | 31.9 | 25.61 | 16.18 | 21.09
Wages(Rs. In Lakhs) | 14.46 | 30.5 | 24.57 | 14.78 | 6.79
Material and skilled Wages(Rs. In Lakhs) | 1.42 | 0.84 | 0.59 | 1.19 | 13.9
Material(%) | 8.95 | 2.69 | 2.35 | 7.46 | 67.2
Total Adm Expenditure (Rs. in Lakhs.) | 0.15 | 0.55 | 0.45 | 0.21 | 0.4
Admin Exp(%) | 0.94 | 1.72 | 1.75 | 1.3 | 1.9
Average Cost Per Day Per Person(In Rs.) | 195.27 | 180.65 | 181.08 | 260.68 | 337.89
% of Total Expenditure through EFMS | 99.94 | 99.95 | 100 | 99.83 | 100
% payments gererated within 15 days | 100 | 94.22 | 95.35 | 98.61 | 50.1