## e DPR
e DPR of Nawdiha GP, Block Kusami, Dist Balrampur Chhattisgarh
A |  | Back ground profile
Micro Watershed code
|  | District | Balrampur Ra.Ganj.
|  | Block | Kusami
|  | Gram Panchayat | Nawadiha
|  | Villages Covered | Nawadiha
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) | 453.89
|  | Rainfall (mm) | 751.91
|  | Soil type | Sandy Loam
|  | Average Slope | 4 to 9 %
|  | Details of Tributaries | Shahitongri Nala, | 3000 m long | Flows till Feb
|  |  | Chelhachuwa Nala | 2000 m long | Flows till Feb
|  |  | Badnijhariya Nala | 2000 m long | Flows till jan
C |  | DEMOGRAPHIC PROFILE
|  | Total Population | 843
|  | Total HouseHolds | 179
|  | ST Population | 617
|  | SC Population | 131
D |  | MGNREGA Status
|  | NREGA Job card holders | 171
|  | Person days per year (average of last 3 years) | 8768
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 64
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 16.14
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 98.28
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) | 398.03
|  | Multi cropped (Ha) | 106.9
|  | Current fallow(Ha) | 0
|  | Forest /Plantation (Ha) | 187.36
|  | Waste land (Ha) | 0
|  | Impounded Waterbody (Ha) | 15.82
|  | Others (Ha) | 17.96
F |  | LAND CLASSIFICATION
|  | Forest (Ha) | 157.22
|  | Upland (Ha) | 89.58
|  | Medium land (Ha) | 103.96
|  | Low Land (Ha) | 98.91
|  | River Stream Length (m) | 4.22
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds | 12 Nos | 20.874 Ha-m
|  | Borewells | 4 Nos
|  | Open wells | 19 Nos
H |  | Livelihood profile
|  | Agriculture | 84%
|  | Off Farm Activities | 3%
|  | Wages, labour | 8%
|  | Business | 2%
|  | Service/ job | 3%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) | 36.75 | Considering 50% Water requirement will be met by Rainfall
|  | Total Water Available (Ham) | 20.874
|  | Water Resource to be created (Ham) | 15.876
|  | Water Resourse Planned ( Ha M) | 15.338
|  | % of Water requirment fulfilled though MWS | 99%
J |  | EXPECTED OUTCOME
|  | Increase in Cropping area (in Ha) | 109.88
|  | Increase in Irrigated area (in Ha) | 59.14
|  | Income Enhancement (INR 50000 per annum as additional income) | 67HH
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Benificiary | No. | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area | Targeted HH
Individual Works:
1 | Mcjh fuekZ.k | Hkxorn;ky@f’koukFk | 1 | 30x30x3 | 3 | 2.92 | 1537
2 | dqvkW fuekZ.k | Hkxorn;ky@f’koukFk | 1 | 4.8x9 | 3.6 | 0.6 | 345
3 | leryhdj.k | Hkxorn;ky@f’koukFk | 1 | 40x100 | 0.45 | 0.42 | 241
4 | ukMsi | Hkxorn;ky@f’koukFk | 1 | Standard | 0.31 | 0.04 | 23
5 | xk; 'ksM | Hkxorn;ky@f’koukFk | 1 | Stadard | 0.415 | 0.035 | 20
6 | Mcjh fuekZ.k | jkelk;@eaxjk | 1 | 30x30x3 | 3 | 2.92 | 1537
7 | ukMsi | jkelk;@ eaxjk | 1 | Standard | 0.31 | 0.04 | 23
8 | xk; 'ksM | jkelk;@ eaxjk | 1 | Stadard | 0.415 | 0.035 | 20
9 | leryhdj.k | jkelk;@ eaxjk | 1 | 40x100 | 0.45 | 0.42 | 241
10 | dqvkW fuekZ.k | jksiuk@la?kjk | 1 | 4.8x9 | 3.6 | 0.6 | 345
11 | xk; 'ksM | jksiuk@la?kjk | 1 | Stadard | 0.415 | 0.035 | 20
12 | leryhdj.k | jksiuk@la?kjk | 1 | 40x100 | 0.45 | 0.42 | 241
13 | lqvj 'ksM | jksiuk@la?kjk | 1 | Standard | 0.415 | 0.035 | 20
14 | ukMsi | jksiuk@la?kjk | 1 | Standard | 0.31 | 0.04 | 23
15 | Mcjh fuekZ.k | lq[ku@cU/kw | 1 | 30x30x3 | 3 | 2.92 | 1537
16 | leryhdj.k | lq[ku@cU/kw | 1 | 40x100 | 0.45 | 0.42 | 241
17 | lqvj 'ksM | lq[ku@cU/kw | 1 | Standard | 0.415 | 0.035 | 20
18 | ukMsi | lq[ku@cU/kw | 1 | Standard | 0.31 | 0.04 | 23
19 | leryhdj.k | [kon@:bZyk | 1 | 40x100 | 0.45 | 0.42 | 241
20 | lqvj 'ksM | [kon@:bZyk | 1 | Standard | 0.415 | 0.035 | 20
21 | ukMsi | [kon@:bZyk | 1 | Standard | 0.31 | 0.04 | 23
22 | leryhdj.k | tksjxks@jlu | 1 | 40x100 | 0.45 | 0.42 | 241
23 | lqvj 'ksM | tksjxks@jlu | 1 | Standard | 0.415 | 0.035 | 20
24 | ukMsi | tksjxks@jlu | 1 | Standard | 0.31 | 0.04 | 23
25 | dqvkW fuekZ.k | tksjxks@jlu | 1 | 4.8x9 | 3.6 | 0.6 | 345
26 | Mcjh fuekZ.k | tksjxks@jlu | 1 | 30x30x3 | 3 | 2.92 | 1537
27 | Mcjh fuekZ.k | egkfcj@f’koukFk | 1 | 30x30x3 | 3 | 2.92 | 1537
28 | xk; 'ksM | egkfcj@f’koukFk | 1 | Stadard | 0.415 | 0.035 | 20
29 | ukMsi | egkfcj@f’koukFk | 1 | Standard | 0.31 | 0.04 | 23
30 | dqvkW fuekZ.k | fcjs'k@fcQbZ;k | 1 | 4.8x9 | 3.6 | 0.6 | 345
31 | xk; 'ksM | fcjs'k@fcQbZ;k | 1 | Stadard | 0.415 | 0.035 | 20
32 | ukMsi | fcjs'k@fcQbZ;k | 1 | Standard | 0.31 | 0.04 | 23
33 | leryhdj.k | fcjs'k@fcQbZ;k | 1 | 40x100 | 0.45 | 0.42 | 241
34 | leryhdj.k | Mqou@ukulk; | 1 | 40x100 | 0.45 | 0.42 | 241
35 | xk; 'ksM | Mqou@ukulk; | 1 | Stadard | 0.415 | 0.035 | 20
36 | ukMsi | Mqou@ukulk; | 1 | Standard | 0.31 | 0.04 | 23
37 | es<canh | ljLorh@jkek/kkj | 1 | 40x100 | 0.45 | 0.42 | 241
38 | xk; 'ksM | ljLorh@jkek/kkj | 1 | Stadard | 0.415 | 0.035 | 20
39 | ukMsi | ljLorh@jkek/kkj | 1 | Standard | 0.31 | 0.04 | 23
40 | es<canh | Hkq[kylk;@v[knw | 1 | 40x100 | 0.45 | 0.42 | 241
41 | xk; 'ksM | Hkq[kylk;@v[knw | 1 | Stadard | 0.415 | 0.035 | 20
42 | ukMsi | Hkq[kylk;@v[knw | 1 | Standard | 0.31 | 0.04 | 23
43 | es<canh | 'kfupj@fpdok | 1 | 40x100 | 0.45 | 0.42 | 241
44 | xk; 'ksM | 'kfupj@fpdok | 1 | Stadard | 0.415 | 0.035 | 20
45 | ukMsi | 'kfupj@fpdok | 1 | Standard | 0.31 | 0.04 | 23
46 | Mcjh fuekZ.k | jke/ku@pjdq | 1 | 30x30x3 | 3 | 2.92 | 1537
47 | leryhdj.k | jke/ku@pjdq | 1 | 40x100 | 0.45 | 0.42 | 241
48 | xk; 'ksM | jke/ku@pjdq | 1 | Stadard | 0.415 | 0.035 | 20
49 | ukMsi | jke/ku@pjdq | 1 | Standard | 0.31 | 0.04 | 23
50 | leryhdj.k | /kje@nsoukFk | 1 | 40x100 | 0.45 | 0.42 | 241
51 | xk; 'ksM | /kje@nsoukFk | 1 | Stadard | 0.415 | 0.035 | 20
52 | ukMsi | /kje@nsoukFk | 1 | Standard | 0.31 | 0.04 | 23
53 | lqvj 'ksM | /kje@nsoukFk | 1 | Standard | 0.415 | 0.035 | 20
54 | leryhdj.k | eax:@tr: | 1 | 40x100 | 0.45 | 0.42 | 241
55 | xk; 'ksM | eax:@tr: | 1 | Stadard | 0.415 | 0.035 | 20
56 | ukMsi | eax:@tr: | 1 | Standard | 0.31 | 0.04 | 23
57 | Mcjh fuekZ.k | Hkq[kk@tr: | 1 | 30x30x3 | 3 | 2.92 | 1537
58 | leryhdj.k | Hkq[kk@tr: | 1 | 40x100 | 0.45 | 0.42 | 241
59 | xk; 'ksM | Hkq[kk@tr: | 1 | Stadard | 0.415 | 0.035 | 20
60 | ukMsi | Hkq[kk@tr: | 1 | Standard | 0.31 | 0.04 | 23
61 | Mcjh fuekZ.k | jkts’k@:ilk; | 1 | 30x30x3 | 3 | 2.92 | 1537
62 | Mcjh fuekZ.k | feJk@jktk | 1 | 30x30x3 | 3 | 2.92 | 1537
63 | Mcjh fuekZ.k | dkSys’oj@e?ks | 1 | 30x30x3 | 3 | 2.92 | 1537
64 | Mcjh fuekZ.k | ukjsUnzj@Hk.Mkjh | 1 | 30x30x3 | 3 | 2.92 | 1537
65 | Mcjh fuekZ.k | [koM@:bZyh | 1 | 30x30x3 | 3 | 2.92 | 1537
66 | xk; 'ksM | jkts’k@:ilk; | 1 | Stadard | 0.415 | 0.035 | 20
67 | ukMsi | jkts’k@:ilk; | 1 | Standard | 0.31 | 0.04 | 23
68 | xk; 'ksM | feJk@jktk | 1 | Stadard | 0.415 | 0.035 | 20
69 | ukMsi | feJk@jktk | 1 | Standard | 0.31 | 0.04 | 23
70 | xk; 'ksM | dkSys’oj@e?ks | 1 | Stadard | 0.415 | 0.035 | 20
71 | ukMsi | dkSys’oj@e?ks | 1 | Standard | 0.31 | 0.04 | 23
72 | xk; 'ksM | ukjsUnzj@Hk.Mkjh | 1 | Stadard | 0.415 | 0.035 | 20
73 | ukMsi | ukjsUnzj@Hk.Mkjh | 1 | Standard | 0.31 | 0.04 | 23
74 | xk; 'ksM | [koM@:bZyh | 1 | Stadard | 0.415 | 0.035 | 20
75 | ukMsi | [koM@:bZyh | 1 | Standard | 0.31 | 0.04 | 23
Community Works:
77 | cksYMj psd | eMh;k Mks<k ukyk 1 | 10 Nag | 8.7x5.7x1.2 | 1.55 | 0.93 | 540
78 | xsfc;u fuekZ.k | eMh;k Mks<k ukyk 1 | 10 Nag | 10x4.6x1 | 11.4 | 2.4 | 1370
79 | LVkWi MSe | eMh;k Mks<k ukyk 1 | 1 Nag | 20x5x2.30 | 18.08 | 3.07 | 1745
80 | cksYMj psd | eMh;k Mks<k ukyk 1 | 5 Nag | 9x5.7x1.2 | 0.545 | 0.27 | 155
81 | xsfc;u fuekZ.k | eMh;k Mks<k ukyk 1 | 3 Nag | 10x4.6x1 | 2.16 | 0.42 | 240
82 | cksYMj psd | eMh;k Mks<k ukyk 1 | 5 Nag | 9x5.7x1.2 | 0.545 | 0.27 | 155
83 | xsfc;u fuekZ.k | eMh;k Mks<k ukyk 1 | 3 Nag | 10x4.6x1 | 3.42 | 0.72 | 411
84 | LVkWi MSe | eMh;k Mks<k ukyk 2 | 1 Nag | 20x5x2.30 | 18.08 | 3.07 | 1745
85 | cksYMj psd | eMh;k Mks<k ukyk 2 | 5 Nag | 10x5.7x1.2 | 0.545 | 0.27 | 155
86 | cksYMj psd | eMh;k Mks<k ukyk 2 | 5 Nag | 8x5.7x1.2 | 0.545 | 0.27 | 155
87 | xyhIyx | eMh;k Mks<k ukyk 2 | 1 Nag | 10x5x2 | 0.33 | 0.297 | 169
88 | cksYMj psd | eMh;k Mks<k ukyk 2 | 6 Nag | 7x5.7x1.2 | 0.86 | 0.86 | 489
89 | xyhIyx | eMh;k Mks<k ukyk 2 | 10 Nag | 5x3x1 | 0.53 | 0.47 | 272
90 | xyhIyx | eMh;k Mks<k ukyk 2 | 10 Nag | 5x3x1 | 0.53 | 0.47 | 272
91 | cksYMj psd | eMh;k Mks<k ukyk 2 | 10 Nag | 7x5.7x1.2 | 1.56 | 0.79 | 452
92 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 4 Nag | 12x4.6x1 | 11.4 | 2.4 | 1370
93 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 5 Nag | 12x4.6x1 | 12.3 | 3.3 | 1875
94 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 5 Nag | 12x4.6x1 | 12.3 | 3.3 | 1875
95 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 4 Nag | 12x4.6x1 | 11.4 | 2.4 | 1370
96 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 5 Nag | 12x4.6x1 | 12.3 | 3.3 | 1875
97 | xsfc;u fuekZ.k | xksUnyh dksuk ukyk | 3 Nag | 10x4.6x1 | 3.42 | 0.72 | 411
98 | LVkWi MSe | xksUnyh dksuk ukyk | 1 Nag | 20x5x2.30 | 18.08 | 3.07 | 1745
99 | xsfc;u fuekZ.k | xksUnyh dksuk ukyk | 5 Nag | 12x4.6x1 | 12.3 | 3.3 | 1875
100 | xsfc;u fuekZ.k | xksUnyh dksuk ukyk | 10 Nag | 10x4.6x1 | 11.4 | 2.4 | 1370
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120

## NREGA Data
State : Chattisgarh District : Balrampur Block : Kusami Panchayat : Nawadiha | [5 empty] | As on 10-06-2020
I Job Card
Total No. of JobCards issued | 171
Total No. of Workers | 378
Total No. of Active Job Cards | 159
Total No. of Active Workers | 340
(i)SC worker against active workers[%] | 5.88
(ii)ST worker against active workers[%] | 75.29
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9198 | 10469 | 6639 | 7835 | 8362
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 4.38 | 2.49 | 4.43 | 5 | 4.97
ST persondays % as of total persondays | 71.09 | 82.35 | 86.4 | 85.31 | 88.89
Women Persondays out of Total (%) | 47.48 | 47.4 | 44.84 | 46.66 | 45
Average days of employment provided per Household | 73 | 91.03 | 65.73 | 68.73 | 63.83
Average Wage rate per day per person(Rs.) | 190 | 176 | 173.97 | 172 | 165.62
Total No of HHs completed 100 Days of Wage Employment | 46 | 54 | 26 | 33 | 30
Total Households Worked | 126 | 115 | 101 | 114 | 131
Total Individuals Worked | 268 | 243 | 208 | 222 | 283
Differently abled persons worked | 0 | 0 | 0 | 0 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 11 | 9 | 28 | 32 | 45
Number of Ongoing Works | 5 | 8 | 5 | 22 | 19
Number of Completed Works | 6 | 1 | 23 | 10 | 26
% of NRM Expenditure(Public + Individual) | 100 | 100 | 94.84 | 61.72 | 73.67
% of Category B Works | 100 | 100 | 82.14 | 65.62 | 22.22
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 15.1 | 17.51 | 15.81 | 17.76 | 24.71
Wages(Rs. In Lakhs) | 14.74 | 17.51 | 10.62 | 14.32 | 19.19
Material and skilled Wages(Rs. In Lakhs) | 0.36 | 0 | 5.19 | 2.89 | 5.09
Material(%) | 2.39 | 0 | 32.84 | 16.77 | 20.96
Total Adm Expenditure (Rs. in Lakhs.) | 0 | 0 | 0 | 0.56 | 0.43
Admin Exp(%) | 0 | 0 | 0 | 3.12 | 1.74
Average Cost Per Day Per Person(In Rs.) | 202.6 | 176 | 185.11 | 179.08 | 220.88
% of Total Expenditure through EFMS | 100 | 100 | 100 | 100 | 99.83
% payments gererated within 15 days | 95.1 | 86.33 | 94.46 | 92.13 | 21.18

## Calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | N | Catcthment Area In Ha | Command Area In Ha | Area Treated
1 | dqvkW fuekZ.k | Hkxorn;ky@f’koukFk |  | 7 | 7 |  |  |  | 5.39 | 5.39
2 | dqvkW fuekZ.k | jksiuk@la?kjk |  | 7 | 7 |  |  |  | 5.39 | 5.39
3 | dqvkW fuekZ.k | tksjxks@jlu |  | 7 | 7 |  |  |  | 5.39 | 5.39
4 | dqvkW fuekZ.k | fcjs'k@fcQbZ;k |  | 7 | 7 |  |  |  | 5.39 | 5.39
5 | es<canh | ljLorh@jkek/kkj |  | 40 | 100 |  |  |  | 0.4 | 0.4
6 | es<canh | Hkq[kylk;@v[knw |  | 40 | 100 |  |  |  | 0.4 | 0.4
7 | es<canh | 'kfupj@fpdok |  | 40 | 100 |  |  |  | 0.4 | 0.4
8 | leryhdj.k | Hkxorn;ky@f’koukFk |  | 40 | 100 |  |  |  | 0.4 | 0.4
9 | leryhdj.k | jkelk;@ eaxjk |  | 40 | 100 |  |  |  | 0.4 | 0.4
10 | leryhdj.k | jksiuk@la?kjk |  | 40 | 100 |  |  |  | 0.4 | 0.4
11 | leryhdj.k | lq[ku@cU/kw |  | 40 | 100 |  |  |  | 0.4 | 0.4
12 | leryhdj.k | [kon@:bZyk |  | 40 | 100 |  |  |  | 0.4 | 0.4
13 | leryhdj.k | tksjxks@jlu |  | 40 | 100 |  |  |  | 0.4 | 0.4
14 | leryhdj.k | fcjs'k@fcQbZ;k |  | 40 | 100 |  |  |  | 0.4 | 0.4
15 | leryhdj.k | Mqou@ukulk; |  | 40 | 100 |  |  |  | 0.4 | 0.4
16 | leryhdj.k | jke/ku@pjdq |  | 40 | 100 |  |  |  | 0.4 | 0.4
17 | leryhdj.k | /kje@nsoukFk |  | 40 | 100 |  |  |  | 0.4 | 0.4
18 | leryhdj.k | eax:@tr: |  | 40 | 100 |  |  |  | 0.4 | 0.4
19 | leryhdj.k | Hkq[kk@tr: |  | 40 | 100 |  |  |  | 0.4 | 0.4
20 | Mcjh fuekZ.k | Hkxorn;ky@f’koukFk |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
21 | Mcjh fuekZ.k | jkelk;@eaxjk |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
22 | Mcjh fuekZ.k | lq[ku@cU/kw |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
23 | Mcjh fuekZ.k | tksjxks@jlu |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
24 | Mcjh fuekZ.k | egkfcj@f’koukFk |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
25 | Mcjh fuekZ.k | jke/ku@pjdq |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
26 | Mcjh fuekZ.k | Hkq[kk@tr: |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
27 | Mcjh fuekZ.k | jkts’k@:ilk; |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
28 | Mcjh fuekZ.k | feJk@jktk |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
29 | Mcjh fuekZ.k | dkSys’oj@e?ks |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
30 | Mcjh fuekZ.k | ukjsUnzj@Hk.Mkjh |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
31 | Mcjh fuekZ.k | [koM@:bZyh |  | 30 | 30 | 3 |  | 0.75 | 1.12 | 0.75
32 | cksYMj psd | eMh;k Mks<k ukyk 1 | 10 Nag | 8.7 | 5.7 | 1.2 |  |  |  | 1
33 | xsfc;u fuekZ.k | eMh;k Mks<k ukyk 1 | 10 Nag | 10 | 4.6 | 1 |  |  |  | 15
34 | LVkWi MSe | eMh;k Mks<k ukyk 1 | 1 Nag | 20 | 5 | 2.3 |  |  | 10.5 | 10.5
35 | cksYMj psd | eMh;k Mks<k ukyk 1 | 5 Nag | 9 | 5.7 | 1.2 |  |  |  | 1
36 | xsfc;u fuekZ.k | eMh;k Mks<k ukyk 1 | 3 Nag | 10 | 4.6 | 1 |  |  |  | 15
37 | cksYMj psd | eMh;k Mks<k ukyk 1 | 5 Nag | 9 | 5.7 | 1.2 |  |  |  | 1
38 | xsfc;u fuekZ.k | eMh;k Mks<k ukyk 1 | 3 Nag | 10 | 4.6 | 1 |  |  |  | 15
39 | LVkWi MSe | eMh;k Mks<k ukyk 2 | 1 Nag | 20 | 5 | 2.3 |  |  | 10.5 | 10.5
40 | cksYMj psd | eMh;k Mks<k ukyk 2 | 5 Nag | 10 | 5.7 | 1.2 |  |  |  | 1
41 | cksYMj psd | eMh;k Mks<k ukyk 2 | 5 Nag | 8 | 5.7 | 1.2 |  |  |  | 1
42 | xyhIyx | eMh;k Mks<k ukyk 2 | 1 Nag | 10 | 5 | 2 |  |  |  | 0.6
43 | cksYMj psd | eMh;k Mks<k ukyk 2 | 6 Nag | 7 | 5.7 | 1.2 |  |  |  | 1
44 | xyhIyx | eMh;k Mks<k ukyk 2 | 10 Nag | 5 | 3 | 1 |  |  |  | 0.35
45 | xyhIyx | eMh;k Mks<k ukyk 2 | 10 Nag | 5 | 3 | 1 |  |  |  | 0.35
46 | cksYMj psd | eMh;k Mks<k ukyk 2 | 10 Nag | 7 | 5.7 | 1.2 |  |  |  | 1
47 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 4 Nag | 12 | 4.6 | 1 |  |  |  | 15
48 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 5 Nag | 12 | 4.6 | 1 |  |  |  | 15
49 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 5 Nag | 12 | 4.6 | 1 |  |  |  | 15
50 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 4 Nag | 12 | 4.6 | 1 |  |  |  | 15
51 | xsfc;u fuekZ.k | cksnh dksuk ukyk | 5 Nag | 12 | 4.6 | 1 |  |  |  | 15
52 | xsfc;u fuekZ.k | xksUnyh dksuk ukyk | 3 Nag | 10 | 4.6 | 1 |  |  |  | 15
53 | LVkWi MSe | xksUnyh dksuk ukyk | 1 Nag | 20 | 5 | 2.3 |  |  | 10.5 | 10.5
54 | xsfc;u fuekZ.k | xksUnyh dksuk ukyk | 5 Nag | 12 | 4.6 | 1 |  |  |  | 15
55 | xsfc;u fuekZ.k | xksUnyh dksuk ukyk | 10 Nag | 10 | 4.6 | 1 |  |  |  | 15
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90