## e DPR
e DPR of Semra GP, Block Kusami , Dist Balrampur-ramanujganj Chhattisgarh
A |  | Back ground profile
Micro Watershed code
|  | District | Balrampur
|  | Block | Kusami
|  | Gram Panchayat | Semra
|  | Villages Covered | Semra
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) | 928.41
|  | Rainfall (mm) | 751.91
|  | Soil type | Sandy Loam
|  | Average Slope | 4%
|  | Details of Tributaries | Jhakmakh Nala
Dumar Nala
C |  | DEMOGRAPHIC PROFILE
|  | Total Population | 1142
|  | Total HouseHolds | 249
|  | ST Population | 981
|  | SC Population | 20
D |  | MGNREGA Status
|  | NREGA Job card holders | 294
|  | Person days per year (average of last 3 years) | 6399
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 15
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 12.81
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 80.23
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) | 310.41
|  | Multi cropped (Ha) | 103.5
|  | Current fallow(Ha) | 122
|  | Forest /Plantation (Ha) | 155
|  | Waste land (Ha) | 25.22
|  | Impounded Waterbody (Ha) | 35
|  | Others (Ha) | 42
F |  | LAND CLASSIFICATION
|  | Forest (Ha) | 350
|  | Upland (Ha) | 100
|  | Medium land (Ha) | 150
|  | Low Land (Ha) | 328.41
|  | River Stream Length (m) | 5000
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds | 13
|  | Borewells | 12
|  | Open wells | 45
H |  | Livelihood profile
|  | Agriculture | 60%
|  | Off Farm Activities | 0%
|  | Wages, labour | 33%
|  | Business | 2%
|  | Service/ job | 5%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) | 55.12 | Considering 50% Water requirement will be met by Rainfall
|  | Total Water Available (Ham) | 28.462
|  | Water Resource to be created (Ham) | 26.658
|  | Water Resourse Planned ( Ha M) | 27.85
|  | % of Water requirment fulfilled though MWS | 104.5%
J |  | EXPECTED OUTCOME
Increase in Cropping area (in Ha)
Increase in Irrigated area (in Ha)
Income Enhancement (INR 50000 per annum as additional income)
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Benificiary | No. | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area | Targeted HH
Individual Works:
1 | कुआँ निर्माण | धीरजन /घासीराम | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
2 | मेढबंदी | धीरजन /घासीराम | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
3 | गाय शेड | धीरजन /घासीराम | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
4 | वर्मी कम्पोस्ट | धीरजन /घासीराम | 1 | Standard | 1.5 | 0.525 | 259 |  | 1
5 | कुआँ निर्माण | रिझन /घासीराम | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
6 | मेढबंदी | रिझन /घासीराम | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
7 | गाय शेड | रिझन /घासीराम | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
8 | वर्मी कम्पोस्ट | रिझन /घासीराम | 1 | Standard | 1.5 | 0.525 | 259 |  | 1
9 | कुआँ निर्माण | राजकुमार /मोहन | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
10 | मेढबंदी | राजकुमार /मोहन | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
11 | गाय शेड | राजकुमार /मोहन | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
12 | कुआँ निर्माण | गंदुर /बिकुल | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
13 | मेढबंदी | गंदुर /बिकुल | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
14 | गाय शेड | गंदुर /बिकुल | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
15 | कुआँ निर्माण | मांझी /बीतन | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
16 | मुर्गी शेड | मांझी /बीतन | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
17 | वर्मी कम्पोस्ट | मांझी /बीतन | 1 | Standard | 1.5 | 0.525 | 259 |  | 1
18 | कुआँ निर्माण | हरीनारायण /बीतन | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
19 | मुर्गी शेड | हरीनारायण /बीतन | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
20 | वर्मी कम्पोस्ट | हरीनारायण /बीतन | 1 | Standard | 1.5 | 0.525 | 259 |  | 1
21 | डबरी | मनसुराम /लोंगसाय राम | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
22 | कुआँ निर्माण | मनसुराम /लोंगसाय राम | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
23 | गाय शेड | मनसुराम /लोंगसाय राम | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
24 | समतली करण | मनसुराम /लोंगसाय राम | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
25 | कुआँ निर्माण | लल्लु पैंकरा /लेदु राम | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
26 | गाय शेड | लल्लु पैंकरा /लेदु राम | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
27 | मेढबंदी | लल्लु पैंकरा /लेदु राम | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
28 | कुआँ निर्माण | संतराम /रंजन | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
29 | गाय शेड | संतराम /रंजन | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
30 | मुर्गी शेड | बंशीधर /ब्रम्हेश्वर धर सिंह | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
31 | डबरी | बंशीधर /ब्रम्हेश्वर धर सिंह | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
32 | समतली करण | बंशीधर /ब्रम्हेश्वर धर सिंह | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
33 | कुआँ निर्माण | नामदेव /पवन साय | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
34 | समतली करण | नामदेव /पवन साय | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
35 | मुर्गी शेड | नामदेव /पवन साय | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
36 | मुर्गी शेड | अमरसाय पैंकरा /बिजन राम | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
37 | डबरी | चन्द्रदेव /प्रभुराम | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
38 | समतली करण | चन्द्रदेव /प्रभुराम | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
39 | मुर्गी शेड | अरविंद /मोहन | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
40 | कुआँ निर्माण | जगेश /अमिन | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
41 | मुर्गी शेड | जगेश /अमिन | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
42 | कुआँ निर्माण | ब्रम्हदेव /बागेश्वर | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
43 | गाय शेड | ब्रम्हदेव /बागेश्वर | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
44 | कुआँ निर्माण | हीरू /देशियर | 1 | 4.8x9m | 3.6 | 0.6 | 345 |  | 1
45 | मुर्गी शेड | हीरू /देशियर | 1 | Standard | 0.42 | 0.063 | 36 |  | 1
46 | समतली करण | हीरू /देशियर | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
47 | गाय शेड | मधेश्वर राम /बिजन राम | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
48 | डबरी | मधेश्वर राम /बिजन राम | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
49 | गाय शेड | राजेश /विष्णु | 1 | Standard | 0.38 | 0.035 | 20 |  | 1
50 | डबरी | राजेश /विष्णु | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
51 | समतली करण | लोकनाथ | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
52 | डबरी | अवधेश /श्रीनाथ | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
53 | डबरी | अशोक /श्रीनाथ | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
54 | डबरी | मदन /चोएट | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
55 | डबरी | जंगलु /रतन | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
56 | समतली करण | किशुन /रामदेव | 1 | 20x100 m | 0.225 | 0.195 | 112 |  | 1
57 | डबरी | चम्पाराम /दलसाय | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
58 | डबरी | बाबुनाथ /अमिनसाय | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
59 | डबरी | गणेश /बाम्हन | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
60 | डबरी | करमु /धुरटू | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
61 | डबरी | महल | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
62 | डबरी | बिहारी /पानसाय | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
63 | डबरी | तेजनाथ /ठेपाराम | 1 | 30x30x3 | 2.51 | 2.43 | 1381 |  | 1
Community Work
64 | स्टॉप डैम | झकमख नाला | 1 | 20X1.5X2 | 19.65 | 3.33 | 1892 |  | 10
65 | स्टॉप डैम | झकमख नाला | 1 | 20X1.5X2 | 19.65 | 3.33 | 1892 |  | 10
66 | गेबियन निर्माण | झकमख नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
67 | गेबियन निर्माण | झकमख नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
68 | गेबियन निर्माण | झकमख नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
69 | गेबियन निर्माण | झकमख नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
70 | गेबियन निर्माण | झकमख नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
71 | गेबियन निर्माण | झकमख नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
72 | गेबियन निर्माण | डूमर नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
73 | गेबियन निर्माण | डूमर नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
74 | गेबियन निर्माण | डूमर नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
75 | गेबियन निर्माण | डूमर नाला | 1 | 15X6X1.5 | 1.245 | 0.24 | 137 |  | 2
76 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
77 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
78 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
79 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
80 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
81 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
82 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
83 | बोल्डर चेक निर्माण | झकमख नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
84 | बोल्डर चेक निर्माण | डूमर नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
85 | बोल्डर चेक निर्माण | डूमर नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
86 | बोल्डर चेक निर्माण | डूमर नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
87 | बोल्डर चेक निर्माण | डूमर नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
88 | बोल्डर चेक निर्माण | डूमर नाला | 1 | 10x6x1.5 | 0.155 | 0.093 | 54 |  | _
89 | मिटटी बांध | झकमख नाला | 1 | 25X10X3 | 15.2 | 9.12 | 5182 |  | 10

## NREGA Data
State : CHHATTISGARH District : BALRAMPUR Block : KUSAMI Panchayat : Semra | [5 empty] | As on 22-02-2021
I Job Card
Total No. of JobCards issued | 294
Total No. of Workers | 1010
Total No. of Active Job Cards | 271
Total No. of Active Workers | 813
(i)SC worker against active workers[%] | 6.64
(ii)ST worker against active workers[%] | 57.56
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9483 | 7973 | 1743 | 3385 | 6936
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 3.64 | 0.01 | 0 | 0 | 0
ST persondays % as of total persondays | 67.35 | 86.76 | 85.83 | 80.71 | 84.18
Women Persondays out of Total (%) | 51.83 | 54.89 | 44.75 | 45.29 | 46.01
Average days of employment provided per Household | 40.18 | 48.03 | 22.35 | 43.4 | 45.63
Average Wage rate per day per person(Rs.) | 190 | 176 | 174 | 172 | 160.45
Total No of HHs completed 100 Days of Wage Employment | 18 | 24 | 1 | 4 | 8
Total Households Worked | 236 | 166 | 78 | 78 | 152
Total Individuals Worked | 412 | 295 | 128 | 131 | 294
Differently abled persons worked | 3 | 3 | 0 | 0 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 15 | 18 | 40 | 59 | 75
Number of Ongoing Works | 11 | 10 | 7 | 32 | 57
Number of Completed Works | 4 | 8 | 33 | 27 | 18
% of NRM Expenditure(Public + Individual) | 82.71 | 90.59 | 67.39 | 12.16 | 25.98
% of Category B Works | 73.33 | 88.89 | 87.5 | 83.05 | 64
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 17.56 | 13.65 | 7.23 | 18.66 | 30.13
Wages(Rs. In Lakhs) | 14.08 | 13.27 | 3.77 | 6.86 | 15.95
Material and skilled Wages(Rs. In Lakhs) | 3.47 | 0.38 | 3.46 | 11.12 | 13.75
Material(%) | 19.78 | 2.78 | 47.87 | 61.85 | 46.3
Total Adm Expenditure (Rs. in Lakhs.) | 0 | 0 | 0 | 0.68 | 0.43
Admin Exp(%) | 0 | 0 | 0 | 3.62 | 1.42
Average Cost Per Day Per Person(In Rs.) | 246.11 | 176 | 302.61 | 276.7 | 364.9
% of Total Expenditure through EFMS | 99.97 | 100 | 100 | 100 | 100
% payments gererated within 15 days | 100 | 94.51 | 98.97 | 95.94 | 10.85

## Calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | N | Catcthment Area In Ha | Command Area In Ha | Area Treated
1 | Mcjh | मनसुराम /लोंगसाय राम | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
2 | Mcjh | बंशीधर /ब्रम्हेश्वर धर सिंह | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
3 | Mcjh | चन्द्रदेव /प्रभुराम | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
4 | Mcjh | मधेश्वर राम /बिजन राम | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
5 | Mcjh | राजेश /विष्णु | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
6 | Mcjh | अवधेश /श्रीनाथ | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
7 | Mcjh | अशोक /श्रीनाथ | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
8 | Mcjh | मदन /चोएट | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
9 | Mcjh | जंगलु /रतन | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
10 | Mcjh | चम्पाराम /दलसाय | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
11 | Mcjh | महल | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
12 | Mcjh | बिहारी /पानसाय | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
13 | Mcjh | तेजनाथ /ठेपाराम | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
14 | Mcjh | बाबुनाथ /अमिनसाय | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
15 | Mcjh | गणेश /बाम्हन | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
16 | Mcjh | करमु /धुरटू | 30x30x3 | 30 | 30 | 3 |  | 1.49 | 2.24 | 3.73
17 | leryhdj.k | मनसुराम /लोंगसाय राम | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
18 | leryhdj.k | बंशीधर /ब्रम्हेश्वर धर सिंह | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
19 | leryhdj.k | नामदेव /पवन साय | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
20 | leryhdj.k | चन्द्रदेव /प्रभुराम | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
21 | leryhdj.k | हीरू /देशियर | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
22 | leryhdj.k | लोकनाथ | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
23 | leryhdj.k | किशुन /रामदेव | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
24 | es<canh | धीरजन /घासीराम | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
25 | es<canh | रिझन /घासीराम | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
26 | es<canh | राजकुमार /मोहन | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
27 | es<canh | गंदुर /बिकुल | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
28 | es<canh | लल्लु पैंकरा /लेदु राम | 20x100 m | 20 | 100 |  |  |  | 0.2 | 0.2
29 | dqvkW fuekZ.k | धीरजन /घासीराम | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
30 | dqvkW fuekZ.k | रिझन /घासीराम | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
31 | dqvkW fuekZ.k | राजकुमार /मोहन | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
32 | dqvkW fuekZ.k | गंदुर /बिकुल | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
33 | dqvkW fuekZ.k | मांझी /बीतन | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
34 | dqvkW fuekZ.k | हरीनारायण /बीतन | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
35 | dqvkW fuekZ.k | मनसुराम /लोंगसाय राम | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
36 | dqvkW fuekZ.k | लल्लु पैंकरा /लेदु राम | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
37 | dqvkW fuekZ.k | संतराम /रंजन | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
38 | dqvkW fuekZ.k | नामदेव /पवन साय | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
39 | dqvkW fuekZ.k | जगेश /अमिन | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
40 | dqvkW fuekZ.k | ब्रम्हदेव /बागेश्वर | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
41 | dqvkW fuekZ.k | हीरू /देशियर | 7mX7m | 7 |  | 7 |  |  | 2.15 | 2.15
Community Work
42 | स्टॉप डैम | झकमख नाला | 20X1.5X2 | 20 | 1.5 | 2 |  |  | 8 | 25
43 | स्टॉप डैम | झकमख नाला | 20X1.5X2 | 20 | 1.5 | 2 |  |  | 8 | 25
44 | गेबियन निर्माण | झकमख नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
45 | गेबियन निर्माण | झकमख नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
46 | गेबियन निर्माण | झकमख नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
47 | गेबियन निर्माण | झकमख नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
48 | गेबियन निर्माण | झकमख नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
49 | गेबियन निर्माण | झकमख नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
50 | गेबियन निर्माण | डूमर नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
51 | गेबियन निर्माण | डूमर नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
52 | गेबियन निर्माण | डूमर नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
53 | गेबियन निर्माण | डूमर नाला | 15X6X1.5 | 15 | 6 | 1.5 |  | 3 | 7 | 12
54 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
55 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
56 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
57 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
58 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
59 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
60 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
61 | बोल्डर चेक निर्माण | झकमख नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
62 | बोल्डर चेक निर्माण | डूमर नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
63 | बोल्डर चेक निर्माण | डूमर नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
64 | बोल्डर चेक निर्माण | डूमर नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
65 | बोल्डर चेक निर्माण | डूमर नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
66 | बोल्डर चेक निर्माण | डूमर नाला | 10x6x1.5 | 10 | 6 | 1.5 |  | 1 | 1.5 | 2
67 | मिटटी बांध | झकमख नाला | 25X10X3 | 25 | 10 | 3 |  |  | 8 | 20