## e DPR kurru
B | C | D | E | F | G | H | I | J | K | L | M | N | O
e-DPR of ______Kurru ______GP, Block ___Kharsiya ___ , District- ___Raigarh__, Chhattisgarh
A |  | Back ground profile
|  | Micro Watershed code | 4G2C6G1j,4G2C6G1i,4G2C6G1k
|  | District- | Raigardh
|  | Block - | kharsiya
|  | Gram Panchayat - | Kurru
|  | Villages Covered - | 1- Kurru ,2 Karawadih
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) - | 1146.21
|  | Rainfall (mm) - | 1192 mm.
|  | Soil type | 1-Sandy clay loam-95% Area 2- Gravelly sandy loam-5% Area
|  | Average Slope - | 1 to 5 %
|  | Details of Tributaries | Mand River
C |  | DEMOGRAPHIC PROFILE
|  | Total Population - | 1629
|  | Total HouseHolds - | 375
|  | ST Population - | 990
|  | SC Population - | 35
D |  | MGNREGA Status |  | FY 2020-2021 | FY 2019-2020 | FY 2018-2019
|  | NREGA Job card holders - |  | 170
|  | Person days per year (average of last 3 years) - |  | 2898 | 5060 | 4706
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) - |  | 4 | 18 | 3
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) |  | 8.26 | 10.26 | 9.31
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) - |  | 74.28 | 72.67 | 41.85
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) | 390.1
|  | Multi cropped (Ha) - | 32.4
|  | Current fallow(Ha) | 4.51
|  | Forest /Plantation (Ha) | 388.24
|  | Waste land (Ha) | 27.17
|  | Impounded Waterbody (Ha) | 12
|  | Others (Ha) | 291.79
F |  | LAND CLASSIFICATION
|  | Forest (Ha) - | 388.24
|  | Upland (Ha) | 298.97
|  | Medium land (Ha) | 345
|  | Low Land (Ha) | 114
|  | River Stream Length (m) | 5000 m.
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds - | 20
|  | Borewells - | 7
|  | Open wells - | 17
H |  | Livelihood profile
|  | Agriculture - |  |  |  | 86.24%
|  | Off Farm Activities - |  |  |  | 2.38%
|  | Wages, labour - |  |  |  | 6.61%
|  | Business - |  |  |  | 2.91%
|  | Service/ job - |  |  |  | 1.85%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) |  |  |  | 122.17
|  | Total Water Available (Ham) - |  |  |  | 59.68
|  | Water Resource to be created (Ham) - |  |  |  | 13.63
|  | Water Resourse Planned ( Ha M) |  |  |  | 7.2
|  | % of Water requirment fulfilled though MWS |  |  |  | 53%
J |  | EXPECTED OUTCOME
Increase in Cropping area (in Ha)
Increase in Irrigated area (in Ha)
Income Enhancement (INR 50,000 per annum as additional income)
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Beneficiary | No. | Dimension |  |  | Estimated cost (lakh) | Estimated labour cost | Persondays Projected | Treated area | Lat.in decimal | Long.in decimal | Targeted HH
|  |  |  | Length (m) | Width (m) | Depth (m) | Lakh Rs. | Lakh Rs. | days | in Ha
Individual Works:
1 | fb | angad singh rathiya | 1 | 155 | 117.8 | 0.3 | 1.054 | 1.0013 | 527 | 1.24 | 22.1666 | 83.2527 | 1
2 | fb | sohan rathiya | 1 | 41.5 | 31.54 | 0.3 | 0.2822 | 0.26809 | 141.1 | 0.332 | 22.1693 | 83.2404 | 1
3 | fb | shyamlal rathiya | 1 | 69 | 52.44 | 0.3 | 0.4692 | 0.44574 | 234.6 | 0.552 | 22.1874 | 83.243 | 1
4 | farm pond | karamsingh rathiya | 1 | 20 | 20 | 3 | 1.2548 | 1.1454 | 602.8211 | 1.5 | 22.1818 | 83.2407 | 1
5 | fb | shital das mahant | 1 | 81 | 61.56 | 0.3 | 0.5508 | 0.52326 | 275.4 | 0.648 | 22.161 | 83.2474 | 1
6 | FRA fb | amar ram rathiya | 1 | 80.125 | 60.895 | 0.3 | 0.54485 | 0.51761 | 272.425 | 0.641 | 22.1596 | 83.2302 | 1
7 | fb | laxman rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1622 | 83.2332 | 1
8 | FRA fb | anand ram rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1704 | 83.2392 | 1
9 | fb | banwari rathiya | 1 | 80 | 60.8 | 0.3 | 0.544 | 0.5168 | 272 | 0.64 | 22.1641 | 83.2596 | 1
10 | FRA fb | foganibai | 1 | 70 | 53.2 | 0.3 | 0.476 | 0.4522 | 238 | 0.56 | 22.1708 | 83.2387 | 1
11 | ll | gopsingh rathiya | 1 | 40.125 | 30.495 | 0.3 | 0.27285 | 0.25921 | 136.425 | 0.321 | 22.183 | 83.2379 | 1
12 | fb | baratram mahant | 1 | 138.75 | 105.45 | 0.3 | 0.9435 | 0.89632 | 471.75 | 1.11 | 22.1723 | 83.2376 | 1
13 | DUG WELL | amarsingh rathiya | 1 | 6 |  | 10.5 | 3.2433 | 1.6098 | 847.2421 | 5.39 | 22.1734 | 83.2371 | 1
14 | fb | sankunwar | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1649 | 83.2478 | 1
15 | FRA fb | narsingh rathiya | 1 | 60.125 | 45.695 | 0.3 | 0.40885 | 0.38841 | 204.425 | 0.481 | 22.1693 | 83.243 | 1
16 | FRA fb | pavansingh rathiya | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1704 | 83.2422 | 1
17 | FRA fb | ratiram rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1639 | 83.232 | 1
18 | FRA fb | ishwar prsad rathiya | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1678 | 83.2423 | 1
19 | ll | gyanlal rathiya | 1 | 39 | 29.64 | 0.3 | 0.2652 | 0.25194 | 132.6 | 0.312 | 22.1662 | 83.2519 | 1
20 | DUG WELL | premlala chouhan | 1 | 6 |  | 10.5 | 3.2433 | 1.6098 | 847.2421 | 5.39 | 22.1655 | 83.2426 | 1
21 | FRA fb | mayaram rathiya | 1 | 80.125 | 60.895 | 0.3 | 0.54485 | 0.51761 | 272.425 | 0.641 | 22.1655 | 83.2426 | 1
22 | fb | ratansingh rathiya | 1 | 30.875 | 23.465 | 0.3 | 0.20995 | 0.19945 | 104.975 | 0.247 | 22.1609 | 83.2517 | 1
23 | FRA fb | aadhram rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1624 | 83.2412 | 1
24 | fb | shyamdas mahant | 1 | 118.75 | 90.25 | 0.3 | 0.8075 | 0.76712 | 403.75 | 0.95 | 22.1696 | 83.2512 | 1
25 | FRA fb | sumitram rathiya | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1573 | 83.2361 | 1
26 | FRA ll | gopal singh rathiya | 1 | 40.125 | 30.495 | 0.3 | 0.27285 | 0.25921 | 136.425 | 0.321 | 22.1701 | 83.2359 | 1
27 | fb | baratdas mahant | 1 | 68.75 | 52.25 | 0.3 | 0.4675 | 0.44412 | 233.75 | 0.55 | 22.1625 | 83.2415 | 1
28 | FRA DW | ajarsingh rathiya | 1 | 6 |  | 9 | 2.9438 | 1.4891 | 783.7368 | 5.39 | 22.1728 | 83.244 | 1
29 | FRA ll | premsingh rathiya | 1 | 96 | 72.96 | 0.3 | 0.6528 | 0.62016 | 326.4 | 0.768 | 22.1663 | 83.242 | 1
30 | FRA fb | sudarsan rathiya | 1 | 121.375 | 92.245 | 0.3 | 0.82535 | 0.78408 | 412.675 | 0.971 | 22.1781 | 83.2205 | 1
31 | FRA fb | chaitkumar rathiya | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1849 | 83.2204 | 1
32 | fb | ghasidas mahant | 1 | 105.875 | 80.465 | 0.3 | 0.71995 | 0.68395 | 359.975 | 0.847 | 22.1774 | 83.2127 | 1
33 | DUG WELL | ktuleshwar patel | 1 | 6 |  | 10.5 | 3.2433 | 1.6098 | 847.2421 | 5.39 | 22.1834 | 83.2209 | 1
34 | DUG WELL | jagbandhu patel | 1 | 6 |  | 10.5 | 3.2433 | 1.6098 | 847.2421 | 5.39 | 22.1747 | 83.2237 | 1
35 | pd | government | 1 | 105 | 90 | 0.9 | 9.381 | 8.9119 | 4690.5 | 9 | 22.1623 | 83.2276 | 5
36 | sichai nali | kanhaiya dansena | 1 | 1000 | 3 | 1.5 | 10 | 9.5 | 5000 | 10 | 22.1606 | 83.2261 | 5
37 | sichai nali | ushabai nishad | 1 | 1000 | 3 | 1.5 | 10 | 9.5 | 5000 | 10 | 22.1689 | 83.2223 | 5
38 | pd | government | 1 | 100 | 90 | 0.9 | 8.934 | 8.4873 | 4467 | 9 | 22.1642 | 83.2213 | 5
39 | pd | government | 1 | 105 | 90 | 0.9 | 9.381 | 8.9119 | 4690.5 | 9 | 22.1651 | 83.2324 | 5
40 | nahar safai | government | 1 | 1000 | 3 | 1.5 | 10 | 9.5 | 5000 | 10 | 22.168 | 83.2203 | 5
41 | nadep tank | government | 1 | 4 | 1.5 | 1 | 0.12 | 0.0276 | 14.5263 |  | 22.1639 | 83.2192 | 1
42 | nadep tank | government | 1 | 4 | 1.5 | 1 | 0.12 | 0.0276 | 14.5263 |  | 22.1692 | 83.2209 | 1
43 | nadep tank | government | 1 | 4 | 1.5 | 1 | 0.12 | 0.0276 | 14.5263 |  | 22.1681 | 83.2228 | 1
44 | nadep tank | government | 1 | 4 | 1.5 | 1 | 0.12 | 0.0276 | 14.5263 |  | 22.1732 | 83.2265 | 1
45 | nadep tank | government | 1 | 4 | 1.5 | 1 | 0.12 | 0.0276 | 14.5263 |  | 22.1717 | 83.2355 | 1
46 | nadep tank | government | 1 | 4 | 1.5 | 1 | 0.12 | 0.0276 | 14.5263 |  | 22.1701 | 83.2229 | 1
47 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1667 | 83.2197 | 1
48 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1606 | 83.2413 | 1
49 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1738 | 83.2309 | 1
50 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1818 | 83.2238 | 1
51 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1628 | 83.236 | 1
52 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1705 | 83.22 | 1
53 | sock pit | government | 1 | 1 | 1 | 1 | 0.12 | 0.03 | 15.7895 | 1 | 22.1751 | 83.2294 | 1
54 | FRA fb | jethsingh | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1758 | 83.2205 | 1
55 | ll | bhojram | 1 | 60.875 | 46.265 | 0.3 | 0.41395 | 0.39325 | 206.975 | 0.487 | 22.1674 | 83.2144 | 1
56 | ll | mohitram | 1 | 106.75 | 81.13 | 0.3 | 0.7259 | 0.6896 | 362.95 | 0.854 | 22.1726 | 83.2429 | 1
57 | FRA fp | mansingh | 1 | 25 | 25 | 3 | 1.999 | 1.86 | 978.9474 | 2.5 | 22.1778 | 83.2159 | 1
58 | FRA fb | leelamati rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1794 | 83.2413 | 1
59 | FRA fb | chaitram rathiya | 1 | 101.25 | 76.95 | 0.3 | 0.6885 | 0.65407 | 344.25 | 0.81 | 22.1631 | 83.2496 | 1
60 | FRA fb | mehattar rathiya | 1 | 109.875 | 83.505 | 0.3 | 0.74715 | 0.70979 | 373.575 | 0.879 | 22.1667 | 83.2173 | 1
61 | FRA fb | sagaram rathiya | 1 | 25.25 | 19.19 | 0.3 | 0.1717 | 0.16312 | 85.85 | 0.202 | 22.1737 | 83.241 | 1
62 | FRA fb | harisingh rathiya | 1 | 131.5 | 99.94 | 0.3 | 0.8942 | 0.84949 | 447.1 | 1.052 | 22.1591 | 83.2362 | 1
63 | FRA fb | yogat rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1591 | 83.2362 | 1
64 | FRA fb | khemsingh rathiya | 1 | 190 | 144.4 | 0.3 | 1.292 | 1.2274 | 646 | 1.52 | 22.1818 | 83.2186 | 1
65 | FRA dw | ramkumar rathiya | 1 | 6 |  | 9 | 2.9438 | 1.4891 | 783.7368 | 5.39 | 22.1833 | 83.2122 | 1
66 | FRA fb | ratthuram rathiya | 1 | 7.125 | 5.415 | 0.3 | 0.04845 | 0.046027 | 24.225 | 0.057 | 22.1858 | 83.2158 | 1
67 | FRA fb | rahas kumar rathiya | 1 | 7.125 | 5.415 | 0.3 | 0.04845 | 0.046027 | 24.225 | 0.057 | 22.1633 | 83.2255 | 1
68 | FRA fb | santram rathiya | 1 | 12 | 9.12 | 0.3 | 0.0816 | 0.07752 | 40.8 | 0.096 | 22.1695 | 83.226 | 1
69 | FRA fb | dhadhram rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1724 | 83.2189 | 1
70 | FRA fb | pyarilal rathiya | 1 | 30.125 | 22.895 | 0.3 | 0.20485 | 0.19461 | 102.425 | 0.241 | 22.1615 | 83.2207 | 1
71 | FRA fb | pitamber rathiya | 1 | 50.625 | 38.475 | 0.3 | 0.34425 | 0.32704 | 172.125 | 0.405 | 22.1672 | 83.2266 | 1
72 | FRA fb | puniram rathiya | 1 | 40.125 | 30.495 | 0.3 | 0.27285 | 0.25921 | 136.425 | 0.321 | 22.1684 | 83.2268 | 1
73 | FRA fb | thakurram | 1 | 50.625 | 38.475 | 0.3 | 0.34425 | 0.32704 | 172.125 | 0.405 | 22.1668 | 83.2279 | 1
74 | FRA fb | ramprasad rathiya | 1 | 41.5 | 31.54 | 0.3 | 0.2822 | 0.26809 | 141.1 | 0.332 | 22.1617 | 83.2265 | 1
75 | FRA fb | ashok rathiya | 1 | 50.625 | 38.475 | 0.3 | 0.34425 | 0.32704 | 172.125 | 0.405 | 22.1703 | 83.2257 | 1
76 | FRA fb | shankar singh rathiya | 1 | 120 | 91.2 | 0.3 | 0.816 | 0.7752 | 408 | 0.96 | 22.1705 | 83.2181 | 1
77 | FRA fb | narendra kumar rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1711 | 83.2277 | 1
78 | FRA fb | filam singh rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1626 | 83.2289 | 1
79 | FRA fb | bidyasingh rathiya | 1 | 50.625 | 38.475 | 0.3 | 0.34425 | 0.32704 | 172.125 | 0.405 | 22.1692 | 83.2269 | 1
80 | FRA fb | rajaram rathiya | 1 | 72 | 54.72 | 0.3 | 0.4896 | 0.46512 | 244.8 | 0.576 | 22.1652 | 83.2368 | 1
81 | FRA fb | sampatti bai rathiya | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1862 | 83.2378 | 1
82 | FRA fb | gajaram rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1714 | 83.2394 | 1
83 | FRA fb | manmohan rathiya | 1 | 25.25 | 19.19 | 0.3 | 0.1717 | 0.16312 | 85.85 | 0.202 | 22.1638 | 83.2278 | 1
84 | FRA fb | chotelal rathiya | 1 | 33.25 | 25.27 | 0.3 | 0.2261 | 0.21479 | 113.05 | 0.266 | 22.1896 | 83.2157 | 1
85 | FRA fb | madhuri bai rathiya | 1 | 101.125 | 76.855 | 0.3 | 0.68765 | 0.65327 | 343.825 | 0.809 | 22.1697 | 83.2292 | 1
86 | FRA PS | shashibhusan rathiya | 1 | 8 | 3.5 |  | 1.2 | 0.14675 | 77.2368 |  | 22.1758 | 83.2205 | 1
87 | FRA DW | santlal rathiya | 1 | 6 |  | 9 | 2.9438 | 1.4891 | 783.7368 | 5.39 | 22.1758 | 83.2205 | 1
88 | FRA LL | lagansingh rathiya | 1 | 65 | 49.4 | 0.3 | 0.442 | 0.4199 | 221 | 0.52 | 22.1752 | 83.214 | 1
89 | FRA LL | pannalal rathiya | 1 | 30 | 22.8 | 0.3 | 0.204 | 0.1938 | 102 | 0.24 | 22.1743 | 83.2162 | 1
90 | FRA fb | puransingh rathiya | 1 | 56 | 42.56 | 0.3 | 0.3808 | 0.36176 | 190.4 | 0.448 | 22.1731 | 83.2124 | 1
91 | FRA fb | dhanpat rathiya | 1 | 90 | 68.4 | 0.3 | 0.612 | 0.5814 | 306 | 0.72 | 22.1776 | 83.2264 | 1
92 | FRA fb | chamar singh rathiya | 1 | 35 | 26.6 | 0.3 | 0.238 | 0.2261 | 119 | 0.28 | 22.1576 | 83.2376 | 1
93 | FRA fb | laxmi prasad rathiya | 1 | 104 | 79.04 | 0.3 | 0.7072 | 0.67184 | 353.6 | 0.832 | 22.1631 | 83.2391 | 1
94 | FRA fb | akhaya kumar rathiya | 1 | 104 | 79.04 | 0.3 | 0.7072 | 0.67184 | 353.6 | 0.832 | 22.1645 | 83.2348 | 1
95 | FRA fb | prakash nath | 1 | 78 | 59.28 | 0.3 | 0.5304 | 0.50388 | 265.2 | 0.624 | 22.1707 | 83.2376 | 1
96 | FRA fb | hetram rathiya | 1 | 66 | 50.16 | 0.3 | 0.4488 | 0.42636 | 224.4 | 0.528 | 22.175 | 83.2447 | 1
97 | FRA fb | santanu rathiya | 1 | 55 | 41.8 | 0.3 | 0.374 | 0.3553 | 187 | 0.44 | 22.1668 | 83.2454 | 1
98 | FRA fb | manjhilal rathiya | 1 | 75 | 57 | 0.3 | 0.51 | 0.4845 | 255 | 0.6 | 22.1542 | 83.2272 | 1
99 | FRA fb | devsingh rathiya | 1 | 25.25 | 19.19 | 0.3 | 0.1717 | 0.16312 | 85.85 | 0.202 | 22.1756 | 83.235 | 1
100 | FRA fb | meena rathiya | 1 | 100.75 | 76.57 | 0.3 | 0.6851 | 0.65085 | 342.55 | 0.806 | 22.1811 | 83.2162 | 1
101 | FRA fb | sankunwar rathiya | 1 | 75.875 | 57.665 | 0.3 | 0.51595 | 0.49015 | 257.975 | 0.607 | 22.1682 | 83.2182 | 1
102 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1694 | 83.2272 | 5
103 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1591 | 83.2244 | 5
104 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1673 | 83.2254 | 5
105 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1675 | 83.2271 | 5
106 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1662 | 83.2539 | 5
107 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1625 | 83.2432 | 5
108 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.163 | 83.2352 | 5
109 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1954 | 83.2375 | 5
110 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1876 | 83.2381 | 5
111 | GP | government | 1 | 30 | (10+1)/2 | 3 | 0.45342 | 0.43981 | 231.4789 | 5 | 22.1628 | 83.2439 | 5
112 | LL | sakuntala rathiya | 1 | 73.375 | 55.765 | 0.3 | 0.49895 | 0.474 | 249.475 | 0.587 | 22.156 | 83.2287 | 1
113 | farm pond | damrudhar agariya | 1 | 20 | 20 | 3 | 1.2548 | 1.1454 | 602.8211 | 1.5 | 22.1631 | 83.2391 | 1
114 | DUG WELL | baldev prasad swarnkar | 1 | 6 |  | 10.5 | 3.2433 | 1.6098 | 847.2421 | 5.39 | 22.1636 | 83.2293 | 1
115 | DUG WELL | kenwara bai dansena | 1 | 6 |  | 10.5 | 3.2433 | 1.6098 | 847.2421 | 5.39 | 22.1652 | 83.2455 | 1
116 | LL | nankunwar rathiya | 1 | 82.25 | 62.51 | 0.3 | 0.5593 | 0.53134 | 279.65 | 0.658 | 22.181 | 83.2162 | 1
117 | LL | chandraprakash mahant | 1 | 81.125 | 61.655 | 0.3 | 0.55165 | 0.52407 | 275.825 | 0.649 | 22.181 | 83.2164 | 1
Total |  |  | 117 |  |  |  | 135.6804 | 114.0042 | 60002.1882 | 212.587 | 2593.8779 | 9738.0746 | 181
20

## NREGA Data (hidden)
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Baspattar | [5 empty] | As on 10-06-2020
I Job Card
Total No. of JobCards issued | 302
Total No. of Workers | 1445
Total No. of Active Job Cards | 291
Total No. of Active Workers | 1329
(i)SC worker against active workers[%] | 1.05
(ii)ST worker against active workers[%] | 65.46
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9390 | 37789 | 32713 | 34769 | 15342
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 1.66 | 1.37 | 1.13 | 0.89 | 1.1
ST persondays % as of total persondays | 54.1 | 50.59 | 53.89 | 51.82 | 44.81
Women Persondays out of Total (%) | 47.74 | 48.15 | 47.82 | 51.61 | 51.3
Average days of employment provided per Household | 42.49 | 133.06 | 115.19 | 124.18 | 57.25
Average Wage rate per day per person(Rs.) | 189.85 | 175.93 | 174 | 172 | 167
Total No of HHs completed 100 Days of Wage Employment | 0 | 233 | 204 | 198 | 23
Total Households Worked | 221 | 284 | 284 | 280 | 268
Total Individuals Worked | 455 | 627 | 617 | 606 | 555
Differently abled persons worked | 1 | 4 | 0 | 1 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 47 | 75 | 117 | 85 | 80
Number of Ongoing Works | 19 | 41 | 42 | 44 | 41
Number of Completed Works | 28 | 34 | 75 | 41 | 39
% of NRM Expenditure(Public + Individual) | 83.17 | 85.02 | 77.45 | 86.74 | 69.31
% of Category B Works | 85.11 | 90.67 | 94.02 | 82.35 | 80
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 33.78 | 70.99 | 62.08 | 68.25 | 28.57
Wages(Rs. In Lakhs) | 25.31 | 60.5 | 55.2 | 59.49 | 24.23
Material and skilled Wages(Rs. In Lakhs) | 8.28 | 9.83 | 6.08 | 7.78 | 3.46
Material(%) | 24.65 | 13.98 | 9.92 | 11.56 | 12.51
Total Adm Expenditure (Rs. in Lakhs.) | 0.18 | 0.66 | 0.8 | 0.98 | 0.88
Admin Exp(%) | 0.53 | 0.93 | 1.29 | 1.44 | 3.08
Average Cost Per Day Per Person(In Rs.) | 193.08 | 202 | 176.44 | 195.03 | 178.38
% of Total Expenditure through EFMS | 100 | 100 | 99.98 | 99.73 | 100
% payments gererated within 15 days | 100 | 79.31 | 90.55 | 100 | 45.71

## Calculation (hidden)
Tentative treated area calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | capacity/ volume (In Cum) | Command area (Irrigated Area ) | Minimum required catchment area | Area Treated
|  |  | Dimenssion | in m | in m | in m | In Cum | in Ha | In Ha | In Ha
1 | Farm Pond | शामकुंवर/रामबिशेष | 23X23X3 | 25 | 25 | 3 | 1491.87 | 0.74594 | 1.4919 | 2.2378
2 | Farm Pond | बंदीराम/दयाराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
3 | Farm Pond | आत्माराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
4 | Farm Pond | आत्माराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
5 | Farm Pond | कमितला बाई/सुकडू | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
6 | Farm Pond | बंदीराम/दयाराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
7 | Farm Pond | चैनबती मरकाम/रामदयाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
8 | Farm Pond | रामदयाल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
9 | Farm Pond | सुकमन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
10 | Farm Pond | भागबती | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
11 | Farm Pond | नारायण | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
12 | Farm Pond | नारद | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
13 | Farm Pond | गनेशिया बाई/आनंद राम सोनी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
14 | Farm Pond | नारायण मरकाम/मेहत्तर | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
15 | Farm Pond | सुकलाईन/धनसिंग विश्वकर्मा | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
16 | Farm Pond | बरमन कुलदीप/कंगलाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
17 | Farm Pond | दसरु राम यादव/मेहत्तर यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
18 | Farm Pond | रमेश सोनवानी/राजकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
19 | Farm Pond | पीलादास मरकाम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
20 | Farm Pond | दयमोतीन नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
21 | Farm Pond | अघनसिंह नेताम/तिजिया नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
22 | Farm Pond | रामसिंह वट्टी/केशरी बाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
23 | Farm Pond | प्रभुराम वट्टी/स्वयं | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
24 | Farm Pond | लतखोरीन नेताम/छेरका | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
25 | Farm Pond | मनराखन यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
26 | Farm Pond | मन्नूराम भास्कर/झंगन सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
27 | Farm Pond | पुष्कर/नथेला राम यादव | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
28 | Farm Pond | लक्ष्मी लाल/गनेशिया | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
29 | Farm Pond | नोहर सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
30 | Farm Pond | नोहर सिंह | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
31 | Farm Pond | राजकुमार/सोनूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
32 | Farm Pond | राम/हलाल राम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
33 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
34 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
35 | Farm Pond | झाड़ूराम/लादूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
36 | Farm Pond | झाड़ूराम/लादूराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
37 | Farm Pond | नोहरसिंह/मसिया | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
38 | Farm Pond | फूलसिंह/हीरासिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
39 | Farm Pond | उदेराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
40 | Farm Pond | लक्ष्मण | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
41 | Farm Pond | पिलाराम/रामभरोष | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
42 | Farm Pond | धनीराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
43 | Farm Pond | चमरसिंह /सुरेखा नेताम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
44 | Farm Pond | रामनाथ/रमतुला वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
45 | Farm Pond | नन्दकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
46 | Farm Pond | चमरसिंह/सगन बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
47 | Farm Pond | जयलाल नेताम/अघनबाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
48 | Farm Pond | सुकबाई यादव/स्वयं | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
49 | Farm Pond | सुकबाई यादव/स्वयं | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
50 | Farm Pond | रामजी/मानकी वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
51 | Farm Pond | नवल सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
52 | Farm Pond | नवल यादव/दल्ली यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
53 | Farm Pond | दुर्जन यादव/दिनदयाल | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
54 | Farm Pond | धनेश यादव/धर्मिन | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
55 | Farm Pond | धनेश यादव/धर्मिन | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
56 | Farm Pond | गुहाराम यादव/अहिल्या | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
57 | Farm Pond | छन्नू राम/उषा बाई | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
58 | Farm Pond | छन्नू राम/उषा बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
59 | Farm Pond | लालसाय मंडावी | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
60 | Farm Pond | लक्ष्मीनाथ नेताम/बैजनतीन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
61 | Farm Pond | रामबती/सुकलाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
62 | Farm Pond | शांति बाई/रामसिंग | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
63 | Farm Pond | बिन्देसिंह/रोहीदास | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
64 | Farm Pond | अमरोबाई/रामजी | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
65 | Farm Pond | जयराम/रामचंद | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
66 | Farm Pond | सन्तुराम मंडावी/सवित्री | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
67 | Farm Pond | आनंदराम नेताम/दुखिया | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
68 | Farm Pond | आनंदराम नेताम/दुखिया | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
69 | Farm Pond | दुखिया नेताम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
70 | Farm Pond | संग्राम/रामसिंह | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
71 | Farm Pond | कनसी/सैदर | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
72 | Farm Pond | किसनू/जोहन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
73 | Farm Pond | कौशिल्या/दीपल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
74 | Farm Pond | प्रवीण मरकाम/रामचंद | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
75 | Land levelling | रूपनाथ मरकाम/परमिला मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
76 | Land levelling | राजाराम मरकाम/चंद्रिका मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
77 | Land levelling | अनीत मरकाम/बृजबती | 1.01 | 1.01 | [5 empty] | 1.01
78 | Land levelling | नीलम कुमार/सगारो बाई | 0.8 | 0.8 | [5 empty] | 0.8
79 | Land levelling | अघनसिंह नेताम/तिजिया नेताम | 0.4 | 0.4 | [5 empty] | 0.4
80 | Land levelling | रूपराय मरकाम/रेमा मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
81 | Land levelling | मोहनराम वट्टी/भवनतीन वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
82 | Land levelling | प्रभुराम वट्टी/स्वयं | 0.4 | 0.4 | [5 empty] | 0.4
83 | Land levelling | रामसिंह वट्टी/केशरी बाई | 0.4 | 0.4 | [5 empty] | 0.4
84 | Land levelling | सगनी/देवराज मरकाम | 0.4 | 0.4 | [5 empty] | 0.4
85 | Land levelling | अमरसिंह/परमिला | 0.4 | 0.4 | [5 empty] | 0.4
86 | Land levelling | उदेराम | 0.8 | 0.8 | [5 empty] | 0.8
87 | Land levelling | रामनाथ/रमतुला वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
88 | Land levelling | धनीराम | 0.8 | 0.8 | [5 empty] | 0.8
89 | Land levelling | श्री राम/दयाबती | 0.2 | 0.2 | [5 empty] | 0.2
90 | Land levelling | चमरसिंह/सगन बाई | 0.8 | 0.8 | [5 empty] | 0.8
91 | Land levelling | जयलाल नेताम/अघनबाई | 0.8 | 0.8 | [5 empty] | 0.8
92 | Land levelling | रामजी/मानकी वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
93 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
94 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
95 | Land levelling | लक्ष्मीनाथ नेताम/बैजनतीन | 0.4 | 0.4 | [5 empty] | 0.4
96 | Land levelling | संगीता/राम नेताम | 0.04 | 0.04 | [5 empty] | 0.04
97 | Land levelling | राजूराम/रामसिंग | 0.8 | 0.8 | [5 empty] | 0.8
98 | Land levelling | जयराम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
99 | Land levelling | सिरमो/छेदीलाल | 0.4 | 0.4 | [5 empty] | 0.4
100 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.5 | 0.5 | [5 empty] | 0.5
101 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.4 | 0.4 | [5 empty] | 0.4
102 | Land levelling | लक्ष्मीनाथ/बैजन्तीन | 0.4 | 0.4 | [5 empty] | 0.4
103 | Land levelling | संग्राम/रामसिंह | 0.04 | 0.04 | [5 empty] | 0.04
104 | Plantation | मन्नूराम भास्कर/झंगन सिंह | 0.4 | 0.4 | [5 empty] | 0.4
105 | Plantation | सुकबाई यादव/स्वयं | 0.2 | 0.2 | [5 empty] | 0.2
106 | Plantation | दुर्जन यादव/दिनदयाल | 0.5 | 0.5 | [5 empty] | 0.5
107 | Plantation | धनेश यादव/धर्मिन | 0.5 | 0.5 | [5 empty] | 0.5
108 | Plantation | गुहाराम यादव/अहिल्या | 0.5 | 0.5 | [5 empty] | 0.5
109 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  | as per Field data |  | 1
110 | Dug Well | नारद/जयलाल | 7X7 | 7 | 7 |  |  |  |  | 1
111 | Dug Well | आत्माराम | 7X7 | 7 | 7 |  |  |  |  | 1
112 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  |  |  | 1
113 | Dug Well | बंदीराम/दयाराम | 7X7 | 7 | 7 |  |  |  |  | 1
114 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
115 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
116 | Dug Well | नारायण | 7X7 | 7 | 7 |  |  |  |  | 1
117 | Dug Well | सुकमन | 7X7 | 7 | 7 |  |  |  |  | 1
118 | Dug Well | भागबती | 7X7 | 7 | 7 |  |  |  |  | 1
119 | Dug Well | दशोबाई | 7X7 | 7 | 7 |  |  |  |  | 1
120 | Dug Well | नरेश | 7X7 | 7 | 7 |  |  |  |  | 1
121 | Dug Well | शामकुंवर/रामबिशेष | 7X7 | 7 | 7 |  |  |  |  | 1
122 | Dug Well | गनेशिया बाई/आनंद राम सोनी | 7X7 | 7 | 7 |  |  |  |  | 1
123 | Dug Well | माखन यादव/तिभू | 7X7 | 7 | 7 |  |  |  |  | 1
124 | Dug Well | तीजऊ राम यादव/बिसऊराम | 7X7 | 7 | 7 |  |  |  |  | 1
125 | Dug Well | सुकलाईन/धनसिंग विश्वकर्मा | 7X7 | 7 | 7 |  |  |  |  | 1
126 | Dug Well | बरमन कुलदीप/कंगलाराम | 7X7 | 7 | 7 |  |  |  |  | 1
127 | Dug Well | रामबाई सोनवानी/तुलीया राम सोनवानी | 7X7 | 7 | 7 |  |  |  |  | 1
128 | Dug Well | भगवान सिंह मरकाम/ | 7X7 | 7 | 7 |  |  |  |  | 1
129 | Dug Well | केशव मरकाम/बिराजो मरकाम | 7X7 | 7 | 7 |  |  |  |  | 1
130 | Dug Well | शिवनारायण यादव/रजमन | 7X7 | 7 | 7 |  |  |  |  | 1
131 | Dug Well | लतखोरीन नेताम/छेरका | 7X7 | 7 | 7 |  |  |  |  | 1
132 | Dug Well | श्याम लाल यादव/लतखोर | 7X7 | 7 | 7 |  |  |  |  | 1
133 | Dug Well | मन्नूराम भास्कर/झंगन सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
134 | Dug Well | मोती राम सोनी/मोहन लाल | 7X7 | 7 | 7 |  |  |  |  | 1
135 | Dug Well | राजकुमार/सोनूराम | 7X7 | 7 | 7 |  |  |  |  | 1
136 | Dug Well | झाड़ूराम/लादूराम | 7X7 | 7 | 7 |  |  |  |  | 1
137 | Dug Well | नोहरसिंह/मसिया | 7X7 | 7 | 7 |  |  |  |  | 1
138 | Dug Well | अर्जुन/दीनदयाल | 7X7 | 7 | 7 |  |  |  |  | 1
139 | Dug Well | छन्नू राम | 7X7 | 7 | 7 |  |  |  |  | 1
140 | Dug Well | उदेराम | 7X7 | 7 | 7 |  |  |  |  | 1
141 | Dug Well | लक्ष्मण | 7X7 | 7 | 7 |  |  |  |  | 1
142 | Dug Well | पिलाराम/रामभरोष | 7X7 | 7 | 7 |  |  |  |  | 1
143 | Dug Well | श्री राम/दयाबती | 7X7 | 7 | 7 |  |  |  |  | 1
144 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
145 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
146 | Dug Well | माखन यादव/तीजू यादव | 7X7 | 7 | 7 |  |  |  |  | 1
147 | Dug Well | नवल सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
148 | Dug Well | नवल यादव/दल्ली यादव | 7X7 | 7 | 7 |  |  |  |  | 1
149 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
150 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
151 | Dug Well | गुहाराम यादव/अहिल्या | 7X7 | 7 | 7 |  |  |  |  | 1
152 | Dug Well | लालसाय मंडावी | 7X7 | 7 | 7 |  |  |  |  | 1
153 | Dug Well | तुलसी/सुकलाल | 7X7 | 7 | 7 |  |  |  |  | 1
154 | Dug Well | कांशीराम/सैदर | 7X7 | 7 | 7 |  |  |  |  | 1
155 | Dug Well | किसून/जोहन | 7X7 | 7 | 7 |  |  |  |  | 1
156 | Dug Well | कौश्लिया/दीपल | 7X7 | 7 | 7 |  |  |  |  | 1
157 | Dug Well | प्रवीण मरकाम/रामचंद | 7X7 | 7 | 7 |  |  |  |  | 1
158 | Farm bonding | संगीता/श्रीराम | 0.4 | 0.4 | [5 empty] | 0.4
159 | Farm bonding | श्यामलाल/मेहेरसिंह | 0.4 | 0.4 | [5 empty] | 0.4
160 | Farm bonding | प्रवीण मरकाम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
161 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
162 | Desilting | common Land | 45X45X4 | 45 | 45 | 4 | 6421.3511 | 3.2107 | 6.4214 | 9.632
163 | Desilting | common Land | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
164 | Desilting | common Land | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
165 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
166 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1 | Command area as per actual field data (Minimum command area
167 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1
168 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7500 | 13.5 |  | 2 |  | Time of refills X (Submergence area* d/3)
169 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 8750 | 15.75 |  | 2 |  | Time of refills X (Submergence area* d/3)
170 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7200 | 12.96 |  | 2 |  | Time of refills X (Submergence area* d/3)
171 | Checkdam | 3rd Order Nala | 25X 40X1.5 | 25 | 125 | 2 | 8700 | 15.66 |  | 2 |  | Time of refills X (Submergence area* d/3)
172 | Checkdam | 3rd Order Nala | 25X 40X1.6 | 25 | 125 | 2 | 9800 | 17.64 |  | 2 |  | Time of refills X (Submergence area* d/3)
[7 empty] | 237159.0111 | 173.1145 | 195.209 | 372.0235
23.7159

## Sheet1 (hidden)
Earthwork Calculation
| Step | Length m | Width m | Depth m | Volume m3
Hard soil depth
| Step 1 | 23 | 23 | 0.3 | 158.7 | 17.6
| Step 2 | 22.4 | 22.4 | 0.3 | 150.528 | 22.4
| Step 3 | 21.8 | 21.8 | 0.3 | 142.572 | 21.8
| Step 4 | 21.2 | 21.2 | 0.3 | 134.832 | 16.6
| Step 5 | 20.6 | 20.6 | 0.3 | 127.308 | 16
| Step 6 | 20 | 20 | 0.3 | 120 | 20
3 | Step 7 | 19.4 | 19.4 | 0.3 | 112.908 | 19.4
| Step 8 | 18.8 | 18.8 | 0.3 | 106.032 | 18.8
| Step 9 | 18.2 | 18.2 | 0.3 | 99.372 | 18.2
23 | Step 10 | 17.6 | 17.6 | 0.3 | 92.928 | 17.6
23 | Total Earthwork in Cum |  |  |  | 1245.18