## edpr
e DPR of Charbhatti GP, Block Narharpur , Dist kanker Chhattisgarh
A | Back ground profile
| Micro Watershed code |  | 4G2G5D1f, 4G2G5D1i, 4G2G5D2a, 4G2G5D1h
| District |  | Kanker
| Block |  | Narharpur
| Gram Panchayat |  | Charbhatti
| Villages Covered |  | Charbhatti
B | PHYSIOGRAPHIC PROFILE
| Total Area (Ha) |  | 523.79
| Rainfall (mm) |  | 1200
| Soil type |  | Sandy Loam
| Average Slope |  | 2%-14%
| Details of Tributaries |  | Nakti Nala | 2500 m long | Flows from june to April
C | DEMOGRAPHIC PROFILE
| Total Population |  | 1188
| Total HouseHolds |  | 245
| ST Population |  | 909
| SC Population |  | 25
D | MGNREGA Status
| NREGA Job card holders |  | 263
| Person days per year (average of last 3 years) |  | 12203
| Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) |  | 31.3
| Total annual Exp(Rs. in Lakhs.)(average of last 3 years) |  | 25.06
| % of NRM Expenditure(Public + Individual) (average of last 3 years) |  | 64.8
E | LAND USE LAND COVER
| Mono cropped (Ha) |  | 428.07
| Multi cropped (Ha) |  | 10.43
| Current fallow(Ha) |  | 8.14
| Forest /Plantation (Ha) |  | 22.83
| Waste land (Ha) |  | 4.67
| Impounded Waterbody (Ha) |  | 34
| Others (Ha) |  | 15.65
F | LAND CLASSIFICATION
| Forest (Ha) |  | 22.83
| Upland (Ha) |  | 108.46
| Medium land (Ha) |  | 218
| Low Land (Ha) |  | 174.5
| River Stream Length (m) |  | 2500 m
G | Existing Water sources/ Structures
| Water harvesting Ponds |  | 21 Nos | 14.22 Ha-m
| Borewells |  | 85
| Open wells |  | 7
H | Livelihood profile
| Agriculture |  | 95%
| Off Farm Activities |  | 7%
| Wages, labour |  | 86%
| Business |  | 6%
| Service/ job |  | 3%
I | WATER BUDGET
| Total Water Requirement (Ham) |  | 46.35 | (Considering 50% Water requirement will be meet by Rainfall)
| Total Water Available (Ham) |  | 14.22
| Water Resource to be created (Ham) |  | 32.13
| Water Resourse Planned ( Ha M) |  | 18.149
| % of Water requirment fulfilled though MWS |  | 56.49%
J | EXPECTED OUTCOME
| Increase in Cropping area (in Ha) |  | 114.624
| Increase in Irrigated area (in Ha) |  | 88.344
| Income Enhancement (INR 50000 per annum as additional income) |  | 40 HH
Sr No. | Type of intervention | Name of the Benificiary | No. | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
1 | Farmpond | छेदु / माखन | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3822 | 81.5115 | 1
2 | Farmpond | नरोत्तम / प्रेम सिंह | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3791 | 81.5296 | 1
3 | Farmpond | पीला बाई / लक्ष्मण | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3771 | 81.5223 | 1
4 | Farmpond | प्रभुराम / मेह्तु | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3779 | 81.5282 | 1
5 | Farmpond | घुराऊ / जंगली | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3793 | 81.528 | 1
6 | Farmpond | इतवारी / गुलूराम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3896 | 81.5252 | 1
7 | Farmpond | दाऊराम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 |  |  | 1
8 | Farmpond | मन्नू/कल्याण | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3722 | 81.5218 | 1
9 | Farmpond | रामानन्द कोडोपी | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3892 | 81.5199 | 1
10 | Farmpond | सियाबती/ मायाराम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3845 | 81.5229 | 1
11 | Farmpond | सुधराम / रामलाल | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3716 | 81.5119 | 1
12 | Farmpond | सुकदेव / भवरसिंह | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3902 | 81.527 | 1
13 | Farmpond | पीलाबाई / लक्ष्मण | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3793 | 81.5242 | 1
14 | Farmpond | जयसिंह / कमल | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3788 | 81.5226 | 1
15 | Farmpond | रामलाल / कवल | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3856 | 81.5256 | 1
16 | Farmpond | रामप्रसाद / फागुराम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3791 | 81.5291 | 1
17 | Farmpond | रमेश / हीराराम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3768 | 81.5229 | 1
18 | Farmpond | बसंतीन / ब्रिजलाल | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3779 | 81.5272 | 1
19 | Farmpond | राधेश्याम / जगमोहन | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3895 | 81.5236 | 1
20 | Farmpond | नवली / देवसिंग | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3794 | 81.5248 | 1
21 | Farmpond | महेंद्र / जयलाल | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3889 | 81.5245 | 1
22 | Farmpond | शोभुराम / मंगतू | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3888 | 81.5238 | 1
23 | Farmpond | बिसनाथ | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3972 | 81.5342 | 1
24 | Farmpond | चमरू | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3781 | 81.5259 | 1
25 | Farmpond | कार्तिक | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3872 | 81.5344 | 1
26 | Farmpond | भानू/उजियार | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3782 | 81.5176 | 1
27 | Farmpond | कृष्णा/रामसाय | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3731 | 81.5215 | 1
28 | Farmpond | सग्राम/दसरु | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3733 | 81.5215 | 1
29 | Farmpond | सरद/सुखुराम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3733 | 81.5216 | 1
30 | Farmpond | चिन्ताराम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3773 | 81.5272 | 1
31 | Farmpond | भगवान | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3771 | 81.5229 | 1
32 | Farmpond | भागी / धरमसिंह | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3757 | 81.5258 | 1
33 | Farmpond | देवराज | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3773 | 81.5178 | 1
34 | Farmpond | कन्हैया / रामलाल | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3723 | 81.5229 | 1
35 | Farmpond | दुखुराम नाग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3861 | 81.5347 | 1
36 | Farmpond | राजेश मंडावी | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3846 | 81.5339 | 1
37 | Farmpond | फूल सिंह नेताम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3866 | 81.5327 | 1
38 | Land levelling | छेदु / माखन | 1 | 0.8 | 0.76 | 0.646 | 368 | 0.8 | 20.3826 | 81.5116 | 1
39 | Land levelling | नरोत्तम / प्रेम सिंह | 1 | 0.62 | 0.589 | 0.50065 | 285.2 | 0.62 | 20.3792 | 81.5298 | 1
40 | Land levelling | जयसिंह / कमल | 1 | 0.88 | 0.836 | 0.7106 | 404.8 | 0.88 | 20.3787 | 81.5235 | 1
41 | Land levelling | रामलाल / कवल | 1 | 0.9 | 0.855 | 0.72675 | 414 | 0.9 | 20.3856 | 81.5251 | 1
42 | Land levelling | रामप्रसाद / फागुराम | 1 | 1.8 | 1.71 | 1.4535 | 828 | 1.8 | 20.3841 | 81.5236 | 1
43 | Land levelling | पीला बाई / लक्ष्मण | 1 | 0.6 | 0.57 | 0.4845 | 276 | 0.6 | 20.3774 | 81.5223 | 1
44 | Land levelling | रमेश / हीराराम | 1 | 0.78 | 0.741 | 0.62985 | 358.8 | 0.78 | 20.3768 | 81.5228 | 1
45 | Land levelling | बसंतीन / ब्रिजलाल | 1 | 1.02 | 0.969 | 0.82365 | 469.2 | 1.02 | 20.3779 | 81.5272 | 1
46 | Land levelling | प्रभुराम / मेह्तु | 1 | 0.36 | 0.342 | 0.2907 | 165.6 | 0.36 | 20.3779 | 81.528 | 1
47 | Land levelling | राधेश्याम / जगमोहन | 1 | 0.75 | 0.7125 | 0.60562 | 345 | 0.75 | 20.3893 | 81.5234 | 1
48 | Land levelling | नवली / देवसिंग | 1 | 0.6 | 0.57 | 0.4845 | 276 | 0.6 | 20.3793 | 81.5244 | 1
49 | Land levelling | घुराऊ / जंगली | 1 | 0.45 | 0.4275 | 0.36338 | 207 | 0.45 | 20.3836 | 81.5259 | 1
50 | Land levelling | महेंद्र / जयलाल | 1 | 0.61 | 0.5795 | 0.49257 | 280.6 | 0.61 | 20.389 | 81.525 | 1
51 | Land levelling | इतवारी / गुलूराम | 1 | 1.12 | 1.064 | 0.9044 | 515.2 | 1.12 | 20.3896 | 81.525 | 1
52 | Land levelling | शोभुराम / मंगतू | 1 | 0.62 | 0.589 | 0.50065 | 285.2 | 0.62 | 20.3888 | 81.5239 | 1
53 | Land levelling | बिसनाथ | 1 | 0.8 | 0.76 | 0.646 | 368 | 0.8 | 20.3971 | 81.5335 | 1
54 | Land levelling | चमरू | 1 | 2.31 | 2.1945 | 1.8653 | 1062.6 | 2.31 | 20.3819 | 81.5545 | 1
55 | Land levelling | सुरेश | 1 | 0.8 | 0.76 | 0.646 | 368 | 0.8 |  |  | 1
56 | Land levelling | लतेल | 1 | 0.65 | 0.6175 | 0.52487 | 299 | 0.65 | 20.3721 | 81.5228 | 1
57 | Land levelling | मन्नू/कल्याण | 1 | 0.8 | 0.76 | 0.646 | 368 | 0.8 | 20.3725 | 81.5217 | 1
58 | Land levelling | समरथ/तुलसी | 1 | 0.55 | 0.5225 | 0.44413 | 253 | 0.55 | 20.3733 | 81.5216 | 1
59 | Land levelling | रामप्रसाद साहू | 1 | 0.5 | 0.475 | 0.40375 | 230 | 0.5 | 20.3893 | 81.5196 | 1
60 | Land levelling | चिन्ताराम | 1 | 0.91 | 0.8645 | 0.73483 | 418.6 | 0.91 | 20.3773 | 81.5272 | 1
61 | Land levelling | सियाबती/ मायाराम | 1 | 1.09 | 1.0355 | 0.88018 | 501.4 | 1.09 | 20.3845 | 81.5229 | 1
62 | Land levelling | देवराज | 1 | 0.76 | 0.722 | 0.6137 | 349.6 | 0.76 | 20.3773 | 81.518 | 1
63 | Land levelling | कन्हैया / रामलाल | 1 | 2 | 1.9 | 1.615 | 920 | 2 | 20.3744 | 81.522 | 1
64 | Dugwell | सुकदेव / भवरसिंह | 1 | 7X7 | 1.5 | 0.525 | 259 | 5.39 | 20.3907 | 81.5275 | 1
65 | Plantation | सुकदेव / भवरसिंह | 1 | 2 | 0.87 | 5.36 | 500 | 2 | 20.3906 | 81.5266 | 1
66 | Plantation | पीलाबाई / लक्ष्मण | 1 | 1.2 | 0.522 | 3.216 | 300 | 1.2 | 20.3784 | 81.5224 | 1
67 | LBS | सुन्दरलाल / मोतीलाल | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.379 | 81.528 | 1
68 | LBS | भागीराम / धरमीन | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3788 | 81.5278 | 1
69 | LBS | बंशीलाल / बैशाखू | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3904 | 81.528 | 1
70 | LBS | बंशीलाल / बैशाखू | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3902 | 81.5282 | 1
71 | LBS | बिसराम / बैशाखू | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3898 | 81.5273 | 1
72 | LBS | अभिराम / दुकालू | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3784 | 81.5289 | 1
73 | LBS | रामप्रसाद / फागुराम | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3791 | 81.5293 | 1
74 | LBS | प्रेमबती / जग्गुराम | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3791 | 81.5283 | 1
75 | LBS | श्यामलाल / कवलसिंह | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3858 | 81.525 | 1
76 | LBS | जागेश्वर / रतिराम | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3904 | 81.528 | 1
77 | LBS | मोहन/झिटकू | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3776 | 81.5252 | 1
78 | LBS | भागी / धरमसिंह | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3759 | 81.5259 | 1
79 | LBS | देवकुवर मंडावी | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3931 | 81.5344 | 1
80 | LBS | देवकुवर मंडावी | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3931 | 81.534 | 1
81 | LBS | देवकुवर मंडावी | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3931 | 81.5337 | 1
82 | Gabion | बिसराम / बैशाखू | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3898 | 81.5273 | 1
83 | Gabion | अभिराम / दुकालू | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3896 | 81.5278 | 1
84 | Trench | जंगलीराम / मोहपाल | 1 | 0.09 | 0.097 | 0.088 | 50 | 0.094 | 20.3779 | 81.5276 | 1
Community Work
85 | Desilting | Common Land | 1 | 60X60X2 | 13.81 | 12.7494 | 7244 | 11.55 | 20.3944 | 81.5348 | 8
86 | Desilting | Common Land | 1 | 60X75X2 | 17.087 | 15.6992 | 8920 | 14.49 | 20.3794 | 81.5187 | 12
86 | Desilting | Common Land | 1 | 60X75X2 | 17.087 | 15.6992 | 8920 | 14.49 | 20.3906 | 81.5229 | 12
87 | Desilting | Common Land | 1 | 45X45X2 | 9.16 | 8.4304 | 4790 | 6.41 | 20.3943 | 81.5348 | 10
88 | Desilting | Common Land | 1 | 30X45X2 | 5.94 | 5.4384 | 3090 | 4.22 | 20.3862 | 81.5204 | 8
Total |  |  | 89 |  | 169.129 | 157.0717 | 86585.8 | 208.61 |  |  | 134
355
356
357
358
359
360
361
362
363
364
365
366
367

## Nrega
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Charbhatti | As on 18-07-2020
I Job Card
Total No. of JobCards issued | 263
Total No. of Workers | 615
Total No. of Active Job Cards | 244
Total No. of Active Workers | 448
(i)SC worker against active workers[%] | 9.38
(ii)ST worker against active workers[%] | 86.16
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 4363 | 11319 | 16247 | 9044 | 6168
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 6.74 | 7.77 | 9.06 | 6.44 | 8.88
ST persondays % as of total persondays | 88.88 | 88.31 | 87.51 | 90.97 | 88.39
Women Persondays out of Total (%) | 39.35 | 48.39 | 41.85 | 42.9 | 36.46
Average days of employment provided per Household | 24.79 | 59.57 | 73.52 | 45.22 | 27.78
Average Wage rate per day per person(Rs.) | 188.18 | 175.89 | 173.66 | 172 | 167
Total No of HHs completed 100 Days of Wage Employment | 0 | 21 | 64 | 9 | 2
Total Households Worked | 176 | 190 | 221 | 200 | 222
Total Individuals Worked | 214 | 285 | 355 | 287 | 468
Differently abled persons worked | 0 | 0 | 0 | 0 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 58 | 71 | 58 | 58 | 283
Number of Ongoing Works | 46 | 56 | 36 | 20 | 38
Number of Completed Works | 12 | 15 | 22 | 38 | 245
% of NRM Expenditure(Public + Individual) | 84.41 | 39.07 | 71.97 | 83.36 | 22.21
% of Category B Works | 91.38 | 94.37 | 87.93 | 55.17 | 17.67
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 11.44 | 26.61 | 33.42 | 15.17 | 19.15
Wages(Rs. In Lakhs) | 8.73 | 22.45 | 26.32 | 14.36 | 9.17
Material and skilled Wages(Rs. In Lakhs) | 2.51 | 3.61 | 6.51 | 0.32 | 9.53
Material(%) | 22.34 | 13.85 | 19.82 | 2.2 | 50.96
Total Adm Expenditure (Rs. in Lakhs.) | 0.2 | 0.55 | 0.59 | 0.49 | 0.44
Admin Exp(%) | 1.75 | 2.07 | 1.77 | 3.23 | 2.3
Average Cost Per Day Per Person(In Rs.) | 239.5 | 184.13 | 217.33 | 180.86 | 428.81
% of Total Expenditure through EFMS | 100 | 100 | 99.97 | 99.92 | 100
% payments gererated within 15 days | 100 | 98.44 | 94.14 | 100 | 14.04