## edpr
e DPR of Kanhanpuri GP, Block Narharpur , Dist kanker Chhattisgarh
A | Back ground profile
| Micro Watershed code |  | 4G2G6F4a, 4G2G6F4c, 4G2G6F4i
| District |  | Kanker
| Block |  | Narharpur
| Gram Panchayat |  | Kanhanpuri
| Villages Covered |  | Kanhanpuri
B | PHYSIOGRAPHIC PROFILE
| Total Area (Ha) |  | 870.64
| Rainfall (mm) |  | 1200
| Soil type |  | Sandy Loam
| Average Slope |  | 2%-16%
| Details of Tributaries |  | Mahandi | 2000 m | Flows whole year
C | DEMOGRAPHIC PROFILE
| Total Population |  | 1322
| Total HouseHolds |  | 253
| ST Population |  | 903
| SC Population |  | 112
D | MGNREGA Status
| NREGA Job card holders |  | 288
| Person days per year (average of last 3 years) |  | 19070
| Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) |  | 85
| Total annual Exp(Rs. in Lakhs.)(average of last 3 years) |  | 24.69
| % of NRM Expenditure(Public + Individual) (average of last 3 years) |  | 81.52
E | LAND USE LAND COVER
| Mono cropped (Ha) |  | 592.47
| Multi cropped (Ha) |  | 12.48
| Current fallow(Ha) |  | 57.44
| Forest /Plantation (Ha) |  | 99.26
| Waste land (Ha) |  | 6.12
| Impounded Waterbody (Ha) |  | 3
| Others (Ha) |  | 39.87
F | LAND CLASSIFICATION
| Forest (Ha) |  | 99.26
| Upland (Ha) |  | 286.16
| Medium land (Ha) |  | 220.56
| Low Land (Ha) |  | 264.66
| River Stream Length (m) |  | 2000 m
G | Existing Water sources/ Structures
| Water harvesting Ponds |  | 20 Nos | 6.14 Ha-m
| Borewells |  | 62
| Open wells |  | 9
H | Livelihood profile
| Agriculture |  | 87%
| Off Farm Activities |  | 10%
| Wages, labour |  | 75%
| Business |  | 11%
| Service/ job |  | 7%
I | WATER BUDGET
| Total Water Requirement (Ham) |  | 51.71 | (Considering 50% Water requirement will be meet by Rainfall)
| Total Water Available (Ham) |  | 6.14
| Water Resource to be created (Ham) |  | 45.57
| Water Resourse Planned ( Ha M) |  | 24.96
| % of Water requirment fulfilled though MWS |  | 54.77%
J | EXPECTED OUTCOME
| Increase in Cropping area (in Ha) |  | 132.97 |  | 101.148
| Increase in Irrigated area (in Ha) |  | 101.148
| Income Enhancement (INR 50000 per annum as additional income) |  | 50 HH
Sr No. | Type of intervention | Name of the Benificiary | No. | Dimension | Estimated cost (lakh) | Estimated labour cost in lakh | Persondays Projected | Treated area |  |  | Targeted HH
1 | Farmpond | चिंता राम नेताम / धनवा | 1 | 60X60X3 | 13.81 | 12.75 | 7245 | 16.42 | 20.3131 | 81.5726 | 1
2 | Farmpond | तिहारू कुंजाम / सिन्धु कुंजाम | 1 | 45X45X3 | 7.861 | 7.155 | 4285 | 8.95 | 20.3283 | 81.5857 | 1
3 | Farmpond | कन्हैया / बालसिंग | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3039 | 81.5837 | 1
4 | Farmpond | रजनी / बरातू राम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3066 | 81.574 | 1
5 | Farmpond | सीताराम / श्रीराम रामटेके | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3154 | 81.5831 | 1
6 | Farmpond | उरेश नेताम / मन्हेर नेताम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3259 | 81.5957 | 1
7 | Farmpond | तिजिया चक्रधारी | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.319 | 81.5796 | 1
8 | Farmpond | देवप्रसाद चक्रधारी / बरातु | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3186 | 81.5781 | 1
9 | Farmpond | रामप्रसाद यादव / बलीराम यादव | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3076 | 81.582 | 1
10 | Farmpond | सुमन राम नेताम / परऊ राम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3058 | 81.5734 | 1
11 | Farmpond | खुम्मन सिंह पोया | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3044 | 81.5819 | 1
12 | Farmpond | मेहत्तर उसेंडी / मथिराम | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3197 | 81.5754 | 1
13 | Farmpond | सीताराम / श्रीराम रामटेके | 1 | 30X30X3 | 3.261 | 2.963 | 1775 | 3.73 | 20.3155 | 81.5836 | 1
14 | Farmpond | राम/ भवरू | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3182 | 81.5787 | 1
15 | Farmpond | सुभऊ राम / चरण | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3289 | 81.5878 | 1
16 | Farmpond | देवेन्द्र कुमार / मनीराम भास्कर | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3298 | 81.5898 | 1
17 | Farmpond | मंशा राम / हटई राम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3131 | 81.5797 | 1
18 | Farmpond | अगनू सलाम / बोडरा | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.33 | 81.5895 | 1
19 | Farmpond | रामलाल पोया / सतऊ | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3163 | 81.5852 | 1
20 | Farmpond | कुंवरबती/ नरसिंह सलाम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3296 | 81.5894 | 1
21 | Farmpond | मंगल यादव / कन्हैया यादव | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.329 | 81.5894 | 1
22 | Farmpond | छबिलाल कुंजाम / रूपराय कुंजाम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3189 | 81.5809 | 1
23 | Farmpond | मनेश कुमार पोया / रामसिंह | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3059 | 81.5807 | 1
24 | Farmpond | भूपेंद्र प्रयाग / बुधराम प्रयाग | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3101 | 81.5903 | 1
25 | Farmpond | जल सिंह / शिवनाथ | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3064 | 81.5802 | 1
26 | Farmpond | मंगली बाई / हीरऊ राम नेताम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3272 | 81.5963 | 1
27 | Farmpond | भावसिंग सलाम / जगदेव सलाम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3173 | 81.5912 | 1
28 | Farmpond | सुरेश कुमार सुरोजिया / बाला राम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3286 | 81.5856 | 1
29 | Farmpond | जालम सिंह उसेंडी / मथीराम उसेंडी | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.317 | 81.5809 | 1
30 | Farmpond | शिवनाथ सलाम / विक्रम | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3243 | 81.5852 | 1
31 | Farmpond | घुरऊ राम पोया / गुहे सिंह | 1 | 23X23X3 | 1.742 | 1.58 | 908 | 2.06 | 20.3146 | 81.5975 | 1
32 | Farmpond | कमलेश / आजू राम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3212 | 81.5827 | 1
33 | Farmpond | तिहारू / नाथू | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.328 | 81.5962 | 1
34 | Farmpond | दुकालो बाई / सहदेव नेताम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3298 | 81.5897 | 1
35 | Farmpond | हलाल / फुलसिंग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3294 | 81.5896 | 1
36 | Farmpond | सुकंतीन / जोगुराम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.316 | 81.5943 | 1
37 | Farmpond | धर्मिन मेश्राम / प्रेमसिंग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3117 | 81.5739 | 1
38 | Farmpond | विश्राम कोमरा / सुकराम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3234 | 81.593 | 1
39 | Farmpond | भगवंतीन / सुकराम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3263 | 81.5927 | 1
40 | Farmpond | रैनसिंग / रामदयाल | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3248 | 81.587 | 1
41 | Farmpond | कला बाई / सुनहेर | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.329 | 81.5897 | 1
42 | Farmpond | रूपराय कुंजाम / बहादुर | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3182 | 81.5812 | 1
43 | Farmpond | जल सिंह / शिवनाथ | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3064 | 81.5801 | 1
44 | Farmpond | कमल नेताम / फुलसिंग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3126 | 81.5894 | 1
45 | Farmpond | ज्ञान कुमार मांडवी / इतवारू | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3208 | 81.598 | 1
46 | Farmpond | बीसऊ राम सलाम / हलाल सलाम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3159 | 81.5962 | 1
47 | Farmpond | कला बाई / सुनहेर | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3289 | 81.5895 | 1
48 | Farmpond | कमल सिंह / फुलसिंग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3288 | 81.5857 | 1
49 | Farmpond | घसिया कुंजाम / झिटकू राम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3289 | 81.5853 | 1
50 | Farmpond | दिवाकर सलाम / धरम सिंग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3171 | 81.5784 | 1
51 | Farmpond | वीरेंद्र प्रयाग / पी . आर . प्रयाग | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3082 | 81.5801 | 1
52 | Farmpond | मुंशी राम सलाम / बुहरेल सलाम | 1 | 15X15X3 | 0.661 | 0.595 | 356 | 0.76 | 20.3203 | 81.5907 | 1
53 | Land levelling | रजनी / बरातू राम | 1 | 0.57 | 0.5415 | 0.46027 | 262.2 | 0.57 | 20.3159 | 81.5817 | 1
54 | Land levelling | तिहारू / नाथू | 1 | 0.66 | 0.627 | 0.53295 | 303.6 | 0.66 | 20.3276 | 81.5967 | 1
55 | Land levelling | देवेन्द्र कुमार / मनीराम भास्कर | 1 | 0.65 | 0.6175 | 0.52487 | 299 | 0.65 | 20.3297 | 81.5898 | 1
56 | Land levelling | मंशा राम / हटई राम | 1 | 0.36 | 0.342 | 0.2907 | 165.6 | 0.36 | 20.3131 | 81.5797 | 1
57 | Land levelling | दुकालो बाई / सहदेव नेताम | 1 | 0.73 | 0.6935 | 0.58947 | 335.8 | 0.73 | 20.33 | 81.5898 | 1
58 | Land levelling | हलाल / फुलसिंग | 1 | 0.79 | 0.7505 | 0.63793 | 363.4 | 0.79 | 20.3297 | 81.5896 | 1
59 | Land levelling | नाड़ीराम / मयाराम | 1 | 0.09 | 0.0855 | 0.072675 | 41.4 | 0.09 | 20.306 | 81.577 | 1
60 | Land levelling | रामलाल पोया / सतऊ | 1 | 0.42 | 0.399 | 0.33915 | 193.2 | 0.42 | 20.3056 | 81.5803 | 1
61 | Land levelling | सुकंतीन / जोगुराम | 1 | 2.53 | 2.4035 | 2.043 | 1163.8 | 2.53 | 20.3157 | 81.595 | 1
62 | Land levelling | श्याम बाई कुंजाम / प्रेमसिंग | 1 | 0.5 | 0.475 | 0.40375 | 230 | 0.5 | 20.3292 | 81.5897 | 1
63 | Land levelling | धर्मिन मेश्राम / प्रेमसिंग | 1 | 0.38 | 0.361 | 0.30685 | 174.8 | 0.38 | 20.3118 | 81.5737 | 1
64 | Land levelling | विश्राम कोमरा / सुकराम | 1 | 0.93 | 0.8835 | 0.75098 | 427.8 | 0.93 | 20.3233 | 81.5931 | 1
65 | Land levelling | भगवंतीन / सुकराम | 1 | 0.61 | 0.5795 | 0.49257 | 280.6 | 0.61 | 20.3262 | 81.5926 | 1
66 | Land levelling | रैनसिंग / रामदयाल | 1 | 0.42 | 0.399 | 0.33915 | 193.2 | 0.42 | 20.325 | 81.5868 | 1
67 | Land levelling | शिवनाथ सलाम / विक्रम | 1 | 0.48 | 0.456 | 0.3876 | 220.8 | 0.48 | 20.3236 | 81.5901 | 1
68 | Land levelling | देवप्रसाद चक्रधारी / बरातु | 1 | 1.45 | 1.3775 | 1.1709 | 667 | 1.45 | 20.3189 | 81.5781 | 1
69 | Land levelling | रूपराय कुंजाम / बहादुर | 1 | 1.04 | 0.988 | 0.8398 | 478.4 | 1.04 | 20.3187 | 81.5809 | 1
70 | Land levelling | छबिलाल कुंजाम / रूपराय कुंजाम | 1 | 1.04 | 0.988 | 0.8398 | 478.4 | 1.04 | 20.3189 | 81.5809 | 1
71 | Land levelling | तुलसी राम / घसिया राम मांडवी | 1 | 1.04 | 0.988 | 0.8398 | 478.4 | 1.04 | 20.3241 | 81.5938 | 1
72 | Land levelling | उरेश नेताम / मन्हेर नेताम | 1 | 0.9 | 0.855 | 0.72675 | 414 | 0.9 | 20.3259 | 81.596 | 1
73 | Land levelling | रुखमणि प्रयाग / बुधराम प्रयाग | 1 | 0.72 | 0.684 | 0.5814 | 331.2 | 0.72 | 20.3153 | 81.594 | 1
74 | Land levelling | मनेश कुमार पोया / रामसिंह | 1 | 0.65 | 0.6175 | 0.52487 | 299 | 0.65 | 20.3061 | 81.5805 | 1
75 | Land levelling | शिवदयाल मरकाम / रामुराम | 1 | 0.5 | 0.475 | 0.40375 | 230 | 0.5 | 20.3279 | 81.5887 | 1
76 | Land levelling | मंगली बाई / हीरऊ राम नेताम | 1 | 0.12 | 0.114 | 0.0969 | 55.2 | 0.12 | 20.3273 | 81.5973 | 1
77 | Land levelling | बल्लू राम सलाम / सोमनी राम | 1 | 0.34 | 0.323 | 0.27455 | 156.4 | 0.34 | 20.3204 | 81.5981 | 1
78 | Land levelling | भावसिंग सलाम / जगदेव सलाम | 1 | 0.16 | 0.152 | 0.1292 | 73.6 | 0.16 | 20.3253 | 81.5923 | 1
79 | Land levelling | शिवनाथ सलाम / विक्रम | 1 | 0.3 | 0.285 | 0.24225 | 138 | 0.3 | 20.3175 | 81.5942 | 1
80 | Land levelling | बीसऊ राम सलाम / हलाल सलाम | 1 | 1.87 | 1.7765 | 1.51 | 860.2 | 1.87 | 20.3169 | 81.5954 | 1
81 | Land levelling | कला बाई / सुनहेर | 1 | 0.5 | 0.475 | 0.40375 | 230 | 0.5 | 20.3288 | 81.5894 | 1
82 | Land levelling | तिहारू कुंजाम / सिन्धु कुंजाम | 1 | 1.55 | 1.4725 | 1.2516 | 713 | 1.55 | 20.328 | 81.5859 | 1
83 | Land levelling | नागेश्वर कुंजाम / भवरू | 1 | 0.4 | 0.38 | 0.323 | 184 | 0.4 | 20.3147 | 81.5914 | 1
84 | Land levelling | सुरेश कुमार सुरोजिया / बाला राम | 1 | 0.21 | 0.1995 | 0.16958 | 96.6 | 0.21 | 20.328 | 81.586 | 1
85 | Land levelling | सुरेश कुमार सुरोजिया / बाला राम | 1 | 0.17 | 0.1615 | 0.13728 | 78.2 | 0.17 | 20.3282 | 81.5861 | 1
86 | Land levelling | घसिया कुंजाम / झिटकू राम | 1 | 0.7 | 0.665 | 0.56525 | 322 | 0.7 | 20.3289 | 81.5851 | 1
87 | Land levelling | सुमन राम नेताम / परऊ राम | 1 | 3.07 | 2.9165 | 2.479 | 1412.2 | 3.07 | 20.3169 | 81.5783 | 1
88 | Land levelling | दिवाकर सलाम / धरम सिंग | 1 | 0.2 | 0.19 | 0.1615 | 92 | 0.2 | 20.3172 | 81.5782 | 1
89 | Land levelling | जालम सिंह उसेंडी / मथीराम उसेंडी | 1 | 0.36 | 0.342 | 0.2907 | 165.6 | 0.36 | 20.3171 | 81.5812 | 1
90 | Land levelling | मेहत्तर उसेंडी / मथिराम | 1 | 0.3 | 0.285 | 0.24225 | 138 | 0.3 | 20.3168 | 81.5788 | 1
91 | Land levelling | मेहत्तर उसेंडी / मथिराम | 1 | 0.7 | 0.665 | 0.56525 | 322 | 0.7 | 20.3198 | 81.5751 | 1
92 | Land levelling | सीताराम / श्रीराम रामटेके | 1 | 2 | 1.9 | 1.615 | 920 | 2 | 20.3151 | 81.5819 | 1
93 | Land levelling | घुरऊ राम पोया / गुहे सिंह | 1 | 0.48 | 0.456 | 0.3876 | 220.8 | 0.48 | 20.3146 | 81.5976 | 1
94 | Land levelling | मुंशी राम सलाम / बुहरेल सलाम | 1 | 0.49 | 0.4655 | 0.39567 | 225.4 | 0.49 | 20.3203 | 81.5907 | 1
95 | Land levelling | जगेसिंग सलाम / शोभाराम सलाम | 1 | 0.45 | 0.4275 | 0.36338 | 207 | 0.45 | 20.3142 | 81.5925 | 1
96 | LBS | राम/ भवरू | 1 | 3X1 | 0.146 | 0.112 | 17 | 1 | 20.3182 | 81.5787 | 1
97 | LBS | कमलेश / आजू राम | 1 | 3X1 | 0.146 | 0.112 | 17 | 1 | 20.3212 | 81.5827 | 1
98 | LBS | सुभऊ राम / चरण | 1 | 3X1 | 0.146 | 0.112 | 17 | 1 | 20.3289 | 81.5878 | 1
Community Work
99 | Desilting | Common Land | 1 | 60X60X2 | 9.3 | 8.56 | 4864 | 11.55 | 20.3021 | 81.5843 | 1
99 | Desilting | Common Land | 1 | 60X60X2 | 9.3 | 8.56 | 4864 | 11.55 | 20.3006 | 81.5844 | 1
99 | Desilting | Common Land | 1 | 60X60X2 | 9.3 | 8.56 | 4864 | 11.55 | 20.3109 | 81.5761 | 1
100 | Desilting | Common Land | 1 | 60X75X2 | 11.64 | 10.73 | 6097 | 14.49 | 20.3159 | 81.5807 | 1
101 | LBS | Common Land | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3293 | 81.5894 | 1
101 | LBS | Common Land | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3292 | 81.5894 | 1
101 | LBS | Common Land | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3292 | 81.5894 | 1
101 | LBS | Common Land | 1 | 3X1 | 0.146 | 0.015 | 17 | 1 | 20.3297 | 81.5895 | 1
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3302 | 81.5902 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.33 | 81.5901 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3299 | 81.5901 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3298 | 81.5902 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3297 | 81.59 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3296 | 81.5899 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3295 | 81.5898 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3293 | 81.5897 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3293 | 81.5899 | 0
102 | Gabian | Common Land | 1 | 5X1 | 0.51 | 0.143 | 82 | 10 | 20.3291 | 81.5895 | 0
Total |  |  | 115 |  | 178.1695 | 157.2287 | 91062.8 | 307.41 |  |  | 106

## Narega
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Kanhanpuri | As on 18-07-2020
I Job Card
Total No. of JobCards issued | 288
Total No. of Workers | 595
Total No. of Active Job Cards | 275
Total No. of Active Workers | 535
(i)SC worker against active workers[%] | 6.54
(ii)ST worker against active workers[%] | 69.16
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 8141 | 19820 | 19217 | 18174 | 18942
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 4.62 | 6.28 | 5.58 | 4.96 | 5.85
ST persondays % as of total persondays | 70.43 | 69.43 | 67.86 | 68.23 | 70.19
Women Persondays out of Total (%) | 53.89 | 53.88 | 51.57 | 55.44 | 52.51
Average days of employment provided per Household | 38.22 | 82.58 | 84.66 | 73.28 | 76.38
Average Wage rate per day per person(Rs.) | 190 | 175.93 | 168.98 | 171.99 | 167
Total No of HHs completed 100 Days of Wage Employment | 2 | 92 | 90 | 73 | 84
Total Households Worked | 213 | 240 | 227 | 248 | 248
Total Individuals Worked | 331 | 390 | 377 | 452 | 459
Differently abled persons worked | 0 | 0 | 0 | 2 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 29 | 56 | 51 | 78 | 82
Number of Ongoing Works | 28 | 30 | 29 | 14 | 47
Number of Completed Works | 1 | 26 | 22 | 64 | 35
% of NRM Expenditure(Public + Individual) | 97.68 | 90.15 | 93.18 | 61.23 | 84.56
% of Category B Works | 31.03 | 46.43 | 64.71 | 52.56 | 46.34
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 13.19 | 31.35 | 27.83 | 14.9 | 14.05
Wages(Rs. In Lakhs) | 12.33 | 24.67 | 26.22 | 10.81 | 10.76
Material and skilled Wages(Rs. In Lakhs) | 0.62 | 6.02 | 0.91 | 3.61 | 2.93
Material(%) | 4.8 | 19.61 | 3.35 | 25.02 | 21.39
Total Adm Expenditure (Rs. in Lakhs.) | 0.24 | 0.66 | 0.71 | 0.49 | 0.36
Admin Exp(%) | 1.82 | 2.11 | 2.54 | 3.29 | 2.56
Average Cost Per Day Per Person(In Rs.) | 200.45 | 214.59 | 176.7 | 441.59 | 201.88
% of Total Expenditure through EFMS | 100 | 99.82 | 99.73 | 99.83 | 100
% payments gererated within 15 days | 100 | 93.81 | 91.07 | 90.59 | 28.99