## Badedewada
e DPR of Badedewada GP, Bakawand, Chhattisgarh
| A | Back ground profile
|  | Micro Watershed code | 4E2F5C1a
|  | District | Bastar
|  | Block | Bakawand
|  | Gram Panchayat | Badedewada
|  | Villages Covered | Badedewada
| B | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) | 701.18
|  | Rainfall (mm) | 1140
|  | Soil type | Sandy loam, clay
|  | Average Slope | 0-10%
|  | Details of Tributaries | Bakawand | m long | Flows till March
| C | DEMOGRAPHIC PROFILE
|  | Total Population | 2019
|  | Total HouseHolds | 479
|  | ST Population | 1296
|  | SC Population | 0
| D | MGNREGA Status
|  | NREGA Job card holders | 457
|  | Person days per year (average of last 3 years) | 9435
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 31.3
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 17.35
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 66.35
| E | LAND USE LAND COVER
|  | Mono cropped (Ha) | 499.5
|  | Multi cropped (Ha) | 5.67
|  | Current fallow(Ha) | 39.16
Forest /Plantation (Ha)
|  | Waste land (Ha) | 0
Impounded Waterbody (Ha)
Others (Ha)
| F | LAND CLASSIFICATION
|  | Forest (Ha) | 52.92
Upland (Ha)
Medium land (Ha)
Low Land (Ha)
River Stream Length (m)
| G | Existing Water sources/ Structures
|  | Water harvesting Ponds | 09 nos | Ham
|  | Borewells | 03 nos
|  | Open wells | 25 nos
| H | Livelihood profile
|  | Agriculture | 54%
|  | Off Farm Activities | 7%
|  | Wages, labour | 34%
|  | Business | 3%
|  | Service/ job | 2%
| I | WATER BUDGET
|  | Total Water Requirement (Ham) | 934.63
|  | Total Water Available (Ham) | 17.04
|  | Water Resource to be created (Ham) | 450.45
| J | EXPECTED OUTCOME
Increase in Cropping area (in Ha)
Increase in Irrigated area (in Ha)
Income Enhancement (INR 50000 per annum as additional income)
| Sr No. | Name of the Beneficiary | Type of intervention | No. | Dimension | Estimated cost (lakh) | Estimated labour cost (lakh) | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
| 1 | Ishwar/Raghunath | Bunding | 1 | 0.39 | 0.388 | 0.388 | 204 | 0.39 | 19.3794 | 82.1287 | 1
| 2 | Lalit/Dashmu | Bunding | 1 | 0.26 | 0.16 | 0.16 | 84 | 0.26 | 19.3688 | 82.1158 | 1
| 3 | Ishwar/Gheena | Bunding | 1 | 0.3 | 0.214 | 0.214 | 113 | 0.3 | 19.3768 | 82.1203 | 1
| 4 | Harichand/Lachhin | Bunding | 1 | 0.64 | 0.389 | 0.389 | 205 | 0.64 | 19.3813 | 82.1158 | 1
| 5 | Mangalu/Somaru | 30 x 40 | 1 | 0.69 | 1.477 | 0.925 | 487 | 0.69 | 19.3735 | 82.1181 | 1
| 6 | Manglu/Budhu | 30 x 40 | 1 | 0.41 | 0.877 | 0.549 | 289 | 0.41 | 19.3732 | 82.1178 | 1
| 7 | Sadan/Laikhan | Bunding | 1 | 0.9 | 0.544 | 0.544 | 286 | 0.9 | 19.3769 | 82.1209 | 1
| 8 | Jhino/Badar | Bunding | 1 | 0.62 | 0.476 | 0.476 | 251 | 0.62 | 19.376 | 82.1209 | 1
| 9 | Rajuram/Ghanshyam | Bunding | 1 | 0.41 | 0.307 | 0.307 | 162 | 0.41 | 19.3749 | 82.1167 | 1
| 10 | Piluram/Ghanshyam | 30 x 40 | 1 | 0.28 | 0.599 | 0.375 | 197 | 0.28 | 19.374700° | 82.116544° | 1
| 11 | Dausingh/Arjun | Bunding | 1 | 0.25 | 0.181 | 0.181 | 95 | 0.25 | 19.369 | 82.1189 | 1
| 12 | Neelkanth/Burunda (Govt. Land) | 30 x 40 | 1 | 0.53 | 1.134 | 0.71 | 374 | 0.53 | 19.372842° | 82.117551° | 1
| 13 | Baleshwar/Panchkoudi | Bunding | 1 | 1.2 | 0.612 | 0.612 | 322 | 1.2 | 19.3718 | 82.1314 | 1
| 14 | Harichand/Narayan | Bunding | 1 | 0.61 | 0.551 | 0.551 | 290 | 0.61 | 19.3731 | 82.1319 | 1
| 15 | Nidhi/Ayatu | Bunding | 1 | 0.6 | 0.432 | 0.432 | 227 | 0.6 | 19.3711 | 82.1206 | 1
| 16 | Dhanurjay/Baliram | Bunding | 1 | 2.56 | 0.663 | 0.663 | 349 | 2.56 | 19.382 | 82.1351 | 1
| 17 | Kamlu/Puran | Bunding | 1 | 2.43 | 0.629 | 0.629 | 331 | 2.43 | 19.3781 | 82.1285 | 1
| 18 | Chandru/Hanu | Bunding | 1 | 3.01 | 0.665 | 0.665 | 350 | 3.01 | 19.3798 | 82.1294 | 1
| 19 | Subalan/Mangal | Bunding | 1 | 0.4 | 0.382 | 0.382 | 201 | 0.4 | 19.3801 | 82.1292 | 1
| 20 | Tularam/Gourichand | 30 x 40 | 1 | 0.51 | 1.091 | 0.683 | 359 | 0.51 | 19.374147° | 82.116374° | 1
| 21 | Motiram/Govind | Bunding | 1 | 0.89 | 0.529 | 0.529 | 278 | 0.89 | 19.3689 | 82.1191 | 1
| 22 | Dashru/Bhujabal | Bunding | 1 | 4.84 | 0.709 | 0.709 | 373 | 4.84 | 19.3814 | 82.1158 | 1
| 23 | Manku/Boti | Bunding | 1 | 0.59 | 0.434 | 0.434 | 228 | 0.59 | 19.3708 | 82.1207 | 1
| 24 | Lachhan/Ghano | Bunding | 1 | 0.37 | 0.456 | 0.456 | 240 | 0.37 | 19.381 | 82.1156 | 1
| 25 | Jhinbandhu/Bali | Bunding | 1 | 0.59 | 0.467 | 0.467 | 246 | 0.59 | 19.3705 | 82.1188 | 1
| 26 | Sonadai/Shankar | Bunding | 1 | 0.35 | 0.377 | 0.377 | 198 | 0.35 | 19.3769 | 82.1082 | 1
| 27 | Parvati/Ramo | Bunding | 1 | 0.35 | 0.456 | 0.456 | 240 | 0.35 | 19.3824 | 82.1167 | 1
| 28 | Farshuram/Manbodh | Bunding | 1 | 3.82 | 0.64 | 0.64 | 337 | 3.82 | 19.3683 | 82.1158 | 1
| 29 | Shankar/Dhanurjay | Bunding | 1 | 0.27 | 0.229 | 0.229 | 121 | 0.27 | 19.3688 | 82.1174 | 1
| 30 | Umesh/Mandhu | Bunding | 1 | 0.26 | 0.188 | 0.188 | 99 | 0.26 | 19.3687 | 82.1173 | 1
| 31 | Murha/Loknath | 30 x 40 | 1 | 0.95 | 2.033 | 1.273 | 670 | 0.95 | 19.374204° | 82.117747° | 1
| 32 | Chaitu/Sonsay | Bunding | 1 | 1.76 | 0.69 | 0.69 | 363 | 1.76 | 19.384546° | 82.114604° | 1
| 33 | Dayaram/Motiram | 30 x 40 | 1 | 0.93 | 1.99 | 1.246 | 656 | 0.93 | 19.3733 | 82.1177 | 1
| 34 | Foolsingh/Ghina | Bunding | 1 | 0.3 | 0.391 | 0.391 | 206 | 0.3 | 19.384565° | 82.117349° | 1
| 35 | Baldev/Dasmat | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 11.45 | 19.3736 | 82.1272 | 2
| 36 | Jaysingh/Lachim | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 11.45 | 19.3828 | 82.1166 | 2
| 37 | Sadan/Laikhan | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 4.58 | 19.3768 | 82.121 | 2
| 38 | Chingadu/Jhitaru | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 11.45 | 19.3682 | 82.1088 | 2
| 39 | Sonu/Soman | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 11.45 | 19.3701 | 82.1091 | 2
| 40 | Umesh/Mandhu | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3715 | 82.1304 | 3
| 41 | Ratiram/Raysingh | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3711 | 82.1323 | 3
| 42 | Nidhi/Haribandhu | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3595 | 82.0933 | 3
| 43 | Baliram/Soma | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3801 | 82.1233 | 3
| 44 | Aashamn/Somaru | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3764 | 82.1156 | 3
| 45 | Gurbandhu/Faganu | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.377 | 82.1128 | 3
| 46 | Dhanurjay/Baliram | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3669 | 82.1271 | 3
| 47 | Farsuram/Manbodh | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3725 | 82.1283 | 3
| 48 | Dalimchand/Pankoudiya | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3636 | 82.1119 | 3
| 49 | Baliram/Mahadev | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3635 | 82.1129 | 3
| 50 | Lakhiram/Budharam | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3661 | 82.113 | 3
| 51 | Sonadai/Kawalsay | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3669 | 82.1112 | 3
| 52 | Dashmat/Salindhar | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3689 | 82.1099 | 3
| 53 | Baliram/Somaru | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3584 | 82.0936 | 3
| 54 | Pitam/Baichand | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3747 | 82.1147 | 3
| 55 | Tularam/Gourichand | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.375 | 82.1142 | 3
| 56 | Mohan/Bhagat | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3679 | 82.1184 | 3
| 57 | Kamdev/Burunda | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3774 | 82.1213 | 3
| 58 | Farsuram/Suku | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3725 | 82.1283 | 3
| 59 | Foolsingh/Asatu | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3718 | 82.1294 | 3
| 60 | Kuldhar/Budhu | Farm Pond | 1 | 30x30x3 | 2.74 | 2.74 | 1443 | 3.73 | 19.3678 | 82.1074 | 3
| 61 | Lachhandai/Sada | Bunding | 1 | 3.29 | 4.17 | 3.29 | 1732 | 3.29 | 19.3702 | 82.1194 | 1
| 62 | Dongari Paich | Plantation | 1 | 12 | 0.635 | 0.5 | 2632 | 0.4 | 19.3775 | 82.1345 | 15
| 63 | Mari Paich | Plantation | 1 | 2.27 | 0.635 | 0.5 | 2632 | 0.56 | 19.3816 | 82.1313 | 10
| 64 | Gas Godam Paich | Plantation | 1 | 30 | 0.635 | 0.5 | 2632 | 0.68 | 19.3778 | 82.108 | 20
| 65 | Mahara Para | Pond | 1 | 50x50x3 | 82.05 | 82.05 | 4318 | 11.19 | 19.3819 | 82.1278 | 15
| 66 | Maridenga Ke Pass | Pond | 1 | 50x50x3 | 82.05 | 82.05 | 4318 | 11.19 | 19.3837 | 82.1323 | 15
| 67 | Petfula | Pond | 1 | 50x50x3 | 82.05 | 82.05 | 4318 | 11.19 | 19.3804 | 82.1258 | 20
| 68 | Sonadhar/Mokund | Goatary Shed | 1 | 3.40 m x 2.80 m | 0.51 | 0.1 | 53 | 0 | 19.3779 | 82.1255 | 2
| 69 | Jai Mangal/Lakhapati | Poultry Shed | 1 | 4.25 m x 2.50 m | 0.5 | 0.9 | 47 | 0 | 19.3833 | 82.1162 | 2
| 70 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 3x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3788 | 82.131 | 0
| 71 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 3.3x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3789 | 82.1308 | 0
| 72 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 3.4x1 | 0.1 | 0.1 | 5 | 0.25 | 19.379 | 82.1306 | 0
| 73 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 3.7x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3791 | 82.1305 | 0
| 74 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 3.6x1 | 0.1 | 0.1 | 5 | 0.25 | 19.379 | 82.1305 | 0
| 75 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 3.8x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3791 | 82.1304 | 0
| 76 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 4x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3792 | 82.1303 | 0
| 77 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 4.2x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3791 | 82.1309 | 0
| 78 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 4.4x1 | 0.1 | 0.1 | 5 | 0.25 | 19.3791 | 82.1308 | 0
| 79 | Eardhen Gully Plug | Eardhen Gully Plug | 1 | 4.8x1 | 0.1 | 0.1 | 5 | 0.35 | 19.3792 | 82.1306 | 0
| 80 | Mahara Para | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3776 | 82.1266 | 0
| 81 | Moligudiya Para | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3722 | 82.133 | 0
| 82 | Aanganbadi Kendra Ke Pass | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3751 | 82.128 | 0
| 83 | Hariram/Jhitaru Ghar Ke Pass | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3646 | 82.1104 | 0
| 84 | Primary School Upar Para | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3743 | 82.1273 | 0
| 85 | Sukde/Motiram Ghar Ke Pass | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3842 | 82.1176 | 0
| 86 | Khuda/Jagaro Ghar Ke Pass | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3753 | 82.1254 | 0
| 87 | Ratiram/Raysingh Ghar Ke Pass | Souk Pit | 1 | 2x2x2 | 0.6 | 0.18 | 9 | 0 | 19.3757 | 82.1248 | 0
| 88 | Irrigation Canal (Nuwa munda se kuwa beda Tak) | Irrigation Canal | 1 | 2500x1.5x1 | 4.578 | 4.578 | 2410 | 9 | 19.370751° | 82.118110° | 42
| 89 | WAT (Mari Dongri) | WAT | 1 | 2.27 | 0.153 | 0.153 | 81 | 2 | 19.381144° | 82.132459° | 10
| 90 | WAT (Gothan) | WAT | 1 | 1 | 0.214 | 0.214 | 113 | 1 | 19.378569° | 82.134190° | 10
| 91 | Kataguda Para | Community Pond | 1 | 72x75x3 | 18.36 | 18.36 | 9664 | 25.05 | 19.383772° | 82.115205° | 30
| 92 | Khageswar/Kawalsay | Bunding | 1 | 0.4 |  |  |  | 0.4 | 19.3669 | 82.1102 | 1
| 93 | Bhadar/Budhu | Bunding | 1 | 0.4 |  |  |  | 0.4 | 19.3684 | 82.1083 | 1
| 94 | Jagnath/Baliram | Bunding | 1 | 0.4 |  |  |  | 0.4 | 19.3705 | 82.1188 | 1
| 95 | Lachhandai/Sada | Bunding | 1 | 0.4 |  |  |  | 0.4 | 19.3702 | 82.1194 | 1
| 96 | Bhagtu/Ratan | Farm Pond | 1 | 20 x 20 x3 | 1.1 | 1.1 | 583 | 1.5 | 19.3784 | 82.1267 | 3
| 97 | Dashru/Bhujabal | Farm Pond | 1 | 20 x 20 x3 | 1.1 | 1.1 | 583 | 1.5 | 19.3816 | 82.1154 | 3
| 98 | Laibani/Rajaram | Farm Pond | 1 | 20 x 20 x3 | 1.1 | 1.1 | 583 | 1.5 | 19.3717 | 82.1224 | 3
| 99 | Kushal/Durjan | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 1.27 | 19.3759 | 82.1166 | 2
| 100 | Dasrath/Dhudhru | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 1.27 | 19.3803 | 82.1257 | 2
| 101 | Sundar/Lachhin | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 1.27 | 19.3788 | 82.1248 | 2
| 102 | Fakirchand/Dayasingh | Well | 1 | 5x9 | 2.5 | 1.2 | 632 | 1.27 | 19.3736 | 82.1266 | 2
| 103 | Parwati/Purtam | Farm Pond | 1 | 20 x 20 x3 | 1.1 | 1.1 | 583 | 1.5 | 19.3756 | 82.1164 | 3
| 104 | Irrigation Canal Gandaram khet se danda badi tak | Irrigation Canal | 1 | 1500x1.2x1 | 2.198 | 2.198 | 1156 | 3 | 19.380237° | 82.128765° | 10
| 105 | Chasew Plantation of individual land | Patch Plantation | 1 | 9.00 ha | 33.349 | 2.33 | 1230 | 9 | 19.3709 | 82.118 | 14
| 106 | Guava Plantation of individual land | Patch Plantation | 1 | 9.17 ha | 32.386 | 4.49 | 2392 | 9.17 | 19.3705 | 82.1181 | 13
| 107 | Manglu/Dasmat | 30 x 40 | 1 | 0.4 | 0.856 | 0.536 | 282 | 0.4 | 19.3742 | 82.1179 | 1
| 108 | Hemdhar/Ude | 30 x 40 | 1 | 0.4 | 0.856 | 0.536 | 282 | 0.4 | 19.373 | 82.1167 | 1
| 109 | Mangru/Samnath | Goatary Shed | 1 | 3.40 m x 2.80 m |  |  |  | 0 | 19.3783 | 82.1253 | 1
| 110 | Mayaram/Makund | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.378 | 82.1264 | 1
| 111 | Subalan/Mangal | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.3801 | 82.1292 | 1
| 112 | Samanduram/Samnath | 30 x 40 | 1 | 0.4 | 0.856 | 0.536 | 282 | 0.4 | 19.3738 | 82.1165 | 1
| 113 | Padam/Nada | 30 x 40 | 1 | 0.4 | 0.856 | 0.536 | 282 | 0.4 | 19.3738 | 82.1165 | 1
| 114 | Lakheedhar/Budhram | Farm Pond | 1 | 30x30x3 |  |  |  | 3.73 | 19.3675 | 82.1144 | 3
| 115 | Sampat/jino | Farm Pond | 1 | 30x30x3 |  |  |  | 3.73 | 19.372 | 82.1287 | 3
255 | 116 | Budhabai/Kushal | Fishery Pond | 1 | 50x50x3 |  |  |  | 11.19 | 19.3756 | 82.1164 | 5
| 117 | Aaytu/Somaru | Well | 1 | 5x9 |  |  |  | 1.27 | 19.3772 | 82.1213 | 2
| 118 | Niranjan/Jayro | Well | 1 | 5x9 |  |  |  | 1.27 | 19.3786 | 82.1251 | 2
| 119 | Keshbo/Panchkodiya | Well | 1 | 5x9 |  |  |  | 1.27 | 19.3783 | 82.1252 | 2
| 120 | Shankar/Baliram | Bunding | 1 | 0.4 |  |  |  | 0.4 | 19.364362° | 82.127362° | 1
| 121 | Tularam/Kamo | Bunding | 1 | 0.4 |  |  |  | 0.4 | 19.3746 | 82.1194 | 1
| 122 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.376364° | 82.126063° | 10
| 123 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.376796° | 82.125053° | 10
| 124 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.376027° | 82.125792° | 10
| 125 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.375617° | 82.127237° | 10
| 126 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.375288° | 82.125980° | 10
| 127 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.376145° | 82.124380° | 10
| 128 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.377183° | 82.125978° | 10
| 129 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.374476° | 82.130220° | 10
| 130 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.364383° | 82.109070° | 10
| 131 | Community Nadep compost Tank | Nadep | 1 | 4.20 mx 1.50 m x 1.00 m | 0.0727 | 0.029 | 15 | 0 | 19.363577° | 82.109883° | 10
| 132 | Community Vermi compost Tank | Vermi Tank | 1 | 3.00 mx 1.20 m x 0.75 m | 0.097 | 0.038 | 20 | 0 | 19.365648° | 82.107307° | 10
| 133 | Community Vermi compost Tank | Vermi Tank | 1 | 3.00 mx 1.20 m x 0.75 m | 0.097 | 0.038 | 20 | 0 | 19.364772° | 82.110622° | 10
| 134 | Community Vermi compost Tank | Vermi Tank | 1 | 3.00 mx 1.20 m x 0.75 m | 0.097 | 0.038 | 20 | 0 | 19.374861° | 82.128947° | 10
| 135 | Community Vermi compost Tank | Vermi Tank | 1 | 3.00 mx 1.20 m x 0.75 m | 0.097 | 0.038 | 20 | 0 | 19.374482° | 82.126004° | 10
| 135 | Community Vermi compost Tank | Vermi Tank | 1 | 3.00 mx 1.20 m x 0.75 m | 0.097 | 0.038 | 20 | 0 | 19.375792° | 82.125354° | 10
| 137 | SHG work shed for Community | SHG work shed | 1 | 6.60 m x 4.20 m |  |  |  | 0 | 19.379077° | 82.134570° | 10
| 138 | Community Gothan Works | Pashu Ashray Shed | 1 |  | 6.362 | 2.544 | 1339 | 0 | 19.379152° | 82.133949° | 10
| 139 | Chragah | CPT | 1 | 2000 m x 1.5 m x 0.90 m |  |  |  | 0 | 19.379774° | 82.134810° | 10
| 140 | Chragah | Land Development | 1 | 1.00 ha |  |  |  | 0 | 19.379313° | 82.134853° | 30
| 141 | Community Poultry Shed | Poultry Shed | 1 | 10.60 m x 3.90 m |  |  |  | 0 | 19.379356° | 82.133872° | 10
| 142 | Community Goatary Shed | Goatary Shed | 1 | 3.40 m x 2.80 m |  |  |  | 0 | 19.379285° | 82.133719° | 10
| 143 | Amrit Sarovar (Pond Renovation) | Pond Renovation | 1 | 50 x60 x3 | 9.93 | 9.93 | 5231 | 47.34 | 19.3814 | 82.1267 | 50
| 144 | SHG work shed for Community | SHG work shed | 1 | 6.60 m x 4.20 m |  |  |  | 0 | 19.378953° | 82.134554° | 10
| 145 | Community Pond Renovation (Soutpur Para) | Pond Renovation | 1 | 50 x50x3 | 8.2 | 8.2 | 4318 | 11.19 | 19.3712 | 82.1077 | 20
| 146 | Gothan CPT | CPT | 1 | 500 m x 1.5 m x 0.90 m |  |  |  | 0.85 | 19.378653° | 82.134119° | 10
| 147 | Setlal/Shobha | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.3777 | 82.1265 | 1
| 148 | Meghnath/Budhram | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.3777 | 82.1265 | 1
| 149 | Budanti/Baldas | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.3765 | 82.1274 | 1
| 150 | Govardhan/Raghunath | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.3743 | 82.1306 | 1
| 151 | Budhbari/Dharamdas | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.3743 | 82.1306 | 1
| 152 | Antram/Murha | Goatary Shed | 1 | 3.40 m x 2.80 m |  |  |  | 0 | 19.3743 | 82.1306 | 1
| 153 | Jitendra/Fakischand | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.3742 | 82.1314 | 1
| 154 | Hemdhar/Ude | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.3735 | 82.13 | 1
| 155 | Raghu/Buklu | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.3751 | 82.1277 | 1
| 156 | Prahalad/Ransingh | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.3751 | 82.1277 | 1
| 157 | Jhitru/Laikhan | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.375 | 82.1277 | 1
| 158 | Nidhi/Haribandhu | Goatary Shed | 1 | 3.40 m x 2.80 m |  |  |  | 0 | 19.3749 | 82.1275 | 1
| 159 | Baliram/Bhursu | Poultry Shed | 1 | 4.25 m x 2.50 m |  |  |  | 0 | 19.3749 | 82.1272 | 1
| 160 | Kartik/Mathura | Cattle Shed | 1 | 6.00 m x 4.00 m | 0.727 | 0.29 | 153 | 0 | 19.3745 | 82.1267 | 1
| 161 | Community Vermi compost Tank | Vermi Tank | 1 |  | 3.61 | 0.28 | 138 | 0 | 19.379108° | 82.133982° | 80