## e-DPR
e-DPR of Korandha GP, Block Lundra , District- Surguja, Chhattisgarh
A |  | Back ground profile
|  | Micro Watershed code | 2A5E5c4, 2A5E5c5
|  | District | Surguja
|  | Block | Lundra
|  | Gram Panchayat | Korandha
|  | Villages Covered | Korandha
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) | 931.93
|  | Rainfall (mm) | 1300
|  | Soil type | Sandy loam
|  | Average Slope | 4-9%
|  | Details of Tributaries | Jori nala
C |  | DEMOGRAPHIC PROFILE
|  | Total Population | 1412
|  | Total HouseHolds | 352
|  | ST Population | 970
|  | SC Population | 90
D |  | MGNREGA Status
|  | NREGA Job card holders | 330
|  | Person days per year (average of last 3 years) | 16673
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) | 66
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) | 33.61
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) | 43.94
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) | 425.22
|  | Multi cropped (Ha) | 37.38
|  | Current fallow(Ha) | 10.96
|  | Forest /Plantation (Ha) | 430.78
|  | Waste land (Ha) | 0
|  | Impounded Waterbody (Ha) | 32.3
|  | Others (Ha) | 64.97
F |  | LAND CLASSIFICATION
|  | Forest (Ha) | 430.78
|  | Upland (Ha) | 149
|  | Medium land (Ha) | 137
|  | Low Land (Ha) | 215.15
|  | River Stream Length (m) | 5000
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds | 14 Nos
|  | Borewells | 29 Nos
|  | Open wells | 9 Nos
H |  | Livelihood profile
|  | Agriculture | 62%
|  | Off Farm Activities | 11%
|  | Wages, labour | 21%
|  | Business | 2%
|  | Service/ job | 4%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) | 53.1 |  | Considering 40% Water requirement will be met by Rainfall
|  | Total Water Available (Ham) | 2.66
|  | Water Resource to be created (Ham) | 50.365
|  | Water Resourse Planned ( Ha M) | 54.89
|  | % of Water requirment fulfilled though MWS | 109%
J |  | EXPECTED OUTCOME
|  | Increase in Cropping area (in Ha) |  | 58
|  | Increase in Irrigated area (in Ha) |  | 148
|  | Income Enhancement (INR 50,000 per annum as additional income) |  | 49
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Beneficiary | No. | Dimension |  |  | Estimated cost (lakh) | Estimated labour cost | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
|  |  |  | Length (m) | Width (m) | Depth (m) | Lakh Rs. | Lakh Rs. | days | in Ha | in decimal
Individual Works:
1 | Farm Pond | csluk vk- vks/kh | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2475 | 83.4613 | 1
2 | Farm Pond | ,rok vk- csluk | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2474 | 83.4621 | 1
3 | Farm Pond | lksukj vk- vks/kh | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2457 | 83.4639 | 1
4 | Farm Pond | lksek: vk- larlk; | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2414 | 8.4765 | 1
5 | Farm Pond | eqaMjk vk- Qwypan | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2425 | 83.4776 | 1
6 | Farm Pond | cq<mq vk- eqaMjk | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2302 | 83.4675 | 1
7 | Farm Pond | iaM: jke vk- lanjk; | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2473 | 83.462 | 1
8 | Farm Pond | lnkjke vk- vka/kh | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2469 | 83.4627 | 1
9 | Farm Pond | lq[ku jke vk0 uxk; | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2501 | 83.4684 | 1
10 | Farm Pond | VqbZpk vk0 tru | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2327 | 83.4726 | 1
11 | Farm Pond | csluk vk- vks/kh | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2327 | 83.4603 | 1
12 | Farm Pond | ,rok vk- csluk | 1 | 30 | 30 | 3 | 2.8 | 2.8 | 1609 | 1.9 | 23.2327 | 83.448 | 1
13 | Dug Well | lksukj vk- vks/kh | 1 | 0 | 3 | 7 | 2.15 | 1.03 | 591 | 1 | 23.2476 | 83.4615 | 3
14 | Land levelling | lksek: vk- larlk; | 1 | 32 | 23 | 0.3 | 0.32 | 0.32 | 183 | 0 | 23.2442 | 83.4533 | 1
15 | Land levelling | eqaMjk vk- Qwypan | 1 | 37 | 22 | 0.3 | 0.36 | 0.36 | 206 | 0 | 23.2462 | 83.469 | 1
16 | Land levelling | cq<mq vk- eqaMjk | 1 | 41 | 33 | 0.3 | 0.59 | 0.59 | 339 | 0 | 23.2447 | 83.4754 | 1
17 | Land levelling | iaM: jke vk- lanjk; | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.2445 | 83.4725 | 1
18 | Land levelling | lnkjke vk- vka/kh | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.2413 | 83.4649 | 1
19 | Land levelling | lq[ku jke vk0 uxk; | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.2463 | 83.4619 | 1
20 | Land levelling | VqbZpk vk0 tru | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.2475 | 83.4613 | 1
21 | Land levelling | csluk vk- vks/kh | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.2457 | 83.4639 | 1
22 | Land levelling | ,rok vk- csluk | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.2442 | 83.4533 | 1
23 | Land levelling | lksukj vk- vks/kh | 1 | 54 | 32 | 0.3 | 0.76 | 0.76 | 436 | 0 | 23.248 | 83.4667 | 1
24 | Land levelling | lksek: vk- larlk; | 1 | 51 | 89 | 0.3 | 1.99 | 1.99 | 1143 | 0 | 23.2459 | 83.4666 | 1
25 | Land levelling | eqaMjk vk- Qwypan | 1 | 51 | 89 | 0.3 | 1.99 | 1.99 | 1143 | 0 | 23.2327 | 83.4726 | 1
26 | Land levelling | cq<mq vk- eqaMjk | 1 | 51 | 89 | 0.3 | 1.99 | 1.99 | 1143 | 0 | 23.2469 | 83.4627 | 1
27 | Land levelling | iaM: jke vk- lanjk; | 1 | 51 | 89 | 0.3 | 1.99 | 1.99 | 1143 | 0 | 23.248 | 83.4667 | 1
28 | Land levelling | lnkjke vk- vka/kh | 1 | 51 | 89 | 0.3 | 1.99 | 1.99 | 1143 | 0 | 23.2473 | 83.462 | 1
29 | Land levelling | lq[ku jke vk0 uxk; | 1 | 43 | 78 | 0.3 | 1.47 | 1.47 | 844 | 0 | 23.2473 | 83.462 | 1
30 | Land levelling | VqbZpk vk0 tru | 1 | 40 | 92 | 0.3 | 1.62 | 1.62 | 931 | 0 | 23.2457 | 83.4639 | 1
31 | Land levelling | csluk vk- vks/kh | 1 | 41 | 43 | 0.3 | 0.77 | 0.77 | 442 | 0 | 23.2442 | 83.4533 | 1
32 | Land levelling | ,rok vk- csluk | 1 | 41 | 58 | 0.3 | 1.04 | 1.04 | 597 | 0 | 23.2501 | 83.4684 | 1
33 | Land levelling | lksukj vk- vks/kh | 1 | 41 | 34 | 0.3 | 0.61 | 0.61 | 350 | 0 | 23.248 | 83.4667 | 1
34 | Land levelling | lksek: vk- larlk; | 1 | 32 | 61 | 0.3 | 0.86 | 0.86 | 494 | 0 | 23°14´52˝ | 83°27´35˝ | 1
35 | Land levelling | eqaMjk vk- Qwypan | 1 | 53 | 39 | 0.3 | 0.91 | 0.91 | 522 | 0 | 23.2476 | 83.4615 | 1
36 | Land levelling | cq<mq vk- eqaMjk | 1 | 50 | 63 | 0.3 | 1.38 | 1.38 | 793 | 0 | 23.2476 | 83.4615 | 1
37 | Land levelling | iaM: jke vk- lanjk; | 1 | 50 | 84 | 0.3 | 1.85 | 1.85 | 1063 | 0 | 23.2474 | 83.4621 | 1
38 | Land levelling | lnkjke vk- vka/kh | 1 | 50 | 90 | 0.3 | 1.98 | 1.98 | 1137 | 0 | 23.2474 | 83.4621 | 1
39 | Land levelling | बिचकू राम/खिन राम | 1 | 33 | 62 | 0.3 | 0.9 | 0.9 | 517 | 0 | 23.2459 | 83.4666 | 1
40 | Land levelling | बिचकू राम/खिन राम | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2459 | 83.4666 | 1
41 | Land levelling | मेडसाय/सुरगिन | 1 | 55 | 77 | 0.3 | 1.86 | 1.86 | 1068 | 0 | 23.2469 | 83.4627 | 1
42 | Land levelling | मेडसाय/सुरगिन | 1 | 72 | 85 | 0.3 | 2.69 | 2.69 | 1545 | 0 | 23.248 | 83.4667 | 1
43 | Land levelling | धीरन राम /टीरू राम | 1 | 43 | 44 | 0.3 | 0.83 | 0.83 | 477 | 0 | 23.2501 | 83.4684 | 1
44 | Land levelling | धीरन राम /टीरू राम | 1 | 71 | 42 | 0.3 | 1.31 | 1.31 | 752 | 0 | 23.2459 | 83.4666 | 1
45 | Land levelling | हीरा सिंह/ कबरू राम | 1 | 37 | 68 | 0.3 | 1.11 | 1.11 | 637 | 0 | 23.2374 | 83.4711 | 1
46 | Land levelling | हीरा सिंह/ कबरू राम | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2327 | 83.4726 | 1
47 | Land levelling | सोमार साय /ठूठा राम | 1 | 33 | 62 | 0.3 | 0.9 | 0.9 | 517 | 0 | 23.2459 | 83.4666 | 1
48 | Land levelling | सोमार साय /ठूठा राम | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2459 | 83.4666 | 1
49 | Land levelling | सोमार साय /ठूठा राम | 1 | 55 | 77 | 0.3 | 1.86 | 1.86 | 1068 | 0 | 23.2469 | 83.4627 | 1
50 | Land levelling | चक्रधारी/ बागर साय | 1 | 72 | 85 | 0.3 | 2.69 | 2.69 | 1545 | 0 | 23.248 | 83.4667 | 1
51 | Land levelling | चक्रधारी/ बागर साय | 1 | 43 | 44 | 0.3 | 0.83 | 0.83 | 477 | 0 | 23.2501 | 83.4684 | 1
52 | Land levelling | राम साय/डोकरी | 1 | 71 | 42 | 0.3 | 1.31 | 1.31 | 752 | 0 | 23.2459 | 83.4666 | 1
53 | Land levelling | राम साय/डोकरी | 1 | 37 | 68 | 0.3 | 1.11 | 1.11 | 637 | 0 | 23.2374 | 83.4711 | 1
54 | Land levelling | नानकुंवर/गोनसाय | 1 | 33 | 62 | 0.3 | 0.9 | 0.9 | 517 | 0 | 23.2459 | 83.4666 | 1
55 | Land levelling | नानकुंवर/गोनसाय | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2459 | 83.4666 | 1
56 | Land levelling | नानकुंवर/गोनसाय | 1 | 55 | 77 | 0.3 | 1.86 | 1.86 | 1068 | 0 | 23.2469 | 83.4627 | 1
57 | Land levelling | बिहारी/टीरू राम | 1 | 72 | 85 | 0.3 | 2.69 | 2.69 | 1545 | 0 | 23.248 | 83.4667 | 1
58 | Land levelling | बिहारी/टीरू राम | 1 | 43 | 44 | 0.3 | 0.83 | 0.83 | 477 | 0 | 23.2501 | 83.4684 | 1
59 | Land levelling | बिहारी/टीरू राम | 1 | 71 | 42 | 0.3 | 1.31 | 1.31 | 752 | 0 | 23.2459 | 83.4666 | 1
60 | Land levelling | सोमारी/रामा | 1 | 37 | 68 | 0.3 | 1.11 | 1.11 | 637 | 0 | 23.2374 | 83.4711 | 1
61 | Land levelling | सोमारी/रामा | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2327 | 83.4726 | 1
62 | Land levelling | दसरू/रोपन | 1 | 33 | 62 | 0.3 | 0.9 | 0.9 | 517 | 0 | 23.2459 | 83.4666 | 1
63 | Land levelling | दसरू/रोपन | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2459 | 83.4666 | 1
64 | Land levelling | घासी/भीखा | 1 | 55 | 77 | 0.3 | 1.86 | 1.86 | 1068 | 0 | 23.2469 | 83.4627 | 1
65 | Land levelling | घासी/भीखा | 1 | 72 | 85 | 0.3 | 2.69 | 2.69 | 1545 | 0 | 23.248 | 83.4667 | 1
66 | Land levelling | लक्ष्मण/दशरथ | 1 | 43 | 44 | 0.3 | 0.83 | 0.83 | 477 | 0 | 23.2501 | 83.4684 | 1
67 | Land levelling | लक्ष्मण/दशरथ | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2459 | 83.4666 | 1
68 | Land levelling | पारसनाथ/सोमार साय | 1 | 55 | 77 | 0.3 | 1.86 | 1.86 | 1068 | 0 | 23.2469 | 83.4627 | 1
69 | Land levelling | पारसनाथ/सोमार साय | 1 | 72 | 85 | 0.3 | 2.69 | 2.69 | 1545 | 0 | 23.248 | 83.4667 | 1
70 | Land levelling | पारसनाथ/सोमार साय | 1 | 43 | 44 | 0.3 | 0.83 | 0.83 | 477 | 0 | 23.2501 | 83.4684 | 1
71 | Land levelling | सोल्डू/चमरा | 1 | 71 | 42 | 0.3 | 1.31 | 1.31 | 752 | 0 | 23.2459 | 83.4666 | 1
72 | Land levelling | सोल्डू/चमरा | 1 | 37 | 68 | 0.3 | 1.11 | 1.11 | 637 | 0 | 23.2374 | 83.4711 | 1
73 | Land levelling | अमरसाय/पड़हन | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2327 | 83.4726 | 1
74 | Land levelling | अमरसाय/पड़हन | 1 | 33 | 62 | 0.3 | 0.9 | 0.9 | 517 | 0 | 23.2459 | 83.4666 | 1
75 | Land levelling | कुंवरसाय/सोहरसाय | 1 | 32 | 36 | 0.3 | 0.51 | 0.51 | 293 | 0 | 23.2459 | 83.4666 | 1
76 | Land levelling | कुंवरसाय/सोहरसाय | 1 | 55 | 77 | 0.3 | 1.86 | 1.86 | 1068 | 0 | 23.2469 | 83.4627 | 1
Total |  |  | 76 |  |  |  | 112.31 | 111.19 | 63863 | 23.8 |  |  | 78

## NREGA Data (hidden)
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Baspattar | [5 empty] | As on 10-06-2020
I Job Card
Total No. of JobCards issued | 302
Total No. of Workers | 1445
Total No. of Active Job Cards | 291
Total No. of Active Workers | 1329
(i)SC worker against active workers[%] | 1.05
(ii)ST worker against active workers[%] | 65.46
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9390 | 37789 | 32713 | 34769 | 15342
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 1.66 | 1.37 | 1.13 | 0.89 | 1.1
ST persondays % as of total persondays | 54.1 | 50.59 | 53.89 | 51.82 | 44.81
Women Persondays out of Total (%) | 47.74 | 48.15 | 47.82 | 51.61 | 51.3
Average days of employment provided per Household | 42.49 | 133.06 | 115.19 | 124.18 | 57.25
Average Wage rate per day per person(Rs.) | 189.85 | 175.93 | 174 | 172 | 167
Total No of HHs completed 100 Days of Wage Employment | 0 | 233 | 204 | 198 | 23
Total Households Worked | 221 | 284 | 284 | 280 | 268
Total Individuals Worked | 455 | 627 | 617 | 606 | 555
Differently abled persons worked | 1 | 4 | 0 | 1 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 47 | 75 | 117 | 85 | 80
Number of Ongoing Works | 19 | 41 | 42 | 44 | 41
Number of Completed Works | 28 | 34 | 75 | 41 | 39
% of NRM Expenditure(Public + Individual) | 83.17 | 85.02 | 77.45 | 86.74 | 69.31
% of Category B Works | 85.11 | 90.67 | 94.02 | 82.35 | 80
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 33.78 | 70.99 | 62.08 | 68.25 | 28.57
Wages(Rs. In Lakhs) | 25.31 | 60.5 | 55.2 | 59.49 | 24.23
Material and skilled Wages(Rs. In Lakhs) | 8.28 | 9.83 | 6.08 | 7.78 | 3.46
Material(%) | 24.65 | 13.98 | 9.92 | 11.56 | 12.51
Total Adm Expenditure (Rs. in Lakhs.) | 0.18 | 0.66 | 0.8 | 0.98 | 0.88
Admin Exp(%) | 0.53 | 0.93 | 1.29 | 1.44 | 3.08
Average Cost Per Day Per Person(In Rs.) | 193.08 | 202 | 176.44 | 195.03 | 178.38
% of Total Expenditure through EFMS | 100 | 100 | 99.98 | 99.73 | 100
% payments gererated within 15 days | 100 | 79.31 | 90.55 | 100 | 45.71

## Calculation (hidden)
Tentative treated area calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | capacity/ volume (In Cum) | Command area (Irrigated Area ) | Minimum required catchment area | Area Treated
|  |  | Dimenssion | in m | in m | in m | In Cum | in Ha | In Ha | In Ha
1 | Farm Pond | शामकुंवर/रामबिशेष | 23X23X3 | 25 | 25 | 3 | 1491.87 | 0.74594 | 1.4919 | 2.2378
2 | Farm Pond | बंदीराम/दयाराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
3 | Farm Pond | आत्माराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
4 | Farm Pond | आत्माराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
5 | Farm Pond | कमितला बाई/सुकडू | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
6 | Farm Pond | बंदीराम/दयाराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
7 | Farm Pond | चैनबती मरकाम/रामदयाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
8 | Farm Pond | रामदयाल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
9 | Farm Pond | सुकमन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
10 | Farm Pond | भागबती | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
11 | Farm Pond | नारायण | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
12 | Farm Pond | नारद | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
13 | Farm Pond | गनेशिया बाई/आनंद राम सोनी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
14 | Farm Pond | नारायण मरकाम/मेहत्तर | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
15 | Farm Pond | सुकलाईन/धनसिंग विश्वकर्मा | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
16 | Farm Pond | बरमन कुलदीप/कंगलाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
17 | Farm Pond | दसरु राम यादव/मेहत्तर यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
18 | Farm Pond | रमेश सोनवानी/राजकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
19 | Farm Pond | पीलादास मरकाम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
20 | Farm Pond | दयमोतीन नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
21 | Farm Pond | अघनसिंह नेताम/तिजिया नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
22 | Farm Pond | रामसिंह वट्टी/केशरी बाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
23 | Farm Pond | प्रभुराम वट्टी/स्वयं | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
24 | Farm Pond | लतखोरीन नेताम/छेरका | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
25 | Farm Pond | मनराखन यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
26 | Farm Pond | मन्नूराम भास्कर/झंगन सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
27 | Farm Pond | पुष्कर/नथेला राम यादव | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
28 | Farm Pond | लक्ष्मी लाल/गनेशिया | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
29 | Farm Pond | नोहर सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
30 | Farm Pond | नोहर सिंह | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
31 | Farm Pond | राजकुमार/सोनूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
32 | Farm Pond | राम/हलाल राम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
33 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
34 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
35 | Farm Pond | झाड़ूराम/लादूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
36 | Farm Pond | झाड़ूराम/लादूराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
37 | Farm Pond | नोहरसिंह/मसिया | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
38 | Farm Pond | फूलसिंह/हीरासिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
39 | Farm Pond | उदेराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
40 | Farm Pond | लक्ष्मण | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
41 | Farm Pond | पिलाराम/रामभरोष | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
42 | Farm Pond | धनीराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
43 | Farm Pond | चमरसिंह /सुरेखा नेताम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
44 | Farm Pond | रामनाथ/रमतुला वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
45 | Farm Pond | नन्दकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
46 | Farm Pond | चमरसिंह/सगन बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
47 | Farm Pond | जयलाल नेताम/अघनबाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
48 | Farm Pond | सुकबाई यादव/स्वयं | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
49 | Farm Pond | सुकबाई यादव/स्वयं | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
50 | Farm Pond | रामजी/मानकी वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
51 | Farm Pond | नवल सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
52 | Farm Pond | नवल यादव/दल्ली यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
53 | Farm Pond | दुर्जन यादव/दिनदयाल | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
54 | Farm Pond | धनेश यादव/धर्मिन | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
55 | Farm Pond | धनेश यादव/धर्मिन | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
56 | Farm Pond | गुहाराम यादव/अहिल्या | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
57 | Farm Pond | छन्नू राम/उषा बाई | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
58 | Farm Pond | छन्नू राम/उषा बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
59 | Farm Pond | लालसाय मंडावी | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
60 | Farm Pond | लक्ष्मीनाथ नेताम/बैजनतीन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
61 | Farm Pond | रामबती/सुकलाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
62 | Farm Pond | शांति बाई/रामसिंग | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
63 | Farm Pond | बिन्देसिंह/रोहीदास | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
64 | Farm Pond | अमरोबाई/रामजी | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
65 | Farm Pond | जयराम/रामचंद | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
66 | Farm Pond | सन्तुराम मंडावी/सवित्री | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
67 | Farm Pond | आनंदराम नेताम/दुखिया | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
68 | Farm Pond | आनंदराम नेताम/दुखिया | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
69 | Farm Pond | दुखिया नेताम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
70 | Farm Pond | संग्राम/रामसिंह | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
71 | Farm Pond | कनसी/सैदर | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
72 | Farm Pond | किसनू/जोहन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
73 | Farm Pond | कौशिल्या/दीपल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
74 | Farm Pond | प्रवीण मरकाम/रामचंद | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
75 | Land levelling | रूपनाथ मरकाम/परमिला मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
76 | Land levelling | राजाराम मरकाम/चंद्रिका मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
77 | Land levelling | अनीत मरकाम/बृजबती | 1.01 | 1.01 | [5 empty] | 1.01
78 | Land levelling | नीलम कुमार/सगारो बाई | 0.8 | 0.8 | [5 empty] | 0.8
79 | Land levelling | अघनसिंह नेताम/तिजिया नेताम | 0.4 | 0.4 | [5 empty] | 0.4
80 | Land levelling | रूपराय मरकाम/रेमा मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
81 | Land levelling | मोहनराम वट्टी/भवनतीन वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
82 | Land levelling | प्रभुराम वट्टी/स्वयं | 0.4 | 0.4 | [5 empty] | 0.4
83 | Land levelling | रामसिंह वट्टी/केशरी बाई | 0.4 | 0.4 | [5 empty] | 0.4
84 | Land levelling | सगनी/देवराज मरकाम | 0.4 | 0.4 | [5 empty] | 0.4
85 | Land levelling | अमरसिंह/परमिला | 0.4 | 0.4 | [5 empty] | 0.4
86 | Land levelling | उदेराम | 0.8 | 0.8 | [5 empty] | 0.8
87 | Land levelling | रामनाथ/रमतुला वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
88 | Land levelling | धनीराम | 0.8 | 0.8 | [5 empty] | 0.8
89 | Land levelling | श्री राम/दयाबती | 0.2 | 0.2 | [5 empty] | 0.2
90 | Land levelling | चमरसिंह/सगन बाई | 0.8 | 0.8 | [5 empty] | 0.8
91 | Land levelling | जयलाल नेताम/अघनबाई | 0.8 | 0.8 | [5 empty] | 0.8
92 | Land levelling | रामजी/मानकी वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
93 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
94 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
95 | Land levelling | लक्ष्मीनाथ नेताम/बैजनतीन | 0.4 | 0.4 | [5 empty] | 0.4
96 | Land levelling | संगीता/राम नेताम | 0.04 | 0.04 | [5 empty] | 0.04
97 | Land levelling | राजूराम/रामसिंग | 0.8 | 0.8 | [5 empty] | 0.8
98 | Land levelling | जयराम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
99 | Land levelling | सिरमो/छेदीलाल | 0.4 | 0.4 | [5 empty] | 0.4
100 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.5 | 0.5 | [5 empty] | 0.5
101 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.4 | 0.4 | [5 empty] | 0.4
102 | Land levelling | लक्ष्मीनाथ/बैजन्तीन | 0.4 | 0.4 | [5 empty] | 0.4
103 | Land levelling | संग्राम/रामसिंह | 0.04 | 0.04 | [5 empty] | 0.04
104 | Plantation | मन्नूराम भास्कर/झंगन सिंह | 0.4 | 0.4 | [5 empty] | 0.4
105 | Plantation | सुकबाई यादव/स्वयं | 0.2 | 0.2 | [5 empty] | 0.2
106 | Plantation | दुर्जन यादव/दिनदयाल | 0.5 | 0.5 | [5 empty] | 0.5
107 | Plantation | धनेश यादव/धर्मिन | 0.5 | 0.5 | [5 empty] | 0.5
108 | Plantation | गुहाराम यादव/अहिल्या | 0.5 | 0.5 | [5 empty] | 0.5
109 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  | as per Field data |  | 1
110 | Dug Well | नारद/जयलाल | 7X7 | 7 | 7 |  |  |  |  | 1
111 | Dug Well | आत्माराम | 7X7 | 7 | 7 |  |  |  |  | 1
112 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  |  |  | 1
113 | Dug Well | बंदीराम/दयाराम | 7X7 | 7 | 7 |  |  |  |  | 1
114 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
115 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
116 | Dug Well | नारायण | 7X7 | 7 | 7 |  |  |  |  | 1
117 | Dug Well | सुकमन | 7X7 | 7 | 7 |  |  |  |  | 1
118 | Dug Well | भागबती | 7X7 | 7 | 7 |  |  |  |  | 1
119 | Dug Well | दशोबाई | 7X7 | 7 | 7 |  |  |  |  | 1
120 | Dug Well | नरेश | 7X7 | 7 | 7 |  |  |  |  | 1
121 | Dug Well | शामकुंवर/रामबिशेष | 7X7 | 7 | 7 |  |  |  |  | 1
122 | Dug Well | गनेशिया बाई/आनंद राम सोनी | 7X7 | 7 | 7 |  |  |  |  | 1
123 | Dug Well | माखन यादव/तिभू | 7X7 | 7 | 7 |  |  |  |  | 1
124 | Dug Well | तीजऊ राम यादव/बिसऊराम | 7X7 | 7 | 7 |  |  |  |  | 1
125 | Dug Well | सुकलाईन/धनसिंग विश्वकर्मा | 7X7 | 7 | 7 |  |  |  |  | 1
126 | Dug Well | बरमन कुलदीप/कंगलाराम | 7X7 | 7 | 7 |  |  |  |  | 1
127 | Dug Well | रामबाई सोनवानी/तुलीया राम सोनवानी | 7X7 | 7 | 7 |  |  |  |  | 1
128 | Dug Well | भगवान सिंह मरकाम/ | 7X7 | 7 | 7 |  |  |  |  | 1
129 | Dug Well | केशव मरकाम/बिराजो मरकाम | 7X7 | 7 | 7 |  |  |  |  | 1
130 | Dug Well | शिवनारायण यादव/रजमन | 7X7 | 7 | 7 |  |  |  |  | 1
131 | Dug Well | लतखोरीन नेताम/छेरका | 7X7 | 7 | 7 |  |  |  |  | 1
132 | Dug Well | श्याम लाल यादव/लतखोर | 7X7 | 7 | 7 |  |  |  |  | 1
133 | Dug Well | मन्नूराम भास्कर/झंगन सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
134 | Dug Well | मोती राम सोनी/मोहन लाल | 7X7 | 7 | 7 |  |  |  |  | 1
135 | Dug Well | राजकुमार/सोनूराम | 7X7 | 7 | 7 |  |  |  |  | 1
136 | Dug Well | झाड़ूराम/लादूराम | 7X7 | 7 | 7 |  |  |  |  | 1
137 | Dug Well | नोहरसिंह/मसिया | 7X7 | 7 | 7 |  |  |  |  | 1
138 | Dug Well | अर्जुन/दीनदयाल | 7X7 | 7 | 7 |  |  |  |  | 1
139 | Dug Well | छन्नू राम | 7X7 | 7 | 7 |  |  |  |  | 1
140 | Dug Well | उदेराम | 7X7 | 7 | 7 |  |  |  |  | 1
141 | Dug Well | लक्ष्मण | 7X7 | 7 | 7 |  |  |  |  | 1
142 | Dug Well | पिलाराम/रामभरोष | 7X7 | 7 | 7 |  |  |  |  | 1
143 | Dug Well | श्री राम/दयाबती | 7X7 | 7 | 7 |  |  |  |  | 1
144 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
145 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
146 | Dug Well | माखन यादव/तीजू यादव | 7X7 | 7 | 7 |  |  |  |  | 1
147 | Dug Well | नवल सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
148 | Dug Well | नवल यादव/दल्ली यादव | 7X7 | 7 | 7 |  |  |  |  | 1
149 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
150 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
151 | Dug Well | गुहाराम यादव/अहिल्या | 7X7 | 7 | 7 |  |  |  |  | 1
152 | Dug Well | लालसाय मंडावी | 7X7 | 7 | 7 |  |  |  |  | 1
153 | Dug Well | तुलसी/सुकलाल | 7X7 | 7 | 7 |  |  |  |  | 1
154 | Dug Well | कांशीराम/सैदर | 7X7 | 7 | 7 |  |  |  |  | 1
155 | Dug Well | किसून/जोहन | 7X7 | 7 | 7 |  |  |  |  | 1
156 | Dug Well | कौश्लिया/दीपल | 7X7 | 7 | 7 |  |  |  |  | 1
157 | Dug Well | प्रवीण मरकाम/रामचंद | 7X7 | 7 | 7 |  |  |  |  | 1
158 | Farm bonding | संगीता/श्रीराम | 0.4 | 0.4 | [5 empty] | 0.4
159 | Farm bonding | श्यामलाल/मेहेरसिंह | 0.4 | 0.4 | [5 empty] | 0.4
160 | Farm bonding | प्रवीण मरकाम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
161 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
162 | Desilting | common Land | 45X45X4 | 45 | 45 | 4 | 6421.3511 | 3.2107 | 6.4214 | 9.632
163 | Desilting | common Land | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
164 | Desilting | common Land | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
165 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
166 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1 | Command area as per actual field data (Minimum command area
167 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1
168 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7500 | 13.5 |  | 2 |  | Time of refills X (Submergence area* d/3)
169 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 8750 | 15.75 |  | 2 |  | Time of refills X (Submergence area* d/3)
170 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7200 | 12.96 |  | 2 |  | Time of refills X (Submergence area* d/3)
171 | Checkdam | 3rd Order Nala | 25X 40X1.5 | 25 | 125 | 2 | 8700 | 15.66 |  | 2 |  | Time of refills X (Submergence area* d/3)
172 | Checkdam | 3rd Order Nala | 25X 40X1.6 | 25 | 125 | 2 | 9800 | 17.64 |  | 2 |  | Time of refills X (Submergence area* d/3)
[7 empty] | 237159.0111 | 173.1145 | 195.209 | 372.0235
23.7159

## Sheet1 (hidden)
Earthwork Calculation
| Step | Length m | Width m | Depth m | Volume m3
Hard soil depth
| Step 1 | 23 | 23 | 0.3 | 158.7 | 17.6
| Step 2 | 22.4 | 22.4 | 0.3 | 150.528 | 22.4
| Step 3 | 21.8 | 21.8 | 0.3 | 142.572 | 21.8
| Step 4 | 21.2 | 21.2 | 0.3 | 134.832 | 16.6
| Step 5 | 20.6 | 20.6 | 0.3 | 127.308 | 16
| Step 6 | 20 | 20 | 0.3 | 120 | 20
3 | Step 7 | 19.4 | 19.4 | 0.3 | 112.908 | 19.4
| Step 8 | 18.8 | 18.8 | 0.3 | 106.032 | 18.8
| Step 9 | 18.2 | 18.2 | 0.3 | 99.372 | 18.2
23 | Step 10 | 17.6 | 17.6 | 0.3 | 92.928 | 17.6
23 | Total Earthwork in Cum |  |  |  | 1245.18