## e-DPR
e-DPR of Sheri GP, Block - Bharatpur , District- Koriya, Chhattisgarh
A |  | Back ground profile
|  | Micro Watershed code |  | 2A5G8g4,2A5G8n2, 2A5G8n3
|  | District |  | Koriya
|  | Block |  | Bharatpur
|  | Gram Panchayat |  | Sheri
|  | Villages Covered |  | Sheri, Uchehra, Tikaritola
B |  | PHYSIOGRAPHIC PROFILE
|  | Total Area (Ha) |  | 722.2
|  | Rainfall (mm) |  | 1053.5
|  | Soil type |  | Sandy Loam
|  | Average Slope |  | 5-6%, 8-12%
|  | Details of Tributaries |  | Devnha - 2km, Jhonga -1km, Patnha -0.8km,Ghorbarha - 0.8km, Jamori -0.8km, Sirtal - 0.7km, Nararidhara nala-2km, Anjanidhara nala -2km, Barjhorki nala -0.7km
C |  | DEMOGRAPHIC PROFILE
|  | Total Population |  | 1339
|  | Total HouseHolds |  | 418 (As per HHs baseline survey)
|  | ST Population |  | 917
|  | SC Population |  | 0
D |  | MGNREGA Status
|  | NREGA Job card holders |  | 257
|  | Person days per year (average of last 3 years) |  | 12848
|  | Total No of HHs completed 100 Days of Wage Employment (average of last 3 years) |  | 42
|  | Total annual Exp(Rs. in Lakhs.)(average of last 3 years) |  | 35.52
|  | % of NRM Expenditure(Public + Individual) (average of last 3 years) |  | 51.64%
E |  | LAND USE LAND COVER
|  | Mono cropped (Ha) |  | 260.1
|  | Multi cropped (Ha) |  | 9.3
|  | Current fallow(Ha) |  | 53.9
|  | Forest /Plantation (Ha) |  | 197.8
|  | Waste land (Ha) |  | 37.4
|  | Impounded Waterbody (Ha) |  | 1.5
|  | Others (Ha) |  | 163.7
F |  | LAND CLASSIFICATION
|  | Forest (Ha) |  | 197.8
|  | Upland (Ha) |  | 249.63
|  | Medium land (Ha) |  | 374.3
|  | Low Land (Ha) |  | 98.27
|  | River Stream Length (m) |  | 10800
G |  | Existing Water sources/ Structures
|  | Water harvesting Ponds |  | 18
|  | Borewells |  | 0
|  | Open wells |  | 134
H |  | Livelihood profile
|  | Agriculture- Paddy,Maize,Kodo,Wheat,Vegaetable,Pigeon pea |  | 57%
|  | Off Farm Activities- |  | 5%
|  | Wages, labour |  | 36%
|  | Business |  | 1%
|  | Service/ job |  | 1%
I |  | WATER BUDGET
|  | Total Water Requirement (Ham) |  | 66.288
|  | Total Water Available (Ham) |  | 20.828
|  | Water Resource to be created (Ham) |  | 45.46
|  | Water Resourse Planned ( Ha M) |  | 64.342
|  | % of Water requirment fulfilled though MWS |  | 141.5%
J |  | EXPECTED OUTCOME
|  | Increase in Cropping area (in Ha) |  | 23
|  | Increase in Irrigated area (in Ha) |  | 22
|  | Income Enhancement (INR 50,000 per annum as additional income) |  | 32 HHs
K |  | ACTIVITY PROPOSED
Sr No. | Type of intervention | Name of the Beneficiary |  | No. | Dimension |  |  | Estimated cost (lakh) | Estimated labour cost | Persondays Projected | Treated area | Lat. | Long. | Targeted HH
[5 empty] | Length (m) | Width (m) | Depth (m) | Lakh Rs. | Lakh Rs. | days | in Ha |  | in decimal
Individual Works: |  | Owner Name | Husband/father Name
Sheri
1 | मेद्बंधान | रोहिणी | रामेश्वर | 1 | 600 | 1.15 | 0.75 | 1.201 | 1.12 | 643.6782 | 2 | 23º39.860'N | 81º48.5860'E | 1
2 | मेद्बंधान | गयाप्रसाद | आ.इन्द्रमान - | 1 | 120 | 1.15 | 0.75 | 0.265 | 0.23 | 132.1839 | 0.8 | 23º39.3020' | 81º48.9130'E | 1
3 | मेद्बंधान | नाथू | आ.मुडिया - | 1 | 200 | 1.15 | 0.75 | 0.423 | 0.38 | 218.3908 | 0.62 | 23º39.1580' | 81º48.9920'E | 1
4 | मेद्बंधान | श्यासुन्दर | आ.राम सिंह बुटी वेवा राम सिंह | 1 | 165 | 1.15 | 0.75 | 0.35 | 0.31 | 178.1609 | 0.52 | 23º39.1510' | 81º49.20'E | 1
5 | मेद्बंधान | हीरालाल श्रीलाल शिवप्रसाद | आ.मोहन | 1 | 200 | 1.15 | 0.75 | 0.42 | 0.377 | 216.6667 | 0.81 | 23º39.1290' | 81º49.380'E | 1
6 | मेद्बंधान | रामेश्वर | आ.इन्द्रमान - | 1 | 275 | 1.15 | 0.75 | 0.58 | 0.53 | 304.5977 | 1.01 | 23º39.760' | 81º49.2350'E | 1
7 | मेद्बंधान | रोहिणी प्रसाद, गेदनी प्रसाद | पि.रामेश्वर - | 1 | 240 | 1.15 | 0.75 | 0.496 | 0.45 | 258.6207 | 0.4 | 23º39.920' | 81º49.2490'E | 1
8 | बोल्डर चेक | मनटोलिया वि. | छमधारी | 2 | 5 | 2.5 | 1 | 0.115 | 0.1 | 57.4713 | 0.44 | 23º39.1050' | 81º49.3030'E | 2
9 | मेद्बंधान | मनटोलिया वि. | छमधारी | 1 | 100 | 1.15 | 0.75 | 0.225 | 0.192 | 110.3448 |  | 23º39.1050' | 81º49.3030'E | 1
10 | मेद्बंधान | सियाशरण, जगदीश | दशोदिया बेवा भीमसेन, सुदामा,रामकलेश, | 1 | 100 | 1.15 | 0.75 | 0.225 | 0.192 | 110.3448 | 0.05 | 23º39.2890' | 81º49.3650'E | 1
11 | अरदन गली प्लग | सियाशरण, जगदीश | दशोदिया बेवा भीमसेन, सुदामा,रामकलेश, | 1 | 5 | 3 | 1 | 0.019 | 0.013 | 7.4713 | 0.05 | 23º39.2890' | 81º49.3650'E | 1
12 | मेद्बंधान | बाबूलाल | आ.चोर्रा - | 1 | 100 | 1.15 | 0.75 | 0.225 | 0.192 | 110.3448 | 0.17 | 23º39.2880' | 81º49.3680'E | 1
13 | मेद्बंधान | नन्दलाल, चन्द्रिका मुकेश | बेबा राममिलन - | 1 | 195 | 1.15 | 0.75 | 0.412 | 0.37 | 212.6437 | 1.1 | 23392830N | 81496990E | 1
14 | मेद्बंधान | सुर्दशन चरकू सुद्धू | आ.सुकाली - | 1 | 150 | 1.15 | 0.75 | 0.328 | 0.29 | 166.6667 | 0.77 | 23º39.5200' | 81º49.8100'E | 1
15 | मेद्बंधान | जीतराम | आ.ठाकुरदीन - | 1 | 110 | 1.15 | 0.75 | 0.244 | 0.21 | 120.6897 | 0.39 | 23º39.5430' | 81º49.8730'E | 1
16 | गेबियन | सोहनलाल | नत्थूलाल - | 1 | 4 | 3 | 1 | 0.564 | 0.374 | 214.9425 | 2.54 | 23º39.4530' | 81º49.7960'E | 2
17 | मेद्बंधान | जीतराम | आ.ठाकुरदीन - | 1 | 80 | 1.15 | 0.75 | 0.192 | 0.16 | 91.954 | 0.28 | 23º39.4200' | 81º49.7910'E | 1
18 | गेबियन | भरतलाल, राजीवलोचन, मुन्नी,श्यामवती, दद्दी | पि.दददी;सुमित्रा बेवा दददी | 1 | 4 | 3 | 1 | 0.564 | 0.374 | 214.9425 | 0.48 | 23º39.4060' | 81º49.7660'E | 2
19 | मेद्बंधान | महिपाल | आ.रामसहाय - | 1 | 165 | 1.15 | 0.75 | 0.349 | 0.31 | 178.1609 | 0.47 | 23º39.3600'N | 81º49.7960'E | 1
20 | मेद्बंधान | सूरजदीन | आ.विजवा - | 1 | 90 | 1.15 | 0.75 | 0.199 | 0.167 | 95.977 | 0.58 | 23º39.3620'N | 81º49.8440'E | 1
21 | मेद्बंधान | भगवन्ता आ. धमधारी, महेश, रमेश आ. सहदेव | बुटन पि.सहदेव, धमधारी | 1 | 80 | 1.15 | 0.75 | 0.179 | 0.148 | 85.0575 | 0.37 | 23º37.3130' | 81º49.8980'E | 1
22 | मेद्बंधान | महीपाल | आ.रामसहाय - | 1 | 60 | 1.15 | 0.75 | 0.138 | 0.11 | 63.2184 | 0.22 | 23º39.3130' | 81º50.0'E | 1
23 | मेद्बंधान | रामनन्दन आ निरपहा, गयाप्रसाद आ इन्द्रमान | आ.इन्द्रमान | 1 | 160 | 1.15 | 0.75 | 0.357 | 0.317 | 182.1839 | 1.32 | 23º39.3160' | 81º50.30'E | 1
24 | मेद्बंधान | भगवन्ता | आ.छत्रधारी - | 1 | 240 | 1.15 | 0.75 | 0.505 | 0.458 | 263.2184 | 1.23 | 23º39.4050' | 81º50.1010'E | 1
25 | मेद्बंधान | रमेश नरेश पि. बैसाखू, सुखमंती बेवा बैसाखू | जेठू पि.दीनदयाल,बुटई बेवा दीनदयाल | 1 | 150 | 1.15 | 0.75 | 0.324 | 0.286 | 164.3678 | 0.41 | 23º39.5970' | 81º50.1130'E | 1
26 | मेद्बंधान | रामचरन | पि.गोपाल बाबूलाल पि.गोपालबिकनूपि.गोपाल | 1 | 50 | 1.15 | 0.75 | 0.112 | 0.092 | 52.8736 | 1.81 | 23º39.5740' | 81º50.1160'E | 1
27 | मेद्बंधान | नन्दलाल चनद्रिका मुकेश आ. राममिलन तिजउआ | बेबा राममिलन - | 1 | 110 | 1.15 | 0.75 | 0.244 | 0.21 | 120.6897 | 0.15 | 23º39.493' | 81º50.1340'E | 1
28 | मेद्बंधान | भैकू रमेश कोदू | आ.मेहीलाल - | 1 | 595 | 1.15 | 0.75 | 0.917 | 0.828 | 475.8621 | 1.21 | 23º39.3770' | 81º50.2840'E | 1
29 | मेद्बंधान | तेजभान, सत्यदेव, ददोल, पिता इन्द्रभान, मु ममता बैवा | सूरजभान,नाबा.रिंकू,राधा,ࣿ पि.सूरजभान,पा.मॉ ममता | 1 | 100 | 1.15 | 0.75 | 0.23 | 0.197 | 113.2184 | 0.25 | 23º39.2420' | 81º50.420'E | 1
30 | मेद्बंधान | हीरालाल, श्रीलाल शिवप्रसाद | मोहन | 1 | 70 | 1.15 | 0.75 | 0.159 | 0.13 | 74.7126 | 0.11 | 23º39.2640' | 81º49.9580'E | 1
31 | मेद्बंधान | रामरचन | पि.गोपाल बाबूलाल पि.गोपालबिकनूपि.गोपाल | 1 | 50 | 1.15 | 0.75 | 0.121 | 0.093 | 53.4483 | 0.17 | 23º39.2430' | 81º49.9730'E | 1
32 | मेद्बंधान | मोतीलाल पि. चरका, सुखसेन पि. चरका बालकरन | पि.चरका समतिया बेबा चरका | 1 | 90 | 1.15 | 0.75 | 0.197 | 0.166 | 95.4023 | 0.18 | 23º39.2140' | 81º49.9050'E | 1
33 | मेद्बंधान | हीरालाल श्रीलाल शिवप्रसाद | आ मोहन | 1 | 90 | 1.15 | 0.75 | 0.198 | 0.166 | 95.4023 | 0.16 | 23º39.2260' | 81º49.9030'E | 1
34 | मेद्बंधान | तेजभान, सत्यदेव, ददोल, पिता इन्द्रभान, मु ममता बैवा | सूरजभान,नाबा.रिंकू,राधा,ࣿ पि.सूरजभान,पा.मॉ ममता | 1 | 250 | 1.15 | 0.75 | 0.328 | 0.29 | 166.6667 | 0.42 | 23º39.2560' | 81º49.8730'E | 1
35 | मेद्बंधान | श्यामलाल | आ.लालमनी - | 1 | 40 | 1.15 | 0.75 | 0.071 | 0.046 | 26.4368 | 0.72 | 23º39.2650' | 81º49.8670'E | 1
36 | मेद्बंधान | राममिलन | आ. दधी | 1 | 180 | 1.15 | 0.75 | 0.244 | 0.21 | 120.6897 | 1.01 | 23º39.2620' | 81º49.8300'E | 1
37 | मेद्बंधान | भगवन्ता आ धमधारी महेश रमेश आ सहदेव | बुटन पि.सहदेव - | 1 | 70 | 1.15 | 0.75 | 0.108 | 0.081 | 46.5517 | 0.97 | 23º39.3000' | 81º49.8150'E | 1
38 | मेद्बंधान | महिपाल | आ.रामसहाय - | 1 | 120 | 1.15 | 0.75 | 0.17 | 0.14 | 80.4598 | 0.17 | 23º39.3450' | 81º49.7850'E | 1
39 | मेद्बंधान | श्यामलाल | आ.लालमनी - | 1 | 360 | 1.15 | 0.75 | 0.47 | 0.425 | 244.2529 | 1.11 | 23º39.3330' | 81º49.7800'E | 1
40 | मेद्बंधान | मिठाईलाल | आ.मेरू - | 1 | 350 | 1.15 | 0.75 | 0.458 | 0.414 | 237.931 | 1.46 | 23º39.1570' | 81º49.8710'E | 1
41 | मेद्बंधान | मोतीलाल | आ.चरमा | 1 | 220 | 1.15 | 0.75 | 0.297 | 0.26 | 149.4253 | 1.18 | 23º39.1810' | 81º49.7300'E | 1
42 | मेद्बंधान | भीमसेन रामप्रसाद | पि.बालमीक समतिया बेबा बाल्मीक | 1 | 275 | 1.15 | 0.75 | 0.365 | 0.325 | 186.7816 | 1.22 | 23º39.900' | 81º49.7600'E | 1
43 | मेद्बंधान | चरकु | आ.सलाकी - | 1 | 25 | 1.15 | 0.75 | 0.053 | 0.029 | 16.6667 | 1.45 | 23º39.590' | 81º49.8830'E | 1
44 | मेद्बंधान | भगवन्ता आ। धमधारी महेश रमेश आ सहदेव | बुटन पि.सहदेव - | 1 | 50 | 1.15 | 0.75 | 0.091 | 0.065 | 37.3563 | 0.15 | 23º39.960' | 81º49.9540'E | 1
45 | मेद्बंधान | कलावती | रामजियावन बैगा | 1 | 80 | 1.15 | 0.75 | 0.217 | 0.185 | 106.3218 | 0.46 | 23º39.5040' | 81º50.2380'E | 1
46 | मेद्बंधान | भगवन्ता आ. धमधारी, महेश, रमेश आ. सहदेव | बुटन पि.सहदेव - | 1 | 630 | 1.15 | 0.75 | 0.799 | 0.737 | 423.5632 | 1.52 | 23º39.2120' | 81º50.2420'E | 1
47 | डबरी निर्माण कार्य | जयमंत्री | रामसुंदर | 1 | 25 | 25 | 3 | 2.4059 | 2.1934 | 1154.4 |  | 23.6304 | 81.8455 | 2
Common Works:
Sheri
1 | स्टॉप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 12 | 2.25 | 1.5 | 13.02 | 4.05 | 2327.5862 | 0.44 | 23º39.2880'N | 81º48.8750'E | 5
2 | अरदन गली प्लग | शासकीय भूमि | शासकीय भूमि | 5 | 3 | 3 | 1 | 0.047 | 0.04 | 22.9885 | 0.15 | 23º39.3010'N | 81º48.9010'E | 3
3 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 2 | 5 | 3 | 1 | 0.115 | 0.1 | 57.4713 | 0.72 | 23º39.7000'N | 81º49.2460'E | 2
4 | गेबियन | शासकीय भूमि | शासकीय भूमि | 1 | 4 | 3 | 1 | 0.564 | 0.374 | 214.9425 | 0.69 | 23º39.5210'N | 81º49.8140'E | 2
5 | गेबियन | शासकीय भूमि | शासकीय भूमि | 1 | 4 | 3 | 1 | 0.564 | 0.374 | 214.9425 | 0.76 | 23º39.5620' | 81º49.8660'E | 2
6 | स्टॉप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 12 | 2.15 | 2 | 15.01 | 4.68 | 2689.6552 | 4.29 | 23º39.2520'N | 81º49.7490'E | 6
7 | तालाब गहरीकरण कार्य राजा तालाब | शासकीय भूमि | शासकीय भूमि | 1 | 50 | 50 | 3 | 3.7534 | 3.3968 | 1787.764 | 3.5 | 23.6534 | 81.8335 | 6
8 | अर्दन गली प्लग निमार्ण कार्य उचेहरा | शासकीय भूमि | शासकीय भूमि | 3 | 10 | 3 | 1.1 | 0.37 | 0.35 | 184.2105 | 1 | 23.6515 | 81.9329 | 2
9 | vatksyk Vsad fuekZ.k dk;Z ¼05 ux½ | शासकीय भूमि | शासकीय भूमि | 5 | 3 | 3 | 0.5 | 0.38 | 0.1064 | 56 | - | 23.6546 | 81.8216 | 5
10 | cksYMj psd Mse fuekZ.k dk;Z [k-u- 179 | शासकीय भूमि | शासकीय भूमि | 15 | 14 | 2.5 | 1 | 4.7374 | 3.3497 | 1763.0263 | 15 | 23.6515 | 81.8329 | 15
11 | lkeqnkf;d eos'kh vkJ; LFky fuekZ.k dk;Z | शासकीय भूमि | शासकीय भूमि | 1 | 100 | 80 |  | 8.04 | 4.22 | 2221.0526 | - | 23.6542 | 81.8221 | 15
12 | LVkWi Mse es xkn fudk'kh fuekZ.k dk;Z lsjh | शासकीय भूमि | शासकीय भूमि | 1 | 300 | 15 | 1.1 | 6.188 | 5.813 | 3059.48 | 1.5 | 23.6528 | 81.8222 | 17
13 | Hkw oehZ dEiksLV VSad fuekZ.k 10 ux | शासकीय भूमि | शासकीय भूमि | 10 |  |  |  | 0.16 | 0.1 | 52.6316 | - | 23.6547 | 81.8214 | 10
Individual Works:
Tikritola
1 | मेढबधान | राजेन्द्र | रतिराम | 1 | 360 | 1.15 | 0.75 | 0.47 | 0.425 | 244.2529 | 0.76 | 23°38.4198'N | 81°49.1510'E | 1
2 | मेढबधान | राजाराम | बंशरूप | 1 | 165 | 1.15 | 0.75 | 0.231 | 0.198 | 113.7931 | 0.32 | 23°38.4350'N | 81°49.2530'E | 1
3 | मेढबधान | राजेन्द्र | रतिराम | 1 | 420 | 1.15 | 0.75 | 0.539 | 0.49 | 281.6092 | 2.07 | 23°38.4050'N | 81°49.2410'E | 1
4 | अर्देन गलीप्लग | राजेन्द्र | रतिराम | 2 | 6 | 3 | 1 | 0.039 | 0.032 | 18.3908 | 0.7 | 23°38.3930'N | 81°49.2040'E | 1
5 | मेढबधान | लालबहादूर | बेचन | 1 | 100 | 1.15 | 0.75 | 0.153 | 0.123 | 70.6897 | 3.07 | 23°38.3120'N | 81°49.2610'E | 1
6 | डबरी | लालबहादूर | बेचन | 1 | 20 | 20 | 3 | 2.14 | 1.84 | 1057.4713 | 0.85 | 23°38.2720'N | 81°49.3550'E | 2
7 | मेढबधान | इन्द्रजीत | श्यामलाल | 1 | 280 | 1.15 | 0.75 | 0.375 | 0.335 | 192.5287 | 2.84 | 23°38.1380'N | 81°49.4880'E | 1
8 | डबरी | इन्द्रजीत | श्यामलाल | 1 | 25 | 25 | 3 | 3.46 | 3.01 | 1729.8851 | 1.5 | 23°38.1760'N | 81°49.4570'E | 2
9 | मेढबधान | इन्द्रजीत | श्यामलाल | 1 | 120 | 1.15 | 0.75 | 0.178 | 0.148 | 85.0575 | 0.7 | 23°38.1230'N | 81°49.4740'E | 1
10 | मेढबधान | कांशी | हीरलाल | 1 | 800 | 1.15 | 0.75 | 1.009 | 0.936 | 537.931 | 4.23 | 23°38.1540'N | 81°49.5330'E | 1
11 | मेढबधान | मायाराम | मंघौउ | 1 | 200 | 1.15 | 0.75 | 0.276 | 0.24 | 137.931 | 4.05 | 23°38.2930'N | 81°49.5770'E | 1
12 | मेढबधान | चन्द्रप्रताप | बब्बू | 1 | 260 | 1.15 | 0.75 | 0.35 | 0.31 | 178.1609 | 0.56 | 23°38.1330'N | 81°49.7750'E | 1
13 | कुआ | कैलाश | महासिंघ | 1 |  |  |  | 1.8 | 1.08 | 620.6897 | 0.32 | 23°38.3620'N | 81°49.7280'E | 2
14 | मेढबधान | मोहन | श्रीनंदन | 1 | 275 | 1.15 | 0.75 | 0.365 | 0.325 | 186.7816 | 1.38 | 23°38.2910'N | 81°49.8800'E | 1
15 | मेढबधान | हिंचपती | रामकरन | 1 | 90 | 1.15 | 0.75 | 0.14 | 0.11 | 63.2184 | 0.23 | 23°38.3710'N | 81°49.7760'E | 1
16 | मेढबधान | हीरालाल | जगभन | 1 | 330 | 1.15 | 0.75 | 0.433 | 0.39 | 224.1379 | 0.72 | 23°38.3600'N | 81°49.8450'E | 1
17 | मेढबधान | हिंचपती | रामकरन | 1 | 240 | 1.15 | 0.75 | 0.328 | 0.29 | 166.6667 | 0.62 | 23°38.3620'N | 81°49.4440'E | 1
18 | मेढबधान | भइयालाल | हिंचपती | 1 | 160 | 1.15 | 0.75 | 0.229 | 0.196 | 112.6437 | 0.88 | 23°38.3450'N | 81°49.8830'E | 1
19 | मेढबधान | मंघौउ | बिहारी | 1 | 260 | 1.15 | 0.75 | 0.35 | 0.31 | 178.1609 | 2.81 | 23°38.2310'N | 81°49.9150'E | 1
20 | मेढबधान | ननहु | गमौउ | 1 | 260 | 1.15 | 0.75 | 0.35 | 0.31 | 178.1609 | 0.89 | 23°38.1890'N | 81°49.9490'E | 1
21 | मेढबधान | हीरालाल | जगभन | 1 | 120 | 1.15 | 0.75 | 0.17 | 0.14 | 80.4598 | 0.24 | 23°38.3140'N | 81°50.0820'E | 1
22 | मेढबधान | हिंचपती | रामकरन | 1 | 188 | 1.15 | 0.75 | 0.255 | 0.22 | 126.4368 | 0.56 | 23°38.2770'N | 81°50.0970'E | 1
23 | मेढबधान | कैलाश | महासिंघ | 1 | 200 | 1.15 | 0.75 | 0.275 | 0.24 | 137.931 | 0.28 | 23°38.0790'N | 81°50.0280'E | 1
24 | मेढबधान | भगवनति | सवनाराम | 1 | 90 | 1.15 | 0.75 | 0.149 | 0.12 | 68.9655 | 0.98 | 23°38.0100'N | 81°50.1610'E | 1
25 | मेढबधान | गननु | हरबजन | 1 | 80 | 1.15 | 0.75 | 0.133 | 0.105 | 60.3448 | 0.36 | 23°38.0190'N | 81°50.1810'E | 1
26 | बोलडर चेक | गननु | हरबजन | 2 | 10 | 2.5 | 1 | 0.22 | 0.2 | 114.9425 |  | 23°38.0190'N | 81°50.1810'E | 2
27 | बोलडर चेक | रूपसिंह | छत्रधारी | 4 | 10 | 2.5 | 1 | 0.43 | 0.4 | 229.8851 | 1.39 | 23°38'4.90"N | 81°50'11.88"E | 3
28 | मेढबधान | रामबली | प्यारेलाल | 1 | 400 | 1.15 | 0.75 | 0.518 | 0.47 | 270.1149 | 1.75 | 23°38.1090'N | 81°50.1940'E | 1
29 | बोलडर चेक | रामबली | प्यारेलाल | 2 | 10 | 2.5 | 1 | 0.22 | 0.2 | 114.9425 | 1.99 | 23°38'6.88"N | 81°50'12.24"E | 2
30 | मेढबधान | रामप्रसाद | चरकू | 1 | 120 | 1.15 | 0.75 | 0.18 | 0.15 | 86.2069 | 0.98 | 23°38.2060'N | 81°50.1360'E | 1
31 | डबरी | अमरसिंघ | समयलाल | 1 | 20 | 20 | 3 | 2.14 | 1.84 | 1057.4713 | 1.2 | 23°38.2290'N | 81°50.1640'E | 2
32 | मेढबधान | अमरसिंघ | समयलाल | 1 | 165 | 1.15 | 0.75 | 0.233 | 0.2 | 114.9425 | 1.4 | 23°38.2290'N | 81°50.1640'E | 1
33 | मेढबधान | पंजाब | धनकुधारी | 1 | 80 | 1.15 | 0.75 | 0.138 | 0.11 | 63.2184 | 0.9 | 23°38.2910'N | 81°50.1990'E | 1
34 | मेढबधान | गननु | हरबजन | 1 | 165 | 1.15 | 0.75 | 0.233 | 0.2 | 114.9425 | 0.6 | 23°38.2190'N | 81°50.1970'E | 1
35 | मेढबधान | मोहन | श्रीनंदन | 1 | 100 | 1.15 | 0.75 | 0.153 | 0.123 | 70.6897 | 0.53 | 23°38.1750'N | 81°50.2180'E | 1
36 | मेढबधान | रूपसिंघ | छत्रधारी | 1 | 90 | 1.15 | 0.75 | 0.15 | 0.12 | 68.9655 | 0.52 | 23°38.0860'N | 81°50.1980'E | 1
37 | मेढबधान | अमरसिंघ | समयलाल | 1 | 100 | 1.15 | 0.75 | 0.15 | 0.12 | 68.9655 | 0.22 | 23°38.1000'N | 81°50.2940'E | 1
38 | मेढबधान | शिवप्रसाद | कठकू | 1 | 420 | 1.15 | 0.75 | 0.844 | 0.78 | 448.2759 | 1.88 | 23°38.1010'N | 81°50.2990'E | 1
39 | मेढबधान | लालबहादूर | बेचन | 1 | 70 | 1.15 | 0.75 | 0.17 | 0.14 | 80.4598 | 1.25 | 23°38.1220'N | 81°50.4400'E | 1
40 | मेढबधान | चंदरभनसिंघ | प्यारेलाल | 1 | 210 | 1.15 | 0.75 | 0.44 | 0.4 | 229.8851 | 2.63 | 23°38.1240'N | 81°50.4920'E | 1
41 | मेढबधान | बबुआ | रामसुंदर | 1 | 90 | 1.15 | 0.75 | 0.212 | 0.18 | 103.4483 | 1.48 | 23°38.1710'N | 81°50.5110'E | 1
42 | मेढबधान | भगवतसिंघ | बबनसिंह | 1 | 150 | 1.15 | 0.75 | 0.318 | 0.28 | 160.9195 | 0.51 | 23°38.1340'N | 81°50.5860'E | 1
43 | मेढबधान | प्रीतमसिंघ | बबनसिंह | 1 | 60 | 1.15 | 0.75 | 0.105 | 0.078 | 44.8276 | 0.51 | 23°38.1270'N | 81°50.5900'E | 1
44 | मेढबधान | ठाकुरप्रसाद | बबनसिंह | 1 | 70 | 1.15 | 0.75 | 0.119 | 0.091 | 52.2989 | 0.5 | 23°38.1000'N | 81°50.5870'E | 1
45 | डबरी | बबुआ | रामसुंदर | 1 | 30 | 30 | 3 | 5.16 | 4.52 | 2597.7011 | 0.9 | 23°37.8760'N | 81°50.6850'E | 2
46 | मेढबधान | बबुआ | रामसुंदर | 1 | 80 | 1.15 | 0.75 | 0.12 | 0.092 | 52.8736 |  | 23°37.8420'N | 81°50.7120'E | 1
47 | मेढबधान | गुलबसिया | चंदु | 1 | 90 | 1.15 | 0.75 | 0.15 | 0.12 | 68.9655 | 1.88 | 23°37.9520'N | 81°50.7020'E | 1
48 | डबरी निर्माण कार्य टिकरीटोला | इन्द्रजीत | श्यामलाल | 1 | 25 | 20 | 3 | 2.0359 | 1.8598 | 978.8353 | 1.2 | 23.6361 | 81.8244 | 2
49 | डबरी निर्माण कार्य लाल टिकरीटोला | बहादुर | बेचन | 1 | 25 | 25 | 3 | 2.0309 | 1.8598 | 978.8358 | 1.5 | 23.638 | 81.8225 | 2
Common Works:
Tikritola
1 | 30*40 | शासकीय भूमि | शासकीय भूमि | 1 | 70 | 60 |  | 0.84 | 0.69 | 396.5517 | 0.62 | 23°38.4430'N | 81°49.1270'E | 3
2 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 7 | 6 | 2.5 | 1 | 0.45 | 0.42 | 241.3793 | 1.21 | 23°38.4450'N | 81°49.2680'E | 5
3 | डबरी | शासकीय भूमि | शासकीय भूमि | 1 | 20 | 20 | 3 | 2.14 | 1.84 | 1057.4713 | 0.74 | 23°38.1220'N | 81°49.4870'E | 2
4 | कुॅआ | शासकीय भूमि | शासकीय भूमि | 1 |  |  |  | 1.8 | 1.08 | 620.6897 | 0.43 | 23°38.3370'N | 81°49.8470'E | 2
5 | स्आप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 10 | 2 | 1.3 | 9.16 | 2.87 | 1649.4253 | 2.05 | 23°38.2070'N | 81°50.1780'E | 5
6 | तालाब गहरी करण काय्र्र दर्री पारा टिकरीटोला | शासकीय भूमि | शासकीय भूमि | 1 | 50 | 50 | 3 | 8.9938 | 8.1668 | 4298.3034 | 5.5 | 23.6336 | 81.8415 | 5
Individual Works:
Uchehra
1 | मेढबंधान | ललवा | मिटठू | 1 | 780 | 1.15 | 0.75 | 0.98 | 0.91 | 522.9885 | 3.57 | 23°40.0510'N | 81°52.5510'E | 1
2 | बोल्डर चेक | ललवा | मिटठू | 10 | 4 | 2.5 | 1 | 0.43 | 0.4 | 229.8851 | 1.3 | 23°39.9110'N | 81°52.5400'E | 8
3 | मेढबंधान | रामकुमार | सुखसेन | 1 | 180 | 1.15 | 0.75 | 0.244 | 0.21 | 120.6897 | 0.34 | 23°39.5400'N | 81°52.3440'E | 1
4 | मेढबंधान | रूपसाय | कामोद | 1 | 350 | 1.15 | 0.75 | 0.464 | 0.42 | 241.3793 | 1.02 | 23°39.4730'N | 81°52.1690'E | 1
5 | मेढबंधान | लिल्लू | हरदिया | 1 | 180 | 1.15 | 0.75 | 0.254 | 0.22 | 126.4368 | 0.39 | 23°39.5740'N | 81°52.3540'E | 1
6 | मेढबंधान | छेरका | नन्दलाल | 1 | 50 | 1.15 | 0.75 | 0.091 | 0.065 | 37.3563 | 0.38 | 23°39.5730'N | 81°52.3890'E | 1
7 | मेढबंधान | हरप्रसाद | बुद्धू | 1 | 40 | 1.15 | 0.75 | 0.075 | 0.05 | 28.7356 | 0.11 | 23°39.5610'N | 81°52.3930'E | 1
8 | मेढबंधान | रामलाल | बुद्धू | 1 | 60 | 1.15 | 0.75 | 0.096 | 0.07 | 40.2299 | 0.1 | 23°39.5530'N | 81°52.4030'E | 1
9 | मेढबंधान | चैतु | बुद्धू | 1 | 60 | 1.15 | 0.75 | 0.105 | 0.078 | 44.8276 | 0.13 | 23°39.5530'N | 81°52.4090'E | 1
10 | 30*40 | तानी | रूपसाय | 1 | 80 | 60 |  | 0.666 | 0.55 | 316.092 | 1.39 | 23°39.5340'N | 81°52.4550'E | 4
11 | मेढबंधान | राजेन्द्र | सूरजदीन | 1 | 180 | 1.15 | 0.75 | 0.244 | 0.21 | 120.6897 | 1.12 | 23°39.5030'N | 81°52.4690'E | 1
12 | अर्देन गली प्लग | राजेन्द्र | सूरजदीन | 3 | 3 | 1.15 | 0.75 | 0.046 | 0.04 | 22.9885 | 1.12 | 23°39.5280'N | 81°52.4890'E | 2
13 | मेढबंधान | गीता | बिहारी | 1 | 300 | 1.15 | 0.75 | 0.392 | 0.35 | 201.1494 | 0.77 | 23°39.3870'N | 81°52.5040'E | 1
14 | मेढबंधान | लल्लू | बिहारी | 1 | 120 | 1.15 | 0.75 | 0.18 | 0.15 | 86.2069 | 0.34 | 23°39.3280'N | 81°52.4580'E | 1
15 | मेढबंधान | लल्लू | बिहारी | 1 | 150 | 1.15 | 0.75 | 0.212 | 0.18 | 103.4483 | 1.28 | 23°39.3300'N | 81°52.4580'E | 1
16 | मेढबंधान | लल्लू | बिहारी | 1 | 150 | 1.15 | 0.75 | 0.212 | 0.18 | 103.4483 | 0.59 | 23°39.3220'N | 81°52.5010'E | 1
17 | मेढबंधान | रामावतार | भोंदू | 1 | 150 | 1.15 | 0.75 | 0.212 | 0.18 | 103.4483 | 1.9 | 23°39.0880'N | 81°52.3920'E | 1
18 | कुॅआ | रामवतार | भोंदू | 1 |  |  |  | 1.8 | 1.08 | 620.6897 | 1.9 | 23°39.0870'N | 81°52.4100'E | 2
19 | मेढबंधान | लल्लू | बिहारी | 1 | 80 | 1.15 | 0.75 | 0.138 | 0.11 | 63.2184 | 0.17 | 23°39.2960'N | 81°52.2390'E | 1
20 | मेढबंधान | सिरदार | निन्दा | 1 | 60 | 1.15 | 0.75 | 0.105 | 0.078 | 44.8276 | 1.09 | 23°39.2150'N | 81°52.5170'E | 1
21 | मेढबंधान | चैतु | बुद्धू | 1 | 30 | 1.15 | 0.75 | 0.059 | 0.035 | 20.1149 | 0.11 | 23°39.2070'N | 81°52.4680'E | 1
22 | मेढबंधान | लल्ला | रामप्रसाद | 1 | 70 | 1.15 | 0.75 | 0.119 | 0.092 | 52.8736 | 1.56 | 23°39.1780'N | 81°52.4380'E | 1
23 | मेढबंधान | मुंडा | सम्हन | 1 | 70 | 1.15 | 0.75 | 0.119 | 0.092 | 52.8736 | 0.22 | 23°39.3930'N | 81°52.3300'E | 1
24 | मेढबंधान | हरप्रसाद | बुद्धू | 1 | 240 | 1.15 | 0.75 | 0.328 | 0.29 | 166.6667 | 0.64 | 23°39.3680'N | 81562790'E | 1
25 | मेढबंधान | समेलाल | मोहन | 1 | 90 | 1.15 | 0.75 | 0.138 | 0.11 | 63.2184 | 0.2 | 23°39.3310'N | 81°52.2630'E | 1
26 | कुॅआ | हरप्रसाद | बुद्धू | 1 |  |  |  | 1.8 | 1.08 | 620.6897 | 0.63 | 23°39.3230'N | 81°52.2740'E | 2
27 | मेढबंधान | हरप्रसाद | बुद्धू | 1 | 150 | 1.15 | 0.75 | 0.21 | 0.18 | 103.4483 |  | 23°39.3230'N | 81°52.2740'E | 1
28 | मेढबंधान | मुन्ना | बिहारी | 1 | 80 | 1.15 | 0.75 | 0.12 | 0.1 | 57.4713 | 0.17 | 23°39.3250'N | 81°52.2990'E | 1
29 | मेढबंधान | लल्लू | बिहारी | 1 | 80 | 1.15 | 0.75 | 0.138 | 0.11 | 63.2184 | 0.32 | 23°39.3180'N | 81°52.3050'E | 1
30 | मेढबंधान | केतकी | जंगी | 1 | 90 | 1.15 | 0.75 | 0.139 | 0.11 | 63.2184 | 0.22 | 23°39.3980'N | 81°52.3050'E | 1
31 | मेढबंधान | लल्लू | बिहारी | 1 | 90 | 1.15 | 0.75 | 0.139 | 0.11 | 63.2184 | 0.23 | 23°39.2860'N | 81°52.3070'E | 1
32 | मेढबंधान | लल्लू | बिहारी | 1 | 150 | 1.15 | 0.75 | 0.212 | 0.18 | 103.4483 | 0.3 | 23°39.7060'N | 81°52.2970'E | 1
33 | मेढबंधान | रामकुमार | सुखसेन | 1 | 180 | 1.15 | 0.75 | 0.254 | 0.22 | 126.4368 | 0.32 | 23°39.2980'N | 81°52.2480'E | 1
34 | बोल्डर चेक | चिक्धारी | सुदिन | 10 | 4 | 1.15 | 0.75 | 0.43 | 0.4 | 229.8851 | 0.96 | 23°39.2600'N | 81°52.1840'E | 6
35 | मेढबंधान | सीता | सोनसाय | 1 | 120 | 1.15 | 0.75 | 0.17 | 0.14 | 80.4598 | 0.26 | 23°39.1930'N | 81°52.2090'E | 1
36 | मेढबंधान | सिरदार | निंदा | 1 | 150 | 1.15 | 0.75 | 0.212 | 0.18 | 103.4483 | 0.53 | 23°39.2260'N | 81°52.2220'E | 1
37 | मेढबंधान | रामावतार | दददी | 1 | 325 | 1.15 | 0.75 | 0.433 | 0.39 | 224.1379 | 1.02 | 23°39.1470'N | 81°52.2840'E | 1
38 | मेढबंधान | रामकुमार | सुखसेन | 1 | 200 | 1.15 | 0.75 | 0.275 | 0.24 | 137.931 | 0.38 | 23°39.1600'N | 81°52.2770'E | 1
39 | मेढबंधान | राजेन्द्र | सूरजदीन | 1 | 120 | 1.15 | 0.75 | 0.18 | 0.15 | 86.2069 | 0.52 | 23°39.1280'N | 81°52.2530'E | 1
40 | मेढबंधान | केतकी | जंगी | 1 | 540 | 1.15 | 0.75 | 0.69 | 0.63 | 362.069 | 3.92 | 23°39.0500'N | 81°52.3°39.0'E | 1
41 | मेढबंधान | केतकी | जंगी | 1 | 1140 | 1.15 | 0.75 | 1.41 | 1.32 | 758.6207 | 2.8 | 23°39.0460'N | 81°52.3700'E | 1
42 | डबरी | केतकी | जंगी | 1 | 20 | 20 | 3 | 1.462 | 1.317 | 756.8966 | 0.85 | 23°38'55.20"N | 81°52'21.75"E | 2
43 | मेढबंधान | चिक्धारी | सुदिन | 1 | 2520 | 1.15 | 0.75 | 3.1 | 2.92 | 1678.1609 | 7.35 | 23°39.2410'N | 81°51.3560'E | 1
44 | डबरी | चिक्धारी | सुदिन | 1 | 30 | 30 | 3 | 3.262 | 3.055 | 1755.7471 |  | 23°38'15.79"N | 81°51'19.58"E | 2
45 | कुॅआ | सुखमंती | वंसु | 1 |  |  |  | 1.8 | 1.08 | 620.6897 | 1 | 23°39.2900'N | 81°51.1140'E | 2
46 | मेढबंधान | दलप्रताप | ठाकुरदीन | 1 | 90 | 1.15 | 0.75 | 0.139 | 0.11 | 63.2184 | 0.18 | 23°39.7440'N | 81°51.3360'E | 1
47 | मेढबंधान | सिरदार | निंदा | 1 | 220 | 1.15 | 0.75 | 0.3 | 0.26 | 149.4253 | 0.78 | 23°39.0100'N | 81°51.4890'E | 1
48 | मेढबंधान | रामावतार | दददी | 1 | 325 | 1.15 | 0.75 | 0.423 | 0.38 | 218.3908 | 1.47 | 23°39.0010'N | 81°51.5540'E | 1
49 | मेढबंधान | चैतु | बुद्धू | 1 | 80 | 1.15 | 0.75 | 0.13 | 0.1 | 57.4713 | 0.2 | 23°39.0370'N | 81°51.5840'E | 1
50 | मेढबंधान | रामलाल | बुद्धू | 1 | 30 | 1.15 | 0.75 | 0.059 | 0.035 | 20.1149 | 0.11 | 23°39.0630'N | 81°51.6710'E | 1
51 | मेढबंधान | ब्रिजभान | सुरजबली | 1 | 120 | 1.15 | 0.75 | 0.18 | 0.15 | 86.2069 | 0.45 | 23°39.0570'N | 81°51.6860'E | 1
52 | मेढबंधान | जीवनलाल | लक्ष्मण | 1 | 500 | 1.15 | 0.75 | 0.634 | 0.58 | 333.3333 | 1.39 | 23°39.5360'N | 81°52.1320'E | 1
53 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 5 | 5 | 2.5 | 1 | 0.275 | 0.25 | 143.6782 | 2.5 | 23°39.5610'N | 81°52.1630'E | 3
54 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 5 | 6 | 2.5 | 1 | 0.325 | 0.3 | 172.4138 | 2.5 | 23°39.3210'N | 81°51.9000'E | 3
55 | मेढबंधान | चंद्रप्रताप | बेनसिंग | 1 | 550 | 1.15 | 0.75 | 0.697 | 0.64 | 367.8161 | 2.14 | 23°39.3480'N | 81°51.9030'E | 1
56 | मेढबंधान | बलजीत | सरहा | 1 | 250 | 1.15 | 0.75 | 0.34 | 0.3 | 172.4138 | 2.13 | 23°39.3610'N | 81°51.9090'E | 1
57 | मेढबंधान | सीता | सोनसाय | 1 | 300 | 1.15 | 0.75 | 0.392 | 0.35 | 201.1494 | 0.57 | 23°39.9420'N | 81°51.9900'E | 1
58 | मेढबंधान | मोहन | बुज्जी | 1 | 450 | 1.15 | 0.75 | 0.58 | 0.53 | 304.5977 | 0.74 | 23°39.9520'N | 81°51.9990'E | 1
59 | मेढबंधान | रामबली | धरमजीत | 1 | 300 | 1.15 | 0.75 | 0.392 | 0.35 | 201.1494 | 0.57 | 23°39.9690'N | 81°52.0340'E | 1
60 | मेढबंधान | रामकुमार | सुखसेन | 1 | 400 | 1.15 | 0.75 | 0.517 | 0.47 | 270.1149 | 1.09 | 23°39.9730'N | 81°52.0370'E | 1
61 | मेढबंधान | जट्टी | नंदराम | 1 | 300 | 1.15 | 0.75 | 0.392 | 0.35 | 201.1494 | 0.61 | 23°39.0050'N | 81°52.0860'E | 1
62 | डबरी | रामसुन्दर | श्रीराम | 1 | 25 | 25 | 3 | 3.468 | 3.018 | 1734.4828 | 0.56 | 23°39.9790'N | 81°52.2400'E | 2
63 | मेढबंधान | श्रीराम | महावीर | 1 | 60 | 1.15 | 0.75 | 0.11 | 0.08 | 45.977 | 1.92 | 23°39.1270'N | 81°52.2910'E | 1
64 | मेढबंधान | मोहन | बुज्जी | 1 | 420 | 1.15 | 0.75 | 0.539 | 0.49 | 281.6092 | 1.47 | 23°39.1590'N | 81°52.2470'E | 1
65 | मेढबंधान | रामकुमार | सुखसेन | 1 | 300 | 1.15 | 0.75 | 0.39 | 0.35 | 201.1494 | 1.09 | 23°39.1830'N | 81°52.2800'E | 1
66 | डबरी | जगदीश | वंशधारी | 1 | 25 | 25 | 3 | 3.468 | 3.018 | 1734.4828 | 2.05 | 23°39.0170'N | 81°52.3640'E | 2
67 | डबरी निर्माण कार्य हितग्राही | तीजिया | मोतीलाल | 1 | 20 | 20 | 3 | 1.837 | 1.627 | 856.3158 | 0.85 | 23.6367 | 81.8566 | 2
68 | डबरी निर्माण कार्य | रामहीत | जगदीश | 1 | 20 | 20 | 3 | 2.0536 | 1.8675 | 982.8741 | 0.85 | 23.6334 | 81.873 | 2
69 | डबरी निर्माण कार्य | रामसुन्दर | श्रीदास | 1 | 25 | 25 | 3 | 2.413 | 2.2 | 1157.8947 | 1.5 | 23.6332 | 81.8709 | 2
Common Works:
Uchehra
1 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 5 | 4 | 2.5 | 1 | 0.22 | 0.2 | 114.9425 | 5.65 | 23°40.0750'N | 81°52.5130'E | 3
2 | सीण्सीण्टीण् | शासकीय भूमि | शासकीय भूमि | 1056 | 5 | 0.5 | 0.5 | 0.532 | 0.45 | 258.6207 | 3.6 | 23°40.0400'N | 81°52.6080'E | 5
3 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 2 | 4 | 2.5 | 1 | 0.094 | 0.08 | 45.977 | 0.97 | 23°39.7810'N | 81°52.5210'E | 2
4 | स्टाप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 6 | 2 | 1.5 | 7.97 | 2.5 | 1436.7816 | 0.97 | 23°39.7670'N | 81°52.5640'E | 5
5 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 1 | 5 | 3 | 1 | 0.0625 | 0.05 | 28.7356 | 0.97 | 23.6632 | 81.8752 | 1
6 | सीण्सीण्टीण् | शासकीय भूमि | शासकीय भूमि | 1344 | 5 | 0.5 | 0.5 | 0.66 | 0.57 | 327.5862 | 14.46 | 23°39.7030'N | 81°52.5050'E | 4
7 | स्टाप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 10 | 2 | 1.5 | 10.09 | 3.14 | 1804.5977 | 0.29 | 23°39.5880'N | 81°52.3780'E | 6
8 | स्टाप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 10 | 2 | 1.2 | 7.96 | 2.48 | 1425.2874 | 1.23 | 23°39.5550'N | 81°52.4300'E | 5
9 | 30*40 | शासकीय भूमि | शासकीय भूमि | 1 | 80 | 80 |  | 1.16 | 0.96 | 551.7241 | 2.7 | 23°39.4970'N | 81°52.5390'E | 3
10 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 3 | 3 | 2.5 | 1 | 0.1045 | 0.09 | 51.7241 | 1.11 | 23°39.4070'N | 81°52.6010'E | 2
11 | सीण्सीण्टीण् | शासकीय भूमि | शासकीय भूमि | 326 | 5 | 0.5 | 0.5 | 0.195 | 0.135 | 77.5862 | 2.33 | 23°39.2390'N | 81°52.5410'E | 3
12 | 30*40 | शासकीय भूमि | शासकीय भूमि | 1 | 70 | 60 |  | 0.94 | 0.77 | 442.5287 | 1.04 | 23°39.9720'N | 81°52.1990'E | 3
13 | सीण्सीण्टीण् | शासकीय भूमि | शासकीय भूमि | 357 | 5 | 0.5 | 0.5 | 0.21 | 0.15 | 86.2069 | 1.71 | 23°39.1240'N | 81°52.2010'E | 3
14 | एसण्सीण्टीण् | शासकीय भूमि | शासकीय भूमि | 1200 | 3 | 0.5 | 0.5 | 0.67 | 0.57 | 327.5862 | 12.84 | 23°39.0720'N | 81°52.7730'E | 5
15 | 30*40 | शासकीय भूमि | शासकीय भूमि | 1 | 40 | 50 |  | 0.494 | 0.4 | 229.8851 | 0.55 | 23°39.8350'N | 81°51.2070'E | 3
16 | डबरी | शासकीय भूमि | शासकीय भूमि | 1 | 30 | 30 | 3 | 3.25 | 3.05 | 1752.8736 | 1.76 | 23°39.9840'N | 81°51.4290'E | 2
17 | स्टाप डेम | शासकीय भूमि | शासकीय भूमि | 1 | 12 | 2 | 1.2 | 8.93 | 2.78 | 1597.7011 | 0.39 | 23°39.0570'N | 81°51.6860'E | 5
18 | 30*40 | शासकीय भूमि | शासकीय भूमि | 1 | 70 | 60 |  | 0.827 | 0.68 | 390.8046 | 0.8 | 23°39.3470'N | 81°51.`9030'E | 3
19 | 30*40 | शासकीय भूमि | शासकीय भूमि | 1 | 70 | 60 |  | 0.827 | 0.68 | 390.8046 | 0.63 | 23°39.3210'N | 81°51.9000'E | 3
20 | बोल्डर चेक | शासकीय भूमि | शासकीय भूमि | 5 | 6 | 2.5 | 1 | 0.325 | 0.3 | 172.4138 | 1.63 | 23°39.3210'N | 81°51.9000'E | 3
Total | [7 empty] | 213.8731 | 141.3221 | 79423.5782 | 256.02 |  |  | 391

## NREGA Data (hidden)
State : CHHATTISGARH District : KANKER Block : NARHARPUR Panchayat : Baspattar | [5 empty] | As on 10-06-2020
I Job Card
Total No. of JobCards issued | 302
Total No. of Workers | 1445
Total No. of Active Job Cards | 291
Total No. of Active Workers | 1329
(i)SC worker against active workers[%] | 1.05
(ii)ST worker against active workers[%] | 65.46
II Progress | FY 2020-2021 | FY 2019-2020 | FY 2018-2019 | FY 2017-2018 | FY 2016-2017 | View Graph
Approved Labour Budget | 0 | 0 | 0 | 0 | 0
Persondays Generated so far | 9390 | 37789 | 32713 | 34769 | 15342
% of Total LB | 0 | 0 | 0 | 0 | 0
% as per Proportionate LB | 0
SC persondays % as of total persondays | 1.66 | 1.37 | 1.13 | 0.89 | 1.1
ST persondays % as of total persondays | 54.1 | 50.59 | 53.89 | 51.82 | 44.81
Women Persondays out of Total (%) | 47.74 | 48.15 | 47.82 | 51.61 | 51.3
Average days of employment provided per Household | 42.49 | 133.06 | 115.19 | 124.18 | 57.25
Average Wage rate per day per person(Rs.) | 189.85 | 175.93 | 174 | 172 | 167
Total No of HHs completed 100 Days of Wage Employment | 0 | 233 | 204 | 198 | 23
Total Households Worked | 221 | 284 | 284 | 280 | 268
Total Individuals Worked | 455 | 627 | 617 | 606 | 555
Differently abled persons worked | 1 | 4 | 0 | 1 | 0
III Works
Number of GPs with NIL exp | 0 | 0 | 0 | 0 | 0
Total No. of Works Takenup (New+Spill Over) | 47 | 75 | 117 | 85 | 80
Number of Ongoing Works | 19 | 41 | 42 | 44 | 41
Number of Completed Works | 28 | 34 | 75 | 41 | 39
% of NRM Expenditure(Public + Individual) | 83.17 | 85.02 | 77.45 | 86.74 | 69.31
% of Category B Works | 85.11 | 90.67 | 94.02 | 82.35 | 80
IV Financial Progress
Total Exp(Rs. in Lakhs.) | 33.78 | 70.99 | 62.08 | 68.25 | 28.57
Wages(Rs. In Lakhs) | 25.31 | 60.5 | 55.2 | 59.49 | 24.23
Material and skilled Wages(Rs. In Lakhs) | 8.28 | 9.83 | 6.08 | 7.78 | 3.46
Material(%) | 24.65 | 13.98 | 9.92 | 11.56 | 12.51
Total Adm Expenditure (Rs. in Lakhs.) | 0.18 | 0.66 | 0.8 | 0.98 | 0.88
Admin Exp(%) | 0.53 | 0.93 | 1.29 | 1.44 | 3.08
Average Cost Per Day Per Person(In Rs.) | 193.08 | 202 | 176.44 | 195.03 | 178.38
% of Total Expenditure through EFMS | 100 | 100 | 99.98 | 99.73 | 100
% payments gererated within 15 days | 100 | 79.31 | 90.55 | 100 | 45.71

## Calculation (hidden)
Tentative treated area calculation
Sl No | Type of Structure | Benificiary Name |  | L ength | Bredth | Depth | capacity/ volume (In Cum) | Command area (Irrigated Area ) | Minimum required catchment area | Area Treated
|  |  | Dimenssion | in m | in m | in m | In Cum | in Ha | In Ha | In Ha
1 | Farm Pond | शामकुंवर/रामबिशेष | 23X23X3 | 25 | 25 | 3 | 1491.87 | 0.74594 | 1.4919 | 2.2378
2 | Farm Pond | बंदीराम/दयाराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
3 | Farm Pond | आत्माराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
4 | Farm Pond | आत्माराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
5 | Farm Pond | कमितला बाई/सुकडू | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
6 | Farm Pond | बंदीराम/दयाराम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
7 | Farm Pond | चैनबती मरकाम/रामदयाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
8 | Farm Pond | रामदयाल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
9 | Farm Pond | सुकमन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
10 | Farm Pond | भागबती | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
11 | Farm Pond | नारायण | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
12 | Farm Pond | नारद | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
13 | Farm Pond | गनेशिया बाई/आनंद राम सोनी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
14 | Farm Pond | नारायण मरकाम/मेहत्तर | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
15 | Farm Pond | सुकलाईन/धनसिंग विश्वकर्मा | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
16 | Farm Pond | बरमन कुलदीप/कंगलाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
17 | Farm Pond | दसरु राम यादव/मेहत्तर यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
18 | Farm Pond | रमेश सोनवानी/राजकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
19 | Farm Pond | पीलादास मरकाम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
20 | Farm Pond | दयमोतीन नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
21 | Farm Pond | अघनसिंह नेताम/तिजिया नेताम | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
22 | Farm Pond | रामसिंह वट्टी/केशरी बाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
23 | Farm Pond | प्रभुराम वट्टी/स्वयं | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
24 | Farm Pond | लतखोरीन नेताम/छेरका | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
25 | Farm Pond | मनराखन यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
26 | Farm Pond | मन्नूराम भास्कर/झंगन सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
27 | Farm Pond | पुष्कर/नथेला राम यादव | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
28 | Farm Pond | लक्ष्मी लाल/गनेशिया | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
29 | Farm Pond | नोहर सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
30 | Farm Pond | नोहर सिंह | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
31 | Farm Pond | राजकुमार/सोनूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
32 | Farm Pond | राम/हलाल राम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
33 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
34 | Farm Pond | पांचोबाई/सखाराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
35 | Farm Pond | झाड़ूराम/लादूराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
36 | Farm Pond | झाड़ूराम/लादूराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
37 | Farm Pond | नोहरसिंह/मसिया | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
38 | Farm Pond | फूलसिंह/हीरासिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
39 | Farm Pond | उदेराम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
40 | Farm Pond | लक्ष्मण | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
41 | Farm Pond | पिलाराम/रामभरोष | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
42 | Farm Pond | धनीराम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
43 | Farm Pond | चमरसिंह /सुरेखा नेताम | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
44 | Farm Pond | रामनाथ/रमतुला वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
45 | Farm Pond | नन्दकुमार | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
46 | Farm Pond | चमरसिंह/सगन बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
47 | Farm Pond | जयलाल नेताम/अघनबाई | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
48 | Farm Pond | सुकबाई यादव/स्वयं | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
49 | Farm Pond | सुकबाई यादव/स्वयं | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
50 | Farm Pond | रामजी/मानकी वट्टी | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
51 | Farm Pond | नवल सिंह | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
52 | Farm Pond | नवल यादव/दल्ली यादव | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
53 | Farm Pond | दुर्जन यादव/दिनदयाल | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
54 | Farm Pond | धनेश यादव/धर्मिन | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
55 | Farm Pond | धनेश यादव/धर्मिन | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
56 | Farm Pond | गुहाराम यादव/अहिल्या | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
57 | Farm Pond | छन्नू राम/उषा बाई | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
58 | Farm Pond | छन्नू राम/उषा बाई | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
59 | Farm Pond | लालसाय मंडावी | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
60 | Farm Pond | लक्ष्मीनाथ नेताम/बैजनतीन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
61 | Farm Pond | रामबती/सुकलाल | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
62 | Farm Pond | शांति बाई/रामसिंग | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
63 | Farm Pond | बिन्देसिंह/रोहीदास | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
64 | Farm Pond | अमरोबाई/रामजी | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
65 | Farm Pond | जयराम/रामचंद | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
66 | Farm Pond | सन्तुराम मंडावी/सवित्री | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
67 | Farm Pond | आनंदराम नेताम/दुखिया | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
68 | Farm Pond | आनंदराम नेताम/दुखिया | 30X23X3 | 30 | 23 | 3 | 1662.57 | 0.83129 | 1.6626 | 2.4939
69 | Farm Pond | दुखिया नेताम | 40X40X3 | 40 | 40 | 3 | 4173.87 | 2.0869 | 4.1739 | 6.2608
70 | Farm Pond | संग्राम/रामसिंह | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
71 | Farm Pond | कनसी/सैदर | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
72 | Farm Pond | किसनू/जोहन | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
73 | Farm Pond | कौशिल्या/दीपल | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
74 | Farm Pond | प्रवीण मरकाम/रामचंद | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
75 | Land levelling | रूपनाथ मरकाम/परमिला मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
76 | Land levelling | राजाराम मरकाम/चंद्रिका मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
77 | Land levelling | अनीत मरकाम/बृजबती | 1.01 | 1.01 | [5 empty] | 1.01
78 | Land levelling | नीलम कुमार/सगारो बाई | 0.8 | 0.8 | [5 empty] | 0.8
79 | Land levelling | अघनसिंह नेताम/तिजिया नेताम | 0.4 | 0.4 | [5 empty] | 0.4
80 | Land levelling | रूपराय मरकाम/रेमा मरकाम | 0.8 | 0.8 | [5 empty] | 0.8
81 | Land levelling | मोहनराम वट्टी/भवनतीन वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
82 | Land levelling | प्रभुराम वट्टी/स्वयं | 0.4 | 0.4 | [5 empty] | 0.4
83 | Land levelling | रामसिंह वट्टी/केशरी बाई | 0.4 | 0.4 | [5 empty] | 0.4
84 | Land levelling | सगनी/देवराज मरकाम | 0.4 | 0.4 | [5 empty] | 0.4
85 | Land levelling | अमरसिंह/परमिला | 0.4 | 0.4 | [5 empty] | 0.4
86 | Land levelling | उदेराम | 0.8 | 0.8 | [5 empty] | 0.8
87 | Land levelling | रामनाथ/रमतुला वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
88 | Land levelling | धनीराम | 0.8 | 0.8 | [5 empty] | 0.8
89 | Land levelling | श्री राम/दयाबती | 0.2 | 0.2 | [5 empty] | 0.2
90 | Land levelling | चमरसिंह/सगन बाई | 0.8 | 0.8 | [5 empty] | 0.8
91 | Land levelling | जयलाल नेताम/अघनबाई | 0.8 | 0.8 | [5 empty] | 0.8
92 | Land levelling | रामजी/मानकी वट्टी | 0.4 | 0.4 | [5 empty] | 0.4
93 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
94 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.36 | 0.36 | [5 empty] | 0.36
95 | Land levelling | लक्ष्मीनाथ नेताम/बैजनतीन | 0.4 | 0.4 | [5 empty] | 0.4
96 | Land levelling | संगीता/राम नेताम | 0.04 | 0.04 | [5 empty] | 0.04
97 | Land levelling | राजूराम/रामसिंग | 0.8 | 0.8 | [5 empty] | 0.8
98 | Land levelling | जयराम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
99 | Land levelling | सिरमो/छेदीलाल | 0.4 | 0.4 | [5 empty] | 0.4
100 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.5 | 0.5 | [5 empty] | 0.5
101 | Land levelling | विष्णुराम मंडावी/कुंवरबाई | 0.4 | 0.4 | [5 empty] | 0.4
102 | Land levelling | लक्ष्मीनाथ/बैजन्तीन | 0.4 | 0.4 | [5 empty] | 0.4
103 | Land levelling | संग्राम/रामसिंह | 0.04 | 0.04 | [5 empty] | 0.04
104 | Plantation | मन्नूराम भास्कर/झंगन सिंह | 0.4 | 0.4 | [5 empty] | 0.4
105 | Plantation | सुकबाई यादव/स्वयं | 0.2 | 0.2 | [5 empty] | 0.2
106 | Plantation | दुर्जन यादव/दिनदयाल | 0.5 | 0.5 | [5 empty] | 0.5
107 | Plantation | धनेश यादव/धर्मिन | 0.5 | 0.5 | [5 empty] | 0.5
108 | Plantation | गुहाराम यादव/अहिल्या | 0.5 | 0.5 | [5 empty] | 0.5
109 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  | as per Field data |  | 1
110 | Dug Well | नारद/जयलाल | 7X7 | 7 | 7 |  |  |  |  | 1
111 | Dug Well | आत्माराम | 7X7 | 7 | 7 |  |  |  |  | 1
112 | Dug Well | कमितला बाई/सुकडू | 7X7 | 7 | 7 |  |  |  |  | 1
113 | Dug Well | बंदीराम/दयाराम | 7X7 | 7 | 7 |  |  |  |  | 1
114 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
115 | Dug Well | निर्मला/भारत | 7X7 | 7 | 7 |  |  |  |  | 1
116 | Dug Well | नारायण | 7X7 | 7 | 7 |  |  |  |  | 1
117 | Dug Well | सुकमन | 7X7 | 7 | 7 |  |  |  |  | 1
118 | Dug Well | भागबती | 7X7 | 7 | 7 |  |  |  |  | 1
119 | Dug Well | दशोबाई | 7X7 | 7 | 7 |  |  |  |  | 1
120 | Dug Well | नरेश | 7X7 | 7 | 7 |  |  |  |  | 1
121 | Dug Well | शामकुंवर/रामबिशेष | 7X7 | 7 | 7 |  |  |  |  | 1
122 | Dug Well | गनेशिया बाई/आनंद राम सोनी | 7X7 | 7 | 7 |  |  |  |  | 1
123 | Dug Well | माखन यादव/तिभू | 7X7 | 7 | 7 |  |  |  |  | 1
124 | Dug Well | तीजऊ राम यादव/बिसऊराम | 7X7 | 7 | 7 |  |  |  |  | 1
125 | Dug Well | सुकलाईन/धनसिंग विश्वकर्मा | 7X7 | 7 | 7 |  |  |  |  | 1
126 | Dug Well | बरमन कुलदीप/कंगलाराम | 7X7 | 7 | 7 |  |  |  |  | 1
127 | Dug Well | रामबाई सोनवानी/तुलीया राम सोनवानी | 7X7 | 7 | 7 |  |  |  |  | 1
128 | Dug Well | भगवान सिंह मरकाम/ | 7X7 | 7 | 7 |  |  |  |  | 1
129 | Dug Well | केशव मरकाम/बिराजो मरकाम | 7X7 | 7 | 7 |  |  |  |  | 1
130 | Dug Well | शिवनारायण यादव/रजमन | 7X7 | 7 | 7 |  |  |  |  | 1
131 | Dug Well | लतखोरीन नेताम/छेरका | 7X7 | 7 | 7 |  |  |  |  | 1
132 | Dug Well | श्याम लाल यादव/लतखोर | 7X7 | 7 | 7 |  |  |  |  | 1
133 | Dug Well | मन्नूराम भास्कर/झंगन सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
134 | Dug Well | मोती राम सोनी/मोहन लाल | 7X7 | 7 | 7 |  |  |  |  | 1
135 | Dug Well | राजकुमार/सोनूराम | 7X7 | 7 | 7 |  |  |  |  | 1
136 | Dug Well | झाड़ूराम/लादूराम | 7X7 | 7 | 7 |  |  |  |  | 1
137 | Dug Well | नोहरसिंह/मसिया | 7X7 | 7 | 7 |  |  |  |  | 1
138 | Dug Well | अर्जुन/दीनदयाल | 7X7 | 7 | 7 |  |  |  |  | 1
139 | Dug Well | छन्नू राम | 7X7 | 7 | 7 |  |  |  |  | 1
140 | Dug Well | उदेराम | 7X7 | 7 | 7 |  |  |  |  | 1
141 | Dug Well | लक्ष्मण | 7X7 | 7 | 7 |  |  |  |  | 1
142 | Dug Well | पिलाराम/रामभरोष | 7X7 | 7 | 7 |  |  |  |  | 1
143 | Dug Well | श्री राम/दयाबती | 7X7 | 7 | 7 |  |  |  |  | 1
144 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
145 | Dug Well | सुकबाई यादव/स्वयं | 7X7 | 7 | 7 |  |  |  |  | 1
146 | Dug Well | माखन यादव/तीजू यादव | 7X7 | 7 | 7 |  |  |  |  | 1
147 | Dug Well | नवल सिंह | 7X7 | 7 | 7 |  |  |  |  | 1
148 | Dug Well | नवल यादव/दल्ली यादव | 7X7 | 7 | 7 |  |  |  |  | 1
149 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
150 | Dug Well | धनेश यादव/धर्मिन | 7X7 | 7 | 7 |  |  |  |  | 1
151 | Dug Well | गुहाराम यादव/अहिल्या | 7X7 | 7 | 7 |  |  |  |  | 1
152 | Dug Well | लालसाय मंडावी | 7X7 | 7 | 7 |  |  |  |  | 1
153 | Dug Well | तुलसी/सुकलाल | 7X7 | 7 | 7 |  |  |  |  | 1
154 | Dug Well | कांशीराम/सैदर | 7X7 | 7 | 7 |  |  |  |  | 1
155 | Dug Well | किसून/जोहन | 7X7 | 7 | 7 |  |  |  |  | 1
156 | Dug Well | कौश्लिया/दीपल | 7X7 | 7 | 7 |  |  |  |  | 1
157 | Dug Well | प्रवीण मरकाम/रामचंद | 7X7 | 7 | 7 |  |  |  |  | 1
158 | Farm bonding | संगीता/श्रीराम | 0.4 | 0.4 | [5 empty] | 0.4
159 | Farm bonding | श्यामलाल/मेहेरसिंह | 0.4 | 0.4 | [5 empty] | 0.4
160 | Farm bonding | प्रवीण मरकाम/रामचंद | 0.4 | 0.4 | [5 empty] | 0.4
161 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
162 | Desilting | common Land | 45X45X4 | 45 | 45 | 4 | 6421.3511 | 3.2107 | 6.4214 | 9.632
163 | Desilting | common Land | 23X23X3 | 23 | 23 | 3 | 1236.27 | 0.61813 | 1.2363 | 1.8544
164 | Desilting | common Land | 30X30X3 | 30 | 30 | 3 | 2235.87 | 1.1179 | 2.2359 | 3.3538
165 | Desilting | common Land | 45X45X3 | 45 | 45 | 3 | 5367.87 | 2.6839 | 5.3679 | 8.0518
166 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1 | Command area as per actual field data (Minimum command area
167 | LBS | common Land | 5 X5 X1 | 5 | 5 | 1 | Actual measurement |  |  | 1
168 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7500 | 13.5 |  | 2 |  | Time of refills X (Submergence area* d/3)
169 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 8750 | 15.75 |  | 2 |  | Time of refills X (Submergence area* d/3)
170 | CheckDam | 3rd Order Nala | 15X 25 X1 | 15 | 75 | 1.5 | 7200 | 12.96 |  | 2 |  | Time of refills X (Submergence area* d/3)
171 | Checkdam | 3rd Order Nala | 25X 40X1.5 | 25 | 125 | 2 | 8700 | 15.66 |  | 2 |  | Time of refills X (Submergence area* d/3)
172 | Checkdam | 3rd Order Nala | 25X 40X1.6 | 25 | 125 | 2 | 9800 | 17.64 |  | 2 |  | Time of refills X (Submergence area* d/3)
[7 empty] | 237159.0111 | 173.1145 | 195.209 | 372.0235
23.7159

## Sheet1 (hidden)
Earthwork Calculation
| Step | Length m | Width m | Depth m | Volume m3
Hard soil depth
| Step 1 | 23 | 23 | 0.3 | 158.7 | 17.6
| Step 2 | 22.4 | 22.4 | 0.3 | 150.528 | 22.4
| Step 3 | 21.8 | 21.8 | 0.3 | 142.572 | 21.8
| Step 4 | 21.2 | 21.2 | 0.3 | 134.832 | 16.6
| Step 5 | 20.6 | 20.6 | 0.3 | 127.308 | 16
| Step 6 | 20 | 20 | 0.3 | 120 | 20
3 | Step 7 | 19.4 | 19.4 | 0.3 | 112.908 | 19.4
| Step 8 | 18.8 | 18.8 | 0.3 | 106.032 | 18.8
| Step 9 | 18.2 | 18.2 | 0.3 | 99.372 | 18.2
23 | Step 10 | 17.6 | 17.6 | 0.3 | 92.928 | 17.6
23 | Total Earthwork in Cum |  |  |  | 1245.18